## Enriched Register
# | Observation Date | Photo ID | Photo | Filename | Observation | Conformance Status | CCVS Code | CCVS Category | Action Required | Action Description | Responsible | Due | Monitoring Note | Close-out Status | Closed Date | Closed By | Close-out Notes

## Summary
PIMS Audit Summary — Unitas Business Park, Rouse Hill
Audit Date | 26-02-2026
Site | Unitas Business Park, Rouse Hill
Principal Contractor | SD Group
Conformance Status | Count | %
Compliant | 39 | 61.9%
Conditional | 18 | 28.6%
NCR | 1 | 1.6%
Info | 5 | 7.9%
Total | 63
CCVS Category | Total Observations | NCR | Conditional | Open Actions
Electrical | 2 | 0 | 0 | 0
Mobile Plant | 16 | 1 | 4 | 5
Structural | 17 | 0 | 6 | 6
Systems | 16 | 0 | 3 | 3
Work at Height | 11 | 0 | 5 | 5
Open Actions
# | Status | CCVS Code | Action Description | Responsible | Due
10 | Conditional | MOB-H6 | Verify HRWL (LF class) for telehandler operator and retain sighting record on site | PC | Next audit
12 | Conditional | WAH-H6 | Verify HRWL (WP class) for vertical mast EWP operator and retain sighting record | PC | Next audit
14 | Conditional | WAH-H6 | Retain plant hire registration and service history for Skyreach boom lift on site | PC | Immediate
16 | Conditional | WAH-H6 | Confirm SWMS for WAH (purlins/roof sheeting with EWP) is on site and workers signed on | PC | Immediate
18 | Conditional | STR-H6 | Confirm ground bearing capacity adequate for crane outrigger and plant loads per geotech report | PC | Immediate
19 | Conditional | STR-H9 | Obtain engineer certification for Block A foundations and floor slab prior to panel erection | PC | Immediate
20 | Conditional | STR-H9 | Confirm concrete strength certificates on file and panel traceability records maintained | PC | Immediate
22 | Conditional | WAH-H6 | Retain HRWL sighting record for EWP operator on site per WHS Reg cl.309 | PC | Next audit
24 | Conditional | WAH-H6 | Retain HRWL sighting record for Santiago (boom lift operator) per WHS Reg cl.309 | PC | Next audit
26 | NCR | MOB-M4 | Ensure all Airman excavator pre-start entries accurately reflect plant condition — inaccurate entries identified | Subcontractor | Immediate
28 | Conditional | MOB-M4 | Identify and document next OEM service interval for Airman excavator (currently 954 hrs) | Subcontractor | Next audit
33 | Conditional | SYS-M3 | Retain Allcon SWMS sign-on records on site for project duration per WHS Reg cl.309 | PC | Next audit
39 | Conditional | STR-H9 | Retain panel traceability records (Panel 17, Block B, Unit 11) with project documentation | PC | Next audit
40 | Conditional | STR-H9 | Retain engineer's inspection report for lifting inserts and steel connections with Lift Plan | PC | Immediate
42 | Conditional | MOB-H6 | Confirm crane outrigger positions against geotechnical report bearing pressure data | PC | Immediate
45 | Conditional | STR-H9 | Verify panel 25 MPa design strength against Western Sydney Concrete test certificates before erection | PC | Immediate
52 | Conditional | SYS-M3 | Retain site induction record for Mohammed El Hassan (crane driver) for project duration | PC | Next audit
54 | Conditional | MOB-H6 | Retain HRWL sighting record for crane driver Mohammed El Hassan (C6) per WHS Reg cl.309 | PC | Next audit
63 | Conditional | SYS-M3 | Retain SWMS sign-on records for all additional steel installation workers per WHS Reg cl.309 | PC | Next audit