| Robertson's Remedial and Painting Pty Ltd | Document No: RPD-PR-SVC-001 |
| --- | --- |
| UNDERGROUND AND OVERHEAD SERVICES PROCEDURE | Version: 1.0 ¦ Date: Feb 2025 ¦ Review: Feb 2027 |
| Approved: Leslie Robertson (Director) | Ed.6 Ref: Checklist 5, Appendix B ¦ WHS Reg 2017 Ch.8 Pt.4, Ch.4 Pt.4.7 |

1. Purpose

This procedure sets out how RPD identifies and manages risks from underground and overhead services (electrical, gas, water, sewer, telecommunications) during construction works. It complies with WHS Regulation 2017 and SafeWork NSW Code of Practice: Managing Electrical Risks in the Workplace.

2. Scope

All RPD sites where work is performed near underground services (excavation, penetration, drilling, cutting) or overhead services (powerlines, comms cables). Applies to all workers including subcontractors operating plant.

3. Procedure — Before, During, After

| Phase | # | Action | Who | Record |
| --- | --- | --- | --- | --- |
| BEFORE | 1 | Obtain Dial Before You Dig (DBYD) service plans for the site. Review plans and mark known service routes on site drawings. | Project Manager | DBYD plans |
|  | 2 | Engage licensed utility locator to physically locate, mark and verify services. Use electromagnetic locator + GPR where possible. Mark with paint/flags on ground. | Project Manager | Locator report |
|  | 3 | Identify overhead services: powerlines, comms cables. Determine voltage and No Go Zone distances per Table of No Go Zones (e.g. <1kV = 1m, 1–132kV = 3m, 132–330kV = 6m). | Site Supervisor | Site plan |
|  | 4 | If work within No Go Zone required: request supply authority isolation, install tiger tails/insulated covers, or use spotter + signage. Obtain written approval. | Project Manager | Isolation cert / permit |
|  | 5 | Prepare SWMS addressing: electrocution, gas leak/explosion, service strike flooding, contact with overhead lines by plant/materials. | Site Supervisor | SWMS (Breadcrumb) |
| DURING | 6 | Toolbox talk: brief all workers on service locations, No Go Zones, emergency procedure (gas leak evacuation, electrical contact — stay in cab). All sign on. | Site Supervisor | Toolbox (Breadcrumb) |
|  | 7 | Hand-dig within 500mm of marked underground services. Pot-hole to expose service before mechanical excavation in vicinity. Use non-destructive digging where available. | Excavation crew | — |
|  | 8 | Overhead services: maintain clearances at all times. Height limiters on EWPs/cranes where overhead risk exists. Spotter for plant movements near lines. | Operator / Spotter | — |
|  | 9 | Drilling/coring into walls, floors, ceilings: scan with cable/pipe detector before every penetration. Mark safe drill zones. Assume live until proven otherwise. | All workers | Scan log |
| AFTER | 10 | Backfill around exposed services with appropriate bedding material. Marker tape 300mm above underground services. Reinstate service covers/lids. | Site Supervisor | Inspection (Breadcrumb) |
|  | 11 | Update site drawings with any newly discovered or relocated services. File all records in Breadcrumb project folder. | Project Manager | Updated drawings |

4. Stop Work Triggers  Unidentified service encountered  •  Gas smell detected  •  Water/sewage ingress from unknown source  •  Plant or materials within No Go Zone of powerlines  •  Cable detector indicates live service in drill path  •  Service isolation not confirmed in writing.

5. References:  WHS Act 2011  •  WHS Reg 2017 Ch.8 Pt.4, Ch.4 Pt.4.7  •  SafeWork NSW COP: Managing Electrical Risks  •  SafeWork NSW COP: Excavation Work  •  RPD WHSMS V7 s.4.17  •  HY Standard: Underground and Overhead Services rev8

Generated by Gatekeeper WHS Advisor  •  Benchmarked against Hansen Yuncken Underground and Overhead Services Standard rev8 and SafeWork NSW COPs