## Project Tracker
RPD WHS SYSTEM UPGRADE AND BREADCRUMB MIGRATION — PROJECT TRACKER
Client: Robertson's Remedial and Painting Pty Ltd ¦ Alan @ AuditCo ¦ Project Start: February 2026
Phase | Task | Owner | Target Date | Status | % Complete | Depends On | Deliverable | Notes | Week Updated | Est. Hours | Actual Hours | Cumulative Hrs
1 | Gap analysis: RPD WHSMS V7 vs Ed.6 bare minimum | Alan | 28 Feb 2025 | DONE | 100% | — | Bare Minimum Ed.6 Review (.docx) | Completed. Both ISO and non-ISO versions delivered. |  |  | 4 | 4
1 | Document register: map every V7 form/register to status | Alan | 28 Feb 2025 | DONE | 100% | Gap analysis | Phase 1 Document Register (.xlsx) | 40 items mapped with REPLACE/PARALLEL/RETAIN/CUSTOM BUILD status. |  |  |  | 4
1 | Breadcrumb verification: confirm module capabilities | Alan + RPD | TBD | NOT STARTED | 0% | Document register | Breadcrumb Verification Checklist (Sheet 2 of register) | Requires Breadcrumb login. 15 modules to verify. |  |  |  | 4
1 | Present Phase 1 findings to RPD management | Alan | TBD | NOT STARTED | 0% | Verification | Meeting + status report | Key decision: confirm elimination list and proceed to V8 drafting. |  |  |  | 4
2 | Draft V8 Section 1: Senior Management Commitment | Alan | TBD | NOT STARTED | 0% | Phase 1 sign-off | V8 Section 1 draft (.docx) | Merge policies. Remove ISO content. Plain English. |  |  |  | 4
2 | Draft V8 Section 2: Communication and Consultation | Alan | TBD | NOT STARTED | 0% | Phase 1 sign-off | V8 Section 2 draft (.docx) | Add Breadcrumb references. |  |  |  | 4
2 | Draft V8 Section 3: Managing Service Providers | Alan | TBD | NOT STARTED | 0% | Phase 1 sign-off | V8 Section 3 draft (.docx) | Streamline pre-qual. Reference Breadcrumb contractor module. |  |  |  | 4
2 | Draft V8 Section 4: Risk Management + Procedures | Alan | TBD | NOT STARTED | 0% | Phase 1 sign-off | V8 Section 4 draft + 7 procedures (.docx) | Merge policies+procedures. Include demo procedures (demolition, heights, etc). |  |  |  | 4
2 | Draft V8 Sections 5–11: Training through Records | Alan | TBD | NOT STARTED | 0% | Section 4 draft | V8 Sections 5–11 (.docx) | Merge incident + corrective action. Remove ISO management review inputs. |  |  |  | 4
2 | RPD management review of V8 draft | RPD Director | TBD | NOT STARTED | 0% | All V8 drafts | Marked-up draft + feedback | Leslie Robertson to review and approve. |  |  |  | 4
2 | Issue V8 final | Alan | TBD | NOT STARTED | 0% | Management review | RPD WHSMS V8 (.docx + PDF) | Target: 100–120 pages. Signed by Director. |  |  |  | 4
3 | Configure Breadcrumb: toolbox talks, hazard reports, inspections | Alan + RPD | TBD | NOT STARTED | 0% | Breadcrumb verification | Configured Breadcrumb modules | HIGH priority forms first. |  |  |  | 4
3 | Configure Breadcrumb: inductions, competency tracking | Alan + RPD | TBD | NOT STARTED | 0% | Breadcrumb verification | Configured Breadcrumb modules | Upload existing training/licence data. |  |  |  | 4
3 | Configure Breadcrumb: incidents, corrective actions | Alan + RPD | TBD | NOT STARTED | 0% | Breadcrumb verification | Configured Breadcrumb modules | Test auto-notification for notifiable incidents. |  |  |  | 4
3 | Configure Breadcrumb: contractor management, asset registers | Alan + RPD | TBD | NOT STARTED | 0% | Breadcrumb verification | Configured Breadcrumb modules | Bulk import from existing Excel registers. |  |  |  | 4
3 | Build custom templates (Subcontractor Statement, RTW Plan) | Alan | TBD | NOT STARTED | 0% | Breadcrumb verification | Custom Breadcrumb templates | Only if Breadcrumb can't handle natively. |  |  |  | 4
3 | Parallel run: paper + Breadcrumb side by side (4–8 weeks) | RPD site teams | TBD | NOT STARTED | 0% | All Breadcrumb config | Parallel run log | Minimum 4 weeks for HIGH priority forms, 8 weeks for registers. |  |  |  | 4
4 | Develop re-induction package for V8 + Breadcrumb | Alan | TBD | NOT STARTED | 0% | V8 issued | Induction presentation + quiz | Cover: what changed, why, how to use Breadcrumb, key procedures. |  |  |  | 4
4 | Deliver re-induction to all RPD workers | RPD + Alan | TBD | NOT STARTED | 0% | Re-induction package | Signed induction records (Breadcrumb) | Record in Breadcrumb induction module. |  |  |  | 4
4 | Supervisor training on Breadcrumb admin | Alan + Breadcrumb | TBD | NOT STARTED | 0% | Breadcrumb config | Training records | Site Supervisors + PMs need admin access training. |  |  |  | 4
5 | Withdraw superseded .docx forms (SUPERSEDED watermark) | Alan + RPD | TBD | NOT STARTED | 0% | Parallel run complete | Updated document register | Archive on server. Do not delete. |  |  |  | 4
5 | Post-implementation internal audit (Ed.6 checklists 1–12) | Alan | TBD | NOT STARTED | 0% | V8 + Breadcrumb live | Internal Audit Report (.docx) | Within 3 months of V8 issue. Use RPD audit form (10.3). |  |  |  | 4
5 | Management review meeting | RPD Director + Alan | TBD | NOT STARTED | 0% | Internal audit | Management Review Minutes | Review V8 effectiveness, Breadcrumb adoption, corrective actions. |  |  |  | 4
5 | Close out project | Alan | TBD | NOT STARTED | 0% | Management review | Project close-out report | Confirm Ed.6 compliance. Hand over to RPD for ongoing maintenance. |  |  |  | 4
[9 empty] | TOTALS: | 0 | 4 | 4

## Weekly Status Report
RPD WHS SYSTEM UPGRADE — WEEKLY STATUS REPORT
Week Ending: | 2026-02-27
Prepared By: | Alan @ AuditCo
For: | Leslie Robertson (RPD Director) / Nick V
Project: | RPD WHSMS V8 Upgrade And Breadcrumb Digital Migration
OVERALL PROJECT STATUS
Phase | Description | Status | This Week | Next Week | Risks / Issues
1 | Gap Analysis & Scoping | DONE | Gap analysis and document register completed. Delivered to RPD. | Present findings to RPD management. Schedule Breadcrumb verification session. | None
2 | WHS Management Plan V8 | NOT STARTED | — | Awaiting Phase 1 sign-off before commencing V8 drafting. | Delay if RPD management review takes longer than 1 week.
3 | Form and Template Migration | NOT STARTED | — | Awaiting Breadcrumb verification. | Breadcrumb module gaps could delay migration.
4 | Training and Competency | NOT STARTED | — | — | Scheduling site re-inductions depends on Phase 2+3 completion.
5 | Verification and Close-out | NOT STARTED | — | — | Internal audit timing depends on all prior phases.
KEY ACHIEVEMENTS THIS WEEK
1 | Completed bare minimum Ed.6 gap analysis — 22 sections identified for elimination, 14 forms for Breadcrumb migration.
2 | [Enter achievement]
3 | [Enter achievement]
ACTIONS FOR NEXT WEEK
# | Action | Owner | Due | Priority
1 | Present Phase 1 gap analysis to Leslie Robertson for approval | Alan | [DATE] | HIGH
2 | Schedule Breadcrumb verification session (need login access) | Alan + RPD | [DATE] | HIGH
3 | Confirm elimination list — any items RPD wants to keep despite Ed.6? | Leslie / Alan | [DATE] | MEDIUM
4 | [Enter action] | [Owner] | [DATE]
RISKS & ISSUES
# | Risk / Issue | Impact | Mitigation | Owner
1 | Breadcrumb modules may not cover all RPD requirements | Delay to Phase 3 if custom builds needed | Early verification session. Identify gaps before V8 drafting. | Alan
2 | RPD management availability for review and sign-off | Delay to Phase 2 if V8 review stalls | Book review sessions in advance. Set 1-week turnaround expectation. | Alan / Leslie
3 | Worker resistance to digital system change | Low adoption of Breadcrumb | Involve site supervisors early. Demonstrate time savings. Parallel run period. | RPD / Alan
4 | [Enter risk]
DECISIONS NEEDED FROM CLIENT
# | Decision Required | Decision Maker | Needed By
1 | Approve elimination list — confirm RPD is comfortable dropping ISO 45001 future-proofing | Leslie Robertson | [DATE]
2 | Provide Breadcrumb login credentials for verification testing | RPD IT / Operations | [DATE]
3 | Confirm V8 review turnaround time (recommend 1 week per section) | Leslie Robertson | [DATE]
HOURS THIS WEEK
Activity | Hours | Notes
Gap analysis / document review | 4
Procedure drafting | 0
Breadcrumb configuration | 0
V8 drafting | 0
Client meetings / presentations | 0
Administration / reporting | 0
TOTAL THIS WEEK | 4
CUMULATIVE PROJECT TOTAL |  | Enter manually from Progress Log running total

## Progress Log
WEEKLY PROGRESS LOG — Append one row per week
Week # | Week Ending | Phase | Key Achievement | Blockers | Overall RAG | Hours | Cumulative Hrs
1 | 28 Feb 2025 | 1 | Gap analysis complete. Document register complete. 7 demo procedures generated. Reference library pushed to Gatekeeper repo. | Awaiting RPD management review session and Breadcrumb access. | ON TRACK |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[6 empty] | TOTAL: | 0