## Enriched Register
# | Observation Date | Photo ID | Filename | Observation | Conformance Status | CCVS Code | CCVS Category | Action Required | Action Description | Responsible | Due | Monitoring Note | Close-out Status | Closed Date | Closed By | Close-out Notes
1 | 2026-02-26 | P-0001 | 001.jpeg | SD Group audit at Unitas Business Park, Rouse Hill — 26-02-2026. Principal contractor | Info |  |  | No |  |  | N/A |  | N/A
2 | 2026-02-26 | P-0002 | 002.jpeg | SD Group Site Safety sign displayed at site entry with PPE requirements, visitor sign-in, and emergency contacts. Compliant — SafeWork NSW Code of Practice: Construction Work (2022) cl.4.2 / WHS Regulation 2017 cl.310. | Compliant | SYS-M3 | Systems | No |  | PC | N/A | Confirm site safety sign current and PPE requirements visible at entry each audit | N/A
3 | 2026-02-26 | P-0003 | 003.jpeg | First aid cabinet fully stocked and accessible on site. Compliant — WHS Regulation 2017 cl.42 / SafeWork NSW Code of Practice: First Aid in the Workplace (2022) / AS 2675-1983. | Compliant | SYS-M3 | Systems | No |  | PC | N/A | Check first aid cabinet stocked and accessible; confirm trained first aider on site | N/A
4 | 2026-02-26 | P-0004 | 004.jpeg | Main retail electrical meter board confirmed in service and secured. Compliant — SafeWork NSW Code of Practice: Managing Electrical Risks in the Workplace (2022) / AS/NZS 3012:2019 / WHS Regulation 2017 cl.164. | Compliant | ELE-H6 | Electrical | No |  | PC | N/A | Confirm meter board secured and tagged in service; check no unauthorised access | N/A
5 | 2026-02-26 | P-0005 | 005.jpeg | Temporary electrical supply board labelling and in-service status confirmed. Compliant — AS/NZS 3012:2019 / SafeWork NSW Code of Practice: Managing Electrical Risks in the Workplace (2022) / WHS Regulation 2017 cl.164. | Compliant | ELE-H6 | Electrical | No |  | PC | N/A | Confirm temporary supply board labelled, tagged in service, and RCD tested each month | N/A
6 | 2026-02-26 | P-0006 | 006.jpeg | Delineated exclusion zones established around tilt-up panel erection area using traffic cones. Compliant — SafeWork NSW Code of Practice: Construction Work (2022) cl.5.3 / Tilt-up and Precast Concrete CoP / WHS Regulation 2017 cl.223. | Compliant | STR-H6 | Structural | No |  | PC | N/A | Check exclusion zone boundaries maintained during all panel erection and crane operations | N/A
7 | 2026-02-26 | P-0007 | 007.jpeg | EWP operating within delineated work zone; engineer's clearance certificate confirmed for Block B structural steel installation. Compliant — SafeWork NSW Tilt-up and Precast Concrete Construction CoP / WHS Regulation 2017 cl.223. | Compliant | WAH-H6 | Work at Height | No |  | PC | N/A | Confirm EWP within delineated zone and engineer clearance cert on site before each lift | N/A
8 | 2026-02-26 | P-0008 | 008.jpeg | Exclusion zone boundaries confirmed with traffic cones during panel erection and EWP operations. Compliant — WHS Regulation 2017 cl.223 / SafeWork NSW Tilt-up and Precast Concrete Construction CoP / Code of Practice: Construction Work (2022). | Compliant | STR-H6 | Structural | No |  | PC | N/A | Confirm exclusion zone perimeter maintained with cones or barriers during panel erection | N/A
9 | 2026-02-26 | P-0009 | 009.jpeg | Full work zone exclusion perimeter confirmed with crane and EWPs operating within delineated area across Block B. Compliant — WHS Regulation 2017 cl.223 / SafeWork NSW Tilt-up and Precast Concrete Construction CoP / AS 2550.1. | Compliant | MOB-H6 | Mobile Plant | No |  | PC | N/A | Confirm full exclusion perimeter established before crane and EWP operations start each day | N/A
10 | 2026-02-26 | P-0010 | 010.jpeg | Telehandler confirmed in SD Group plant and equipment register. Compliant — WHS Regulation 2017 cl.226 / SafeWork NSW Code of Practice: Managing Risks of Plant in the Workplace (2022). Operator HRWL (LF class) to be verified. | Conditional | MOB-H6 | Mobile Plant | Yes | Verify HRWL (LF class) for telehandler operator and retain sighting record on site | PC | Next audit | Confirm HRWL LF class sighted, recorded, and retained by PC per WHS Reg cl.309 | Open
11 | 2026-02-26 | P-0011 | 011.jpeg | Blue boom-type EWP confirmed in SD Group plant and equipment register during structural steel installation. Compliant — WHS Regulation 2017 cl.226 / SafeWork NSW Code of Practice: Managing Risks of Plant in the Workplace (2022) / AS 2550.10. | Compliant | WAH-H6 | Work at Height | No |  | Subcontractor | N/A | Confirm EWP registered in plant register with current inspection tag before each shift | N/A
12 | 2026-02-26 | P-0012 | 012.jpeg | Vertical mast EWP confirmed in SD Group plant and equipment register. Compliant — WHS Regulation 2017 cl.226 / SafeWork NSW Code of Practice: Managing Risks of Plant in the Workplace (2022). Operator HRWL (WP class) to be verified. | Conditional | WAH-H6 | Work at Height | Yes | Verify HRWL (WP class) for vertical mast EWP operator and retain sighting record | PC | Next audit | Confirm HRWL WP class sighted, recorded, and retained by PC per WHS Reg cl.309 | Open
13 | 2026-02-26 | P-0013 | 013.jpeg | Mobile crane confirmed in SD Group plant and equipment register | Info | MOB-H6 | Mobile Plant | No |  |  | N/A |  | N/A
14 | 2026-02-26 | P-0014 | 014.jpeg | Hired Skyreach boom lift EWP confirmed in site plant register prior to use. Compliant — WHS Regulation 2017 cl.203 / SafeWork NSW Code of Practice: Managing Risks of Plant in the Workplace (2022). Plant hire registration and service history to be retained on site. | Conditional | WAH-H6 | Work at Height | Yes | Retain plant hire registration and service history for Skyreach boom lift on site | PC | Immediate | Confirm hire plant registration papers and service history retained on site before use | Open
15 | 2026-02-26 | P-0015 | 015.jpeg | EWP pre-start checklist confirmed completed for current shift. Compliant — SafeWork NSW Code of Practice: Managing Risks of Plant in the Workplace (2022) / AS 2550.10 / WHS Regulation 2017 cl.229. | Compliant | WAH-H6 | Work at Height | No |  | Subcontractor | N/A | Confirm EWP pre-start checklist completed and signed before each shift | N/A
16 | 2026-02-26 | P-0016 | 016.jpeg | Purlins and roof sheeting installation in progress at Block A with EWP in use for work at height. Compliant — SafeWork NSW Code of Practice: Managing the Risk of Falls at Workplaces (2022) / WHS Regulation 2017 cl.79. SWMS for WAH to be confirmed on site. | Conditional | WAH-H6 | Work at Height | Yes | Confirm SWMS for WAH (purlins/roof sheeting with EWP) is on site and workers signed on | PC | Immediate | Confirm WAH SWMS sighted on site and all workers signed on before work starts | Open
17 | 2026-02-26 | P-0017 | 017.jpeg | Lifting clutches confirmed in service for panel erection operations. Compliant — AS 3775.2 / AS 4991 / SafeWork NSW Code of Practice: Managing Risks of Plant in the Workplace (2022) / WHS Regulation 2017 cl.229. | Compliant | MOB-H6 | Mobile Plant | No |  | PC | N/A | Confirm lifting clutches tagged in service with current inspection certificate before each lift | N/A
18 | 2026-02-26 | P-0018 | 018.jpeg | Site hardstand and access road surface observed. Ground bearing capacity must be confirmed adequate for crane outrigger and plant loads. Compliant subject to — SafeWork NSW Tilt-up and Precast Concrete Construction CoP / Level 1 Geotechnical Report. | Conditional | STR-H6 | Structural | Yes | Confirm ground bearing capacity adequate for crane outrigger and plant loads per geotech report | PC | Immediate | Confirm geotechnical sign-off at all outrigger positions is in Lift Plan before crane sets up | Open
19 | 2026-02-26 | P-0019 | 019.jpeg | Block A foundations and floor slab in place with engineer certification required prior to panel erection. Compliant subject to engineer sign-off — SafeWork NSW Tilt-up and Precast Concrete Construction CoP / WHS Regulation 2017 cl.299. | Conditional | STR-H9 | Structural | Yes | Obtain engineer certification for Block A foundations and floor slab prior to panel erection | PC | Immediate | Confirm written engineer sign-off on foundations and slab sighted before erection starts | Open
20 | 2026-02-26 | P-0020 | 020.jpeg | Tilt-up panel casting beds and erected panels observed across Block A/B. Panel traceability and quality records must be maintained. Compliant — SafeWork NSW Tilt-up and Precast Concrete Construction CoP. Concrete strength certificates to be confirmed on file. | Conditional | STR-H9 | Structural | Yes | Confirm concrete strength certificates on file and panel traceability records maintained | PC | Immediate | Confirm 25 MPa test certificates on site for each panel prior to erection | Open
21 | 2026-02-26 | P-0021 | 021.jpeg | EWP pre-start check and OEM maintenance log confirmed completed for boom lift. Compliant — AS 2550.10 / SafeWork NSW Code of Practice: Managing Risks of Plant in the Workplace (2022) / WHS Regulation 2017 cl.229. | Compliant | WAH-H6 | Work at Height | No |  | Subcontractor | N/A | Confirm EWP pre-start and OEM maintenance log completed and available for inspection | N/A
22 | 2026-02-26 | P-0022 | 022.jpeg | HRWL for EWP operation sighted and confirmed current (digital licence). Compliant — WHS Regulation 2017 Part 4.5 / SafeWork NSW licence verification portal. Licence sighting record to be retained on site. | Conditional | WAH-H6 | Work at Height | Yes | Retain HRWL sighting record for EWP operator on site per WHS Reg cl.309 | PC | Next audit | Confirm HRWL sighting record filed and accessible during audit | Open
23 | 2026-02-26 | P-0023 | 023.jpeg | EWP pre-start inspection logbook entries confirmed completed with date and operator details. Compliant — WHS Regulation 2017 cl.229 / SafeWork NSW Code of Practice: Managing Risks of Plant in the Workplace (2022) / AS 2550.10. | Compliant | WAH-H6 | Work at Height | No |  | Subcontractor | N/A | Confirm EWP logbook entries include date, operator name, and defect status for each shift | N/A
24 | 2026-02-26 | P-0024 | 024.jpeg | HRWL for boom lift operator Santiago sighted and confirmed current. Compliant — WHS Regulation 2017 cl.75 / Part 4.5. HRWL sighting record to be retained by principal contractor per WHS Regulation 2017 cl.309. | Conditional | WAH-H6 | Work at Height | Yes | Retain HRWL sighting record for Santiago (boom lift operator) per WHS Reg cl.309 | PC | Next audit | Confirm HRWL sighting record for Santiago filed and retained by PC | Open
25 | 2026-02-26 | P-0025 | 025.jpeg | Fire extinguisher located at Knox Creek boundary and confirmed accessible. Compliant — AS 1841 / AS 1851 / SafeWork NSW Code of Practice: Construction Work (2022). Monthly inspection and annual service records to be maintained. | Compliant | SYS-M3 | Systems | No |  | PC | N/A | Confirm fire extinguisher accessible, tagged with current monthly check and annual service | N/A
26 | 2026-02-26 | P-0026 | 026.jpeg | Pre-start and OEM maintenance records for Airman 5t excavator reviewed — accuracy of entries requires improvement. ACTION REQUIRED — Ensure all pre-start entries accurately reflect plant condition. WHS Regulation 2017 cl.229 / SafeWork NSW Code of Practice: Managing Risks of Plant in the Workplace (2022). | NCR | MOB-M4 | Mobile Plant | Yes | Ensure all Airman excavator pre-start entries accurately reflect plant condition — inaccurate entries identified | Subcontractor | Immediate | Verify corrected pre-start records sighted and accurate entries maintained going forward | Open
27 | 2026-02-26 | P-0027 | 027.jpeg | Excavator service sticker and QR code inspection tag confirmed current on Airman excavator. Compliant — WHS Regulation 2017 cl.229 / SafeWork NSW Code of Practice: Managing Risks of Plant in the Workplace (2022). | Compliant | MOB-M4 | Mobile Plant | No |  | Subcontractor | N/A | Confirm service sticker and QR inspection tag current before excavator use each shift | N/A
28 | 2026-02-26 | P-0028 | 028.jpeg | Airman excavator hour meter confirmed at 954 hours. Next OEM service interval to be identified and documented. Compliant subject to — WHS Regulation 2017 cl.229 / SafeWork NSW Code of Practice: Managing Risks of Plant in the Workplace (2022). | Conditional | MOB-M4 | Mobile Plant | Yes | Identify and document next OEM service interval for Airman excavator (currently 954 hrs) | Subcontractor | Next audit | Confirm next service interval documented and plant taken out of service if overdue | Open
29 | 2026-02-26 | P-0029 | 029.jpeg | Daily sign-in sheet for 26-02-2026 completed with all attending workers signed in. Compliant — SafeWork NSW Code of Practice: Construction Work (2022) cl.4.3 / WHS Regulation 2017 cl.309 / cl.43. | Compliant | SYS-L2 | Systems | No |  | PC | N/A | Confirm daily sign-in sheet completed for all workers before work starts each day | N/A
30 | 2026-02-26 | P-0030 | 030.jpeg | Page 2 of daily sign-in sheet confirms additional subcontractor workers signed onto site. Compliant — SafeWork NSW Code of Practice: Construction Work (2022) cl.4.3 / WHS Regulation 2017 cl.309 / cl.43. | Compliant | SYS-L2 | Systems | No |  | PC | N/A | Confirm all subcontractor workers signed in on daily sheet before accessing site | N/A
31 | 2026-02-26 | P-0031 | 031.jpeg | Allcon SWMS | Info | SYS-M3 | Systems | No |  |  | N/A |  | N/A
32 | 2026-02-26 | P-0032 | 032.jpeg | Allcon SWMS amended | Info | SYS-M3 | Systems | No |  |  | N/A |  | N/A
33 | 2026-02-26 | P-0033 | 033.jpeg | Allcon workers confirmed as signed onto Wilson's SWMS prior to commencing work. Compliant — WHS Regulation 2017 cl.299(3) / SafeWork NSW Code of Practice: Construction Work (2022). Sign-on records to be retained on site. | Conditional | SYS-M3 | Systems | Yes | Retain Allcon SWMS sign-on records on site for project duration per WHS Reg cl.309 | PC | Next audit | Confirm sign-on records retained and accessible during audit | Open
34 | 2026-02-26 | P-0034 | 034.jpeg | Toolbox talk conducted prior to tilt-up panel erection covering emergency procedures and trade coordination. Compliant — SafeWork NSW Tilt-up and Precast Concrete Construction CoP / WHS Regulation 2017 cl.43. Attendance record confirmed. | Compliant | SYS-M3 | Systems | No |  | PC | N/A | Confirm toolbox talk conducted and attendance record retained before each major lift | N/A
35 | 2026-02-26 | P-0035 | 035.jpeg | Crane Lift Plan confirmed on site and available during panel erection operations. Compliant — SafeWork NSW Tilt-up and Precast Concrete Construction CoP / AS 2550.1. Lift Plan prepared by competent person and accessible to crew. | Compliant | MOB-H6 | Mobile Plant | No |  | PC | N/A | Confirm Crane Lift Plan on site, current, and accessible to crew during all lifts | N/A
36 | 2026-02-26 | P-0036 | 036.jpeg | Panel erection sequence document confirmed on site and followed in order. Compliant — SafeWork NSW Tilt-up and Precast Concrete Construction CoP. Deviations from approved sequence require written engineer approval. | Compliant | STR-H9 | Structural | No |  | PC | N/A | Confirm panel erection sequence followed in order; any deviation requires written engineer approval | N/A
37 | 2026-02-26 | P-0037 | 037.jpeg | Emergency procedure document for tilt-up construction operations confirmed available and reviewed at pre-lift toolbox talk. Compliant — WHS Regulation 2017 cl.43 / SafeWork NSW Tilt-up and Precast Concrete Construction CoP. | Compliant | SYS-H6 | Systems | No |  | PC | N/A | Confirm emergency procedure reviewed at each pre-lift toolbox talk and accessible on site | N/A
38 | 2026-02-26 | P-0038 | 038.jpeg | Propping plant schedule confirmed available on site with panel numbers, prop quantities, and positioning noted. Compliant — SafeWork NSW Tilt-up and Precast Concrete Construction CoP. Props must not be removed without engineer approval. | Compliant | STR-H9 | Structural | No |  | PC | N/A | Confirm propping schedule on site with panel numbers, quantities, and no props removed without engineer sign-off | N/A
39 | 2026-02-26 | P-0039 | 039.jpeg | Structural drawing confirming Panel 17, Block B, Unit 11 identification and traceability confirmed. Compliant — SafeWork NSW Tilt-up and Precast Concrete Construction CoP. Panel traceability records to be retained with project documentation. | Conditional | STR-H9 | Structural | Yes | Retain panel traceability records (Panel 17, Block B, Unit 11) with project documentation | PC | Next audit | Confirm panel traceability records filed and accessible during audit | Open
40 | 2026-02-26 | P-0040 | 040.jpeg | Engineer's inspection report confirming lifting inserts and structural steel connections certified for erection. Compliant — SafeWork NSW Tilt-up and Precast Concrete Construction CoP. Written certification to be retained on site and referenced in Lift Plan. | Conditional | STR-H9 | Structural | Yes | Retain engineer's inspection report for lifting inserts and steel connections with Lift Plan | PC | Immediate | Confirm engineer cert retained on site and referenced in Lift Plan before erection | Open
41 | 2026-02-26 | P-0041 | 041.jpeg | Western Sydney Concrete panel tracing register confirms Panel 17 poured 14-02-2026 with compressive strength data. Compliant — SafeWork NSW Tilt-up and Precast Concrete Construction CoP. Concrete test certificates to confirm 25 MPa achieved prior to erection. | Compliant | STR-H9 | Structural | No |  | PC | N/A | Confirm concrete test certificates confirm 25 MPa achieved for each panel before erection | N/A
42 | 2026-02-26 | P-0042 | 042.jpeg | Digital crane set-up model confirms crane positioned from southern boundary per approved Lift Plan. Compliant — SafeWork NSW Tilt-up and Precast Concrete Construction CoP / AS 2550.1. Outrigger positions to be confirmed against geotechnical report. | Conditional | MOB-H6 | Mobile Plant | Yes | Confirm crane outrigger positions against geotechnical report bearing pressure data | PC | Immediate | Confirm outrigger positions checked against geotech report before crane sets up each day | Open
43 | 2026-02-26 | P-0043 | 043.jpeg | Panel 1 structural drawing confirmed with reinforcement, insert positions, and connection details available to lifting crew. Compliant — SafeWork NSW Tilt-up and Precast Concrete Construction CoP. Current approved drawings to be on site during erection. | Compliant | STR-H9 | Structural | No |  | PC | N/A | Confirm current approved drawings on site and accessible to lifting crew during erection | N/A
44 | 2026-02-26 | P-0044 | 044.jpeg | Engineering inspection report for Panel 1 confirming insert adequacy and structural steel readiness. Compliant — SafeWork NSW Tilt-up and Precast Concrete Construction CoP. Pre-erection sign-off completed before Lift Plan executed. | Compliant | STR-H9 | Structural | No |  | PC | N/A | Confirm pre-erection engineer sign-off completed and recorded before each panel lifted | N/A
45 | 2026-02-26 | P-0045 | 045.jpeg | Concrete wall panel shop drawings confirm 25 MPa design compressive strength and panel details. Compliant — SafeWork NSW Tilt-up and Precast Concrete Construction CoP. Strength to be verified against Western Sydney Concrete test certificates before erection. | Conditional | STR-H9 | Structural | Yes | Verify panel 25 MPa design strength against Western Sydney Concrete test certificates before erection | PC | Immediate | Confirm test certificates confirm strength achieved for each panel before lift proceeds | Open
46 | 2026-02-26 | P-0046 | 046.jpeg | Level 1 geotechnical report with compaction test locations across site confirmed available. Compliant — SafeWork NSW Tilt-up and Precast Concrete Construction CoP. Bearing pressure results to be referenced in Lift Plan for crane outrigger positions. | Compliant | STR-H6 | Structural | No |  | PC | N/A | Confirm geotechnical report current and bearing pressure data referenced in Lift Plan | N/A
47 | 2026-02-26 | P-0047 | 047.jpeg | Geotechnical bearing pressure data confirms crane hardstand areas adequate per Level 1 report. Compliant — SafeWork NSW Tilt-up and Precast Concrete Construction CoP. Competent engineer to confirm adequacy at all outrigger positions prior to crane operations. | Compliant | STR-H6 | Structural | No |  | PC | N/A | Confirm competent engineer confirms outrigger position adequacy at each crane set-up | N/A
48 | 2026-02-26 | P-0048 | 048.jpeg | WCTS online portal confirms plant registration and inspection records current for site plant. Compliant — WHS Regulation 2017 Chapter 5 / cl.229. Plant registration records accessible during audit as required. | Compliant | MOB-M4 | Mobile Plant | No |  | PC | N/A | Confirm WCTS records current and accessible during audit for all registered plant on site | N/A
49 | 2026-02-26 | P-0049 | 049.jpeg | Electronic plant register file structure on site computer shows individual plant maintenance records. Compliant — SafeWork NSW Code of Practice: Managing Risks of Plant in the Workplace (2022) / WHS Regulation 2017 cl.229. | Compliant | MOB-M4 | Mobile Plant | No |  | PC | N/A | Confirm individual plant maintenance records on site computer accessible during audit | N/A
50 | 2026-02-26 | P-0050 | 050.jpeg | Plant register for steel installation subcontractor EPS confirms plant items, registration details, and operator HRWLs. Compliant — WHS Regulation 2017 cl.309 / SafeWork NSW Code of Practice: Managing Risks of Plant in the Workplace (2022). | Compliant | MOB-M4 | Mobile Plant | No |  | PC | N/A | Confirm EPS plant register includes current registration, inspection, and HRWL details | N/A
51 | 2026-02-26 | P-0051 | 051.jpeg | Boom lift (rego ending G7P) confirmed entered into site plant register prior to use. Compliant — WHS Regulation 2017 cl.226 / SafeWork NSW Code of Practice: Managing Risks of Plant in the Workplace (2022). | Compliant | WAH-H6 | Work at Height | No |  | Subcontractor | N/A | Confirm boom lift G7P entered into site plant register before use each shift | N/A
52 | 2026-02-26 | P-0052 | 052.jpeg | Site induction record for Mohammed El Hassan (crane driver) confirmed completed. Compliant — WHS Regulation 2017 cl.309 / SafeWork NSW Code of Practice: Construction Work (2022). Induction records to be retained for project duration. | Conditional | SYS-M3 | Systems | Yes | Retain site induction record for Mohammed El Hassan (crane driver) for project duration | PC | Next audit | Confirm induction records retained and accessible during audit per WHS Reg cl.309 | Open
53 | 2026-02-26 | P-0053 | 053.jpeg | Mohammed El Hassan and crew confirmed signed onto applicable SWMS with induction completed. Compliant — WHS Regulation 2017 cl.299(3) / cl.309 / SafeWork NSW Code of Practice: Construction Work (2022). | Compliant | SYS-M3 | Systems | No |  | PC | N/A | Confirm El Hassan and crew signed onto applicable SWMS before each crane operation | N/A
54 | 2026-02-26 | P-0054 | 054.jpeg | HRWLs for crane driver Mohammed El Hassan (C6 class) confirmed current and sighted. Compliant — WHS Regulation 2017 Part 4.5 / cl.75. Licence sighting record to be retained by principal contractor. | Conditional | MOB-H6 | Mobile Plant | Yes | Retain HRWL sighting record for crane driver Mohammed El Hassan (C6) per WHS Reg cl.309 | PC | Next audit | Confirm HRWL C6 sighting record filed and retained by PC; accessible during audit | Open
55 | 2026-02-26 | P-0055 | 055.jpeg | Structural drawing for Unit 01 confirmed on site and current. Compliant — SafeWork NSW Code of Practice: Construction Work (2022). Drawings must reflect approved design revisions and be accessible to relevant trades. | Compliant | STR-H6 | Structural | No |  | PC | N/A | Confirm current approved drawings on site and accessible to all relevant trades | N/A
56 | 2026-02-26 | P-0056 | 056.jpeg | Propping plan layout plan with green-marked work | Info | STR-H9 | Structural | No |  |  | N/A |  | N/A
57 | 2026-02-26 | P-0057 | 057.jpeg | Porter Equipment field service report for Airman excavator confirmed complete at 854 hours. Compliant — WHS Regulation 2017 cl.229 / SafeWork NSW Code of Practice: Managing Risks of Plant in the Workplace (2022). Addresses earlier concern re pre-start accuracy. | Compliant | MOB-M4 | Mobile Plant | No |  | Subcontractor | N/A | Confirm field service report on file and addresses earlier pre-start accuracy concern | N/A
58 | 2026-02-26 | P-0058 |  | Structural steel installer's pre-start inspection records and OEM maintenance booklet confirmed on site. Compliant — WHS Regulation 2017 cl.229 / SafeWork NSW Code of Practice: Managing Risks of Plant in the Workplace (2022). | Compliant | MOB-M4 | Mobile Plant | No |  | Subcontractor | N/A | Confirm pre-start records and OEM maintenance booklet on site and current | N/A
59 | 2026-02-26 | P-0059 |  | Plant service records including tyre replacement and maintenance entries confirmed current. Compliant — WHS Regulation 2017 cl.229 / SafeWork NSW Code of Practice: Managing Risks of Plant in the Workplace (2022). | Compliant | MOB-M4 | Mobile Plant | No |  | Subcontractor | N/A | Confirm plant service records current including tyre and maintenance entries | N/A
60 | 2026-02-26 | P-0060 |  | Structural steel installation subcontractor workers confirmed signed onto applicable SWMS. Compliant — WHS Regulation 2017 cl.299(3) / cl.309 / SafeWork NSW Code of Practice: Construction Work (2022). Principal contractor to retain copies. | Compliant | SYS-M3 | Systems | No |  | PC | N/A | Confirm all steel installation workers signed onto applicable SWMS before work starts | N/A
61 | 2026-02-26 | P-0061 |  | SWMS for structural steel installation — task descriptions, hazard identification, and risk ratings confirmed. Compliant — WHS Regulation 2017 cl.299 / SafeWork NSW Code of Practice: Construction Work (2022). Hierarchy of controls to be applied per WHS Act 2011 s.17. | Compliant | SYS-M3 | Systems | No |  | PC | N/A | Confirm SWMS task descriptions and risk ratings reviewed against current scope each revision | N/A
62 | 2026-02-26 | P-0062 |  | SWMS for structural steel installation — detailed control measures, PPE requirements, and emergency procedures confirmed. Compliant — WHS Regulation 2017 cl.299 / WHS Act 2011 s.17. Controls must reference Lift Plan, HRWL requirements, and fall prevention measures. | Compliant | SYS-M3 | Systems | No |  | PC | N/A | Confirm SWMS controls include Lift Plan reference, HRWL requirements, and fall prevention | N/A
63 | 2026-02-26 | P-0063 |  | Additional workers confirmed signed onto structural steel installation SWMS. Compliant — WHS Regulation 2017 cl.299(3) / cl.309. SWMS sign-on records to be retained for project duration per SafeWork NSW Code of Practice: Construction Work (2022). | Conditional | SYS-M3 | Systems | Yes | Retain SWMS sign-on records for all additional steel installation workers per WHS Reg cl.309 | PC | Next audit | Confirm sign-on records for all workers retained for project duration | Open

## Summary
PIMS Audit Summary — Unitas Business Park, Rouse Hill
Audit Date | 26-02-2026
Site | Unitas Business Park, Rouse Hill
Principal Contractor | SD Group
Conformance Status | Count | %
Compliant | 39 | 61.9%
Conditional | 18 | 28.6%
NCR | 1 | 1.6%
Info | 5 | 7.9%
Total | 63
CCVS Category | Total Observations | NCR | Conditional | Open Actions
Electrical | 2 | 0 | 0 | 0
Mobile Plant | 16 | 1 | 4 | 5
Structural | 17 | 0 | 6 | 6
Systems | 16 | 0 | 3 | 3
Work at Height | 11 | 0 | 5 | 5
Open Actions
# | Status | CCVS Code | Action Description | Responsible | Due
10 | Conditional | MOB-H6 | Verify HRWL (LF class) for telehandler operator and retain sighting record on site | PC | Next audit
12 | Conditional | WAH-H6 | Verify HRWL (WP class) for vertical mast EWP operator and retain sighting record | PC | Next audit
14 | Conditional | WAH-H6 | Retain plant hire registration and service history for Skyreach boom lift on site | PC | Immediate
16 | Conditional | WAH-H6 | Confirm SWMS for WAH (purlins/roof sheeting with EWP) is on site and workers signed on | PC | Immediate
18 | Conditional | STR-H6 | Confirm ground bearing capacity adequate for crane outrigger and plant loads per geotech report | PC | Immediate
19 | Conditional | STR-H9 | Obtain engineer certification for Block A foundations and floor slab prior to panel erection | PC | Immediate
20 | Conditional | STR-H9 | Confirm concrete strength certificates on file and panel traceability records maintained | PC | Immediate
22 | Conditional | WAH-H6 | Retain HRWL sighting record for EWP operator on site per WHS Reg cl.309 | PC | Next audit
24 | Conditional | WAH-H6 | Retain HRWL sighting record for Santiago (boom lift operator) per WHS Reg cl.309 | PC | Next audit
26 | NCR | MOB-M4 | Ensure all Airman excavator pre-start entries accurately reflect plant condition — inaccurate entries identified | Subcontractor | Immediate
28 | Conditional | MOB-M4 | Identify and document next OEM service interval for Airman excavator (currently 954 hrs) | Subcontractor | Next audit
33 | Conditional | SYS-M3 | Retain Allcon SWMS sign-on records on site for project duration per WHS Reg cl.309 | PC | Next audit
39 | Conditional | STR-H9 | Retain panel traceability records (Panel 17, Block B, Unit 11) with project documentation | PC | Next audit
40 | Conditional | STR-H9 | Retain engineer's inspection report for lifting inserts and steel connections with Lift Plan | PC | Immediate
42 | Conditional | MOB-H6 | Confirm crane outrigger positions against geotechnical report bearing pressure data | PC | Immediate
45 | Conditional | STR-H9 | Verify panel 25 MPa design strength against Western Sydney Concrete test certificates before erection | PC | Immediate
52 | Conditional | SYS-M3 | Retain site induction record for Mohammed El Hassan (crane driver) for project duration | PC | Next audit
54 | Conditional | MOB-H6 | Retain HRWL sighting record for crane driver Mohammed El Hassan (C6) per WHS Reg cl.309 | PC | Next audit
63 | Conditional | SYS-M3 | Retain SWMS sign-on records for all additional steel installation workers per WHS Reg cl.309 | PC | Next audit