## Risk Register
Project: | Remedial Building Works — 409-411 New South Head Road, Double Bay NSW 2028
PCBU / Principal Contractor: | Robertson’s Remedial and Painting Pty Ltd
Jurisdiction: | NSW — WHS Act 2011 (NSW), WHS Regulation 2017 (NSW)
Date Prepared: | 23 February 2026
Prepared by: | Gatekeeper Risk Assessment System
# | Task | Code | Hazard | Likelihood (Pre) | Consequence (Pre) | Risk Rating (Pre-Controls) | Controls | Residual Risk | Responsible Person
1 | Industrial rope access — rigging, descent, work positioning, and ascent for all façade and balcony soffit works | WAH | Fall from height due to anchor failure, rope failure, or equipment malfunction; pendulum swing into structure or adjacent surfaces; contact with building edges causing rope abrasion or severance; electrical hazard from proximity to overhead electric lines; environmental hazards — wind causing rope tangle or worker instability, wet ropes reducing device performance, heat stress and UV degradation of ropes and equipment | B — Likely | 3 — Major | Critical (5) | Engineering: Two independent anchor points per worker — one for working line, one for safety line (Safe Work Australia Guide to Industrial Rope Access Systems s4.5); all anchors and supporting structure load tested to minimum 15 kN before first use and annually thereafter; rope edge protection — davit arms, rollers, or textile sheaths at all contact points; exclusion zone established and barricaded below rope access work area; all tools secured to harness via lanyards or tool bags. Admin: HOLD POINT — anchor installation certified by qualified engineer or competent person per WHS Reg r213; all rope access workers hold current certificate of competency — verified before commencement; equipment inspection by competent person before and after each use — harnesses, lanyards, descenders, back-up devices, ropes, slings, anchor devices; ropes packed after each shift; SWMS prepared — IRA is HRCW per WHS Reg r299; weather forecast checked before commencement; equipment stored protected from heat, UV, moisture, and chemicals. PPE: Full body harness (AS/NZS 1891.4); helmet AS/NZS 1801; safety glasses; hi-vis vest; safety boots; gloves. STOP WORK: Anchor certification not sighted; worker competency not verified; equipment defect identified; wind >40 km/h or causing instability; electrical storm; ropes wet and device performance compromised. | Medium (3) | Site Supervisor / Rope Access Supervisor / Qualified Engineer (anchors)
2 | Industrial rope access — emergency rescue, suspension intolerance response, and environmental monitoring | WAH | Suspension intolerance (suspension trauma) — blood pooling in lower legs during harness suspension reducing cardiac output, leading to fainting, renal failure, and death; delayed rescue of incapacitated worker suspended on rope; worker isolation — inability to communicate distress; environmental deterioration during work — sudden wind, rain, or electrical storm increasing rescue difficulty | C — Possible | 3 — Major | High (4) | Engineering: Working and safety lines rigged for rescue — releasable anchors to allow lowering or raising of injured worker without rescuer needing to descend; rescue equipment present and rigged for immediate use at all times; harness with suspension relief straps or footholds. Admin: Emergency rescue plan prepared, documented, and tested before rope access work commences — plan covers rescue from any situation on site per WHS Reg r42; rope access workers never work alone — minimum two workers with line-of-sight or communication at all times; all workers trained in emergency procedures including rope rescue techniques; rescue to be completed within 5 minutes where practicable; weather monitored continuously — immediate descent if conditions deteriorate; communication system confirmed operative before descent. PPE: Full body harness with suspension relief capability; helmet; first aid kit accessible at anchor station. STOP WORK: Rescue plan not documented or tested; fewer than two rope access workers on site; communication system failure; weather deterioration (wind, wet, lightning). | Medium (3) | Site Supervisor / Rope Access Supervisor / First Aid Officer
3 | Jackhammer defective concrete from balcony soffits to expose reinforcement steel — overhead work from rope access position | SIL | Respirable crystalline silica (RCS) from jackhammering concrete soffits — silicosis risk (irreversible lung disease); whole-body and hand-arm vibration from jackhammer; noise >85 dB(A); flying concrete fragments from overhead demolition; falling concrete debris from soffits onto persons below; electrical hazard — striking concealed services during demolition | A — Almost Certain | 3 — Major | Critical (6) | Engineering: H-class dust extraction connected to jackhammer shroud or wet suppression at point of demolition — no dry demolition permitted; RCD-protected power supply; exclusion zone barricaded below soffit work area; overhead protection for adjacent areas; jackhammer anti-vibration mounts. Admin: Air monitoring where demolition >30 min/shift — RCS exposure standard 0.05 mg/m³ TWA; silica register; health monitoring — lung function baseline and periodic per WHS Reg Part 8.4; services scan before demolition at each new location; task rotation to limit vibration exposure; debris contained and removed at end of each shift. PPE: P2 respirator (fit-tested); face shield AS/NZS 1337; hearing protection (Class 5); anti-vibration gloves; helmet; safety boots with metatarsal protection. STOP WORK: Dust extraction/suppression fails; services detected in demolition zone; air monitoring exceeds 0.05 mg/m³ RCS; exclusion zone breached. | Medium (3) | Site Supervisor / Lead Technician / Occupational Hygienist
4 | Treat exposed reinforcement with Nitoprime Zincrich, prime substrate with Nitobond HAR bonding agent, patch with Renderox HB40 repair mortar — overhead application from rope access | ENV | Chemical exposure — Nitoprime Zincrich (zinc-rich primer, flammable, respiratory irritant); Nitobond HAR (acrylic bonding agent, skin/eye irritant); Renderox HB40 (cementitious repair mortar, alkaline — skin and eye irritant, contains chromium VI); overhead application — drips and splashes onto face, eyes, and skin; manual handling at height — mixing and carrying materials while suspended | B — Likely | 2 — Moderate | High (4) | Engineering: Drip containment below work area; RCD-protected power supply for mixing equipment. Admin: SDS for Nitoprime Zincrich, Nitobond HAR, and Renderox HB40 reviewed and on site; workers briefed on chemical hazards, first aid, and spill procedures for each product; chemical register maintained; no ignition sources within 5 m when using Nitoprime Zincrich; materials pre-mixed at ground level where practicable — minimise mixing at height; eye wash station within 20 m. PPE: P2 respirator; face shield for overhead application; chemical-resistant nitrile gloves; long sleeves; safety glasses AS/NZS 1337. STOP WORK: SDS not on site for any product; eye wash not accessible; worker reports skin or eye irritation. | Low (2) | Site Supervisor / Lead Technician
5 | Pressure wash concrete balcony surfaces to remove loose material, contaminants, and failed coatings before waterproofing | ENV | High-pressure water injection injury; overspray drift onto public areas, balconies, and vehicles below; slip hazard on wet surfaces; electrical hazard — water ingress to electrical fittings; environmental contamination — wash water containing concrete dust and coating residue entering stormwater | B — Likely | 2 — Moderate | High (4) | Engineering: Fan nozzle (not zero-degree); containment sheeting to prevent overspray; wash water captured and filtered — sediment trap or bunded collection; RCD-protected power supply; electrical fittings in wash zone isolated or protected. Admin: Wash water disposal per NSW EPA requirements; overspray management plan — stop if wind >25 km/h; never direct pressure washer at persons; occupant notification before commencement; adjacent balconies checked and protected. PPE: Safety glasses/face shield; waterproof gloves and coveralls; safety boots with non-slip sole. STOP WORK: Wash water containment fails; wind >25 km/h; electrical fittings not isolated in wash zone. | Low (2) | Site Supervisor / Lead Technician
6 | Rake out failed sealant from balcony joints, prepare joint surfaces, apply Fosroc Nitoseal MS250 sealant, tool to profile | ENV | Chemical exposure — Nitoseal MS250 solvent vapours and isocyanate content; skin sensitisation; eye contact; manual handling of caulking guns at height; slip hazard from sealant on surfaces | B — Likely | 2 — Moderate | High (4) | Substitute: Select low-VOC sealant variant where specified product allows. Engineering: Natural ventilation confirmed adequate; RCD-protected power tools. Admin: SDS for Nitoseal MS250 reviewed and on site; workers briefed on chemical hazards, first aid, spill procedures; sealant waste disposed per EPA requirements; chemical register maintained. PPE: Nitrile gloves; safety glasses AS/NZS 1337; P2 respirator if confined/recessed joint areas. STOP WORK: SDS not on site; ventilation inadequate in enclosed areas; worker reports symptoms of sensitisation. | Low (2) | Site Supervisor / Lead Technician
7 | Apply Parchem waterproofing membrane to prepared balcony surfaces — primer, membrane coats, and protection layer | ENV | Chemical exposure — Parchem membrane system (solvent/water-based depending on product variant, respiratory and skin irritant); vapour accumulation in sheltered balcony areas; skin contact during roller/brush application; slip hazard from wet membrane on balcony surfaces | C — Possible | 2 — Moderate | Medium (3) | Engineering: Adequate ventilation confirmed — fans if enclosed balcony; drip containment below work area. Admin: SDS for all Parchem membrane products reviewed and on site; apply during favourable weather — manufacturer temperature and humidity requirements checked; chemical register; area barricaded until membrane cured. PPE: Organic vapour respirator (A1P2) if enclosed area; safety glasses; nitrile gloves; long sleeves. STOP WORK: SDS not on site; ventilation inadequate; temperature outside manufacturer’s range. | Low (1) | Site Supervisor / Lead Applicator
8 | Prepare external concrete render and masonry surfaces, apply Acratex Green Render Sealer via spray or roller from rope access | ENV | Chemical exposure — Acratex Green Render Sealer (water-based acrylic, low VOC but respiratory irritant in spray application); overspray drift onto public areas, adjacent properties, and vehicles; environmental contamination from overspray and equipment wash; manual handling at height — carrying spray equipment while suspended | B — Likely | 2 — Moderate | High (4) | Engineering: Containment sheeting on rope access zone to capture overspray; RCD-protected power supply for spray equipment. Admin: SDS reviewed and on site; wind check before spray application — stop if >25 km/h; overspray management plan; occupant and neighbour notification; equipment wash water captured and disposed per NSW EPA. PPE: P2 respirator during spray application; safety glasses AS/NZS 1337; nitrile gloves; long sleeves; coveralls. STOP WORK: Wind >25 km/h during spray application; overspray reaching public areas or adjacent properties; SDS not on site. | Low (2) | Site Supervisor / Lead Painter
9 | Apply Dulux Weathershield Exterior Low Sheen topcoat to external concrete render and masonry surfaces from rope access | ENV | Chemical exposure — Weathershield Low Sheen (water-based acrylic, low VOC); overspray drift from height; drips from rope access work position onto persons or property below; manual handling of paint and equipment at height | C — Possible | 2 — Moderate | Medium (3) | Engineering: Containment sheeting; drip trays below work zone. Admin: SDS reviewed and on site; apply during favourable weather — wind <25 km/h, temperature per manufacturer spec; overspray cleaned immediately; equipment wash water captured. PPE: Safety glasses; nitrile gloves; P2 respirator if spray application in enclosed areas. STOP WORK: Wind >25 km/h; overspray or drips reaching public areas; temperature outside manufacturer’s range. | Low (1) | Site Supervisor / Lead Painter
10 | Surface preparation of existing painted concrete and masonry — abrasion, sanding, or mechanical preparation of coatings of unknown age | LED | CRITICAL — Existing coatings on pre-1997 surfaces may contain lead paint. Respirable lead dust from abrading, sanding, or mechanical preparation — lead poisoning (neurological damage, kidney damage, reproductive harm); dust inhalation; skin and eye contact with lead-contaminated dust | B — Likely | 3 — Major | Critical (5) | Eliminate: HOLD POINT — Test existing coatings for lead before any abrasion or mechanical preparation. If pre-1997 or unknown age, XRF testing or NATA-accredited lab analysis required. If lead confirmed (>1% by weight): lead risk work per WHS Reg Part 8.5; lead risk control plan; air monitoring; blood lead monitoring; wet methods mandatory; HEPA vacuum; hazardous waste disposal; notify SafeWork NSW. Engineering (if lead-free): Wet abrasion; RCD-protected tools; dust extraction; adequate ventilation. Admin: Lead test results on site; lead register if detected; health monitoring per WHS Reg Part 8.5. PPE: P2 respirator (fit-tested); safety glasses; nitrile gloves; disposable coveralls if lead risk work. STOP WORK: Lead test results not available; lead detected and control plan not in place; air monitoring exceeds lead exposure standard. | Medium (3) | Site Supervisor / Occupational Hygienist (if lead confirmed)
11 | Manage pedestrian and vehicle interface around work zone at 409-411 New South Head Road, Double Bay — high-traffic commercial and residential streetscape | TRF | Pedestrian struck by falling object from rope access work zone; vehicle collision with work zone equipment; public accessing exclusion zone below overhead work; overspray, wash water, or debris affecting pedestrians, vehicles, and adjacent commercial premises; noise and dust affecting residents and businesses | B — Likely | 3 — Major | Critical (5) | Engineering: Physical barricading — hoarding or A-class barriers below overhead work zones; overhead protection gantry where footpath cannot be closed; containment sheeting on rope access zone to capture debris and overspray. Admin: Traffic management plan (TMP) where works encroach on road or footpath — Woollahra Municipal Council approval required; spotter during overhead rope access work where public below; signage at all access points; daily barricade inspection; occupant and adjacent business notification before noisy, dusty, or spray work; work scheduled to minimise disruption to commercial peak hours. PPE: Hi-vis vest; helmet mandatory in drop zones. STOP WORK: Exclusion zone barricading not in place; overhead protection not installed where footpath open; TMP not approved where works encroach on road. | Medium (3) | Site Supervisor / Traffic Controller (if TMP required)
12 | Manual handling of materials, tools, chemicals, and equipment across all scope items — ground to rope access transfer | STR | Musculoskeletal injury from repetitive lifting, carrying, and overhead work; back injury from awkward postures during rope access material transfer; fatigue from sustained physical work at height; dropped materials during transfer between ground and rope access position | B — Likely | 2 — Moderate | High (4) | Eliminate: Deliver materials by mechanical means (hoist line, haul bag on separate anchored line) — minimise manual carrying while suspended. Engineering: Mechanical lifting aids for items >20 kg; tool bags and haul bags rated for load; separate anchor for material hauling line. Admin: Team lifts for items >15 kg at ground level; task rotation; correct manual handling technique briefed; rest breaks scheduled; materials pre-staged at ground level in manageable quantities. PPE: Rigger’s gloves; safety boots. STOP WORK: Material haul line not independently anchored; loads exceed rated capacity of haul equipment. | Low (1) | Site Supervisor / Rope Access Supervisor
Risk Profile Summary
Pre-Controls
Risk Rating | Count
Critical (5–6) | 4
High (4) | 6
Medium (3) | 2
Low (1–2) | 0
Post-Controls (Residual)
Risk Rating | Count
Critical (5–6) | 0
High (4) | 0
Medium (3) | 5
Low (1–2) | 7
Critical Hold Points
• Industrial rope access — anchor installation certified by qualified engineer, load tested to 15 kN minimum (WHS Reg r213)
• Existing coatings — test for lead paint before any abrasion or mechanical preparation (WHS Reg Part 8.5)
• All silica-generating tasks — air monitoring and health surveillance required (WHS Reg Part 8.4)
• Pressure washing — wash water containment and disposal plan verified before commencement (NSW EPA)
References
• Work Health and Safety Act 2011 (NSW) — s19, s28, s38
• Work Health and Safety Regulation 2017 (NSW) — Part 3.1, Part 6.3, Part 6.4, Part 8.4, Part 8.5
• Code of Practice: Managing the Risk of Falls at Workplaces (Safe Work Australia)
• Code of Practice: Managing Risks of Hazardous Chemicals in the Workplace (Safe Work Australia)
• Guide to Managing Risks of Industrial Rope Access Systems (Safe Work Australia, June 2022)
• AS/NZS ISO 22846 — Rope access systems
• AS/NZS 1891.4 — Industrial fall-arrest systems and devices — Selection, use and maintenance
• AS/NZS 1801 — Occupational protective helmets
• AS/NZS 1337 — Personal eye protection

## Matrix & Lists
| 1 | 2 | 3
Likelihood \ Consequence | 1 — Minor | 2 — Moderate | 3 — Major | Likelihood Label
A | High (3) | Critical (5) | Critical (6) | A — Almost Certain
B | Medium (2) | High (4) | Critical (5) | B — Likely
C | Low (1) | Medium (3) | High (4) | C — Possible
D | Low (1) | Low (2) | Medium (3) | D — Unlikely
E | Low (1) | Low (1) | Low (2) | E — Rare
Likelihood Definitions
Level | Description
A — Almost Certain | Expected to occur in most circumstances
B — Likely | Will probably occur in most circumstances
C — Possible | Might occur at some time
D — Unlikely | Could occur but not expected
E — Rare | May occur only in exceptional circumstances
Consequence Definitions
Level | Description
1 — Minor | First aid treatment; minor property damage
2 — Moderate | Medical treatment; significant property damage
3 — Major | Fatality, permanent disability, or major structural failure
Gatekeeper Hazard Codes
Code | Category
WAH | Work at height — collective height access (EWP, scaffold, ladder)
SIL | Silica and dust
ENV | Environmental and chemical
STR | Structural
ASB | Asbestos
LED | Lead
TRF | Traffic and public interface
CHM | Chemical hazards
WAT | Water / waterproofing hazards
EMR | Emergency response
Risk Levels
Rating | Action Required
Critical (6) | Immediate stop work — controls must be verified and approved before proceeding
Critical (5) | Immediate stop work — controls must be verified and approved before proceeding
High (4) | Senior management attention required — additional controls needed
High (3) | Senior management attention required — additional controls needed
Medium (3) | Manage with specific procedures and monitoring
Medium (2) | Manage with specific procedures and monitoring
Low (2) | Manage by routine procedures
Low (1) | Manage by routine procedures