## Cover Page
BHPB IRON ORE RISK REGISTER COVER PAGE
Date: |  | 2014-10-06
Physical Site: |  | Weeli Wolli Creek Newman Mainline 291km Bridge - 10 km South of Yandi Junction
Department:
Area: |  | North East side of existing NML 291km Bridge
Risk Assessment Title / Description: (i.e., Mining Dept risk register) |  | Weeli Wolli Creek Newman Mainline 291km Bridge - Earthworks, Siteworks
Risk Assessment Scope: (Boundary of assessment/Subject) |  | Project Startup - Weeli Wolli Creek Newman Mainline 291km Bridge - SOW-G074-C-12017/B
Risk Assessment type: (Work place risk assessment, Construction risk assessment, Corporate risk assessment) |  | Workplace and Construction Risk Assessment
Other References: Documents/Photographs:
List of Risk Assessment Attendees:
First Name | Last Name | Position
James | Ward | Track Supervisor
Darren | Wherry | Track Worker
Mitchell | Beirge | Track Supervisor
Israel | Schorer | Senior Zero Harm Advisor
Sallyanne | Rinehart | HSE Manager
Authorisation of Risk Assessment:
Reviewed By | First Name | Last Name | Comments / Feedback / Amendments |  | Date
Project Manager | Philip | Hunter | Approved for tender only - will need to be revised. |  | 2014-10-06
Construction Manager | David | Hargreaves | Approved for tender only - will need to be revised. |  | 2014-10-06
AMENDMENTS
Version | Date | Revised By | Approved By | Reason for change

## References
Reference documents included in the Risk Assessment workshop
Ref. | Number | Title | Description
1 | PP-09-001 | Contractor Selection & Engagement
2 | PP-09-003 | Induction and Orientation
3 | PP-09-004 | Training & Competency
4 | PP-09-005 | Hazard and Risk Management
5 | PP-09-008 | Site Access & Security
6 | PP-09-010 | Hazardous Materials Management
7 | PP-09-011 | Light Vehicles, Buses & Mobile Plant
8 | PP-09-012 | Traffic Management
9 | PP-09-013 | Mobilisation
10 | PP-09-014 | Loading and Unloading
11 | PP-09-017 | Power and Hand Tools
12 | PP-09-018 | Electrical Safety
13 | PP-09-027 | Working in Hot and Cold
14 | PP-09-028 | Manual Handling
15 | PP-09-030 | Fitness for Work
16 | PP-09-031 | Medical, Injury and Illness Management
17 | PP-09-036 | Rail Safety
18 | PP-09-037 | Pressurized Equipment
19 | PP-09-039 | Bulk Earthworks and Civil Works
20 | PP-09-040 | Dust and Fibrous Materials
21 | PP-09-048 | Communication and Consultation
22 | PP-09-049 | Guarding, Barricading, Signaage and Housekeeping
23 | PP-09-060 | Light Vehicle Rollover Protection Requirements
24 | PP-09-100 | Health and Safety Management Plan
25 | PP-13-030 | Fauna Management
26 | PP-13-100 | Environmental Management Plan
27 | SPR-HR-GEN-005 | BHPBIO Approved Training Providers
28 | SPR-IEN-HC-001 | WAIO Hydrocarbon and Hazardous Chemicals Management
29 | SPR-IHS-000-001 | Light and Road Going Vehicle Use
30 | SPR-IHS-SAF-006 | Personal Protective Equipment
31 | SPR-IHS-SAF-018 | Working at Heights-Fall Injury Prevention Systems
32 | SPR-IHS-SAF-024 | Isolation and Permit to Work- Isolation, Lockout and Tagging
33 | SPR-IHS-SAF-027 | WAIO Requirments for Portable/Mobile Lighting Plants, Electrical Generators, Welding Machines, Electrical Distribution Boards, Compressors, Water Pumps and Fuel Trailers
34 | SPR-IHS-SAF-029 | Cranage, Lifting & Slinging
35 | SPR-IHS-SAF-073 | WAIO Drug and Alcohol Managgement
36 | SPR-IHS-SAF-082 | Working at Heights
37 | SPR-IHS-SAF-098 | WAIO Requirements for Light Vehicles and Surface Mobile Equipment
38 | SPR-IHS-SAFHY-009 | Occupational Hygiene Exposure Assessment and Control
39 | SPR-OHN-SAFES-001 | Vehicle Escort - On and Off Site
40 | SPR-IHS-SAFOH-004 | Irone Ore Fatigue Management Plan
41 | SPR-OHN-SAF-026 | Tropical Cyclone Preparedness and Response
42 | SPR-PHS-SAFES-001 | Port & Rail Cyclone Procedure
43 | WIN-IEN-HC-001 | Major/Minor Spill Response

## RISK ASSESSMENT
| Install/Repair "Hungry" boards | Working at Heights | Fall from height to ground | Failure of EWP - mechanical/hydraulic failure, toppling due to unstable ground conditions or high winds. Scaffold collapse - loosening of components (vibration and product build up) and/or during building and dismantling of scaffold structure, modification without approval. | Single Fatality | 4 | There are maximum 2 people working at any given time and therefore, most plausible scenario is a single fatality. | 1. Work at Height Task Management - Work at heights activities identified at work planning, controls identified and resourced 2. Work at Height Equipment Management - Ladders, Work Platforms, Mobile Equipment (EWP, Scissor Lift) and Scaffolds designed, inspected and maintained to BHPBIO standards 3. Fall Injury Prevention System Fall Injury Prevention equipment registered, tagged, inspected, worn and/or attached correctly prior to use. | Work at Height Rescue Plan in place and resources available | Single Fatality | 30 | 0.3 | 9 | Install temporary steps with handrails and handrails at the back of the tray.
Weeli Wolli Creek Newman Mainline 291km Bridge - Earthworks, Siteworks
Issue # | Activity/Task (Description) | Hazard/ Aspect | Unplanned/unwanted Event (Issue) | Contributing Factors/Causes Root Causes - Latent Causes - Direct Causes | Maximum Foreseeable Loss (Most plausible worst case scenario - controls not in place) | Severity Level (Based on MFL) | Basis for MFL | Current Controls |  | Impact (Most plausible worst case scenario - with controls in place) | Residual Risk |  |  | New Actions / Further Requirements | Actioned by Who? (Name and Surname) | Actioned By When
[8 empty] | Preventive Controls | Mitigating Controls |  | Severity Factor | Likelihood Factor | RRR
RAIL WORKS
people | Crane Operations (Lifting Tamper and Regulator off Mainline on to Construction Track) | Incompetent operators | Single Fatality Project delay Fouling of track causing track damage and train delays Equipment/Rail Mounted Equipment Interaction. Legislative Reportable incident Financial loss Plant / truck rollover Load failure / dropped objects | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No VOC process developed HR Recruitment process inadequate Insufficient risk assessment | Single Fatality Project delay Track damage Legislative Reportable incident Financial loss Crane collapse insufficient risk assessment | 5 | No pre-start checks completed Incorrect equipment used Untrained personnel No risk assessment completed No audits / checks undertaken No rigging or operating procedures implemented No training and VOC process in place | Trained and competent personnel identified through recruitment and VOC process Scheduled audits and inspections of safety management system Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) | Scheduled audits and inspections of safety management system Personnel placed on neccessary training course Removal of personnel from site | Minor equipment and property damage FAC injury | 10 | 0.3 | 3
equipment | Crane Operations (Lifting Tamper and Regulator off Mainline on to Construction Track) | Non compliant equipment | Loss of human life Fouling of track causing track damage and train delays Equipment/Rail Mounted Equipment Interaction. Permanent disability Breach of BHP policies and procedures Equipment failure Dropped objects | Tag & testing and inspections not completed by competent persons Lifting certifications not submitted State law Statutory check not undertaken | Loss of human life permanent disability Breach of BHP policies and procedures Financial loss Company's loss of reputation and future contracts | 4 | Lifting and rigging gear not compliant Daily gear check not undertaken Poor training and absent VOC process HR recruitment process inadequate | Lifting and rigging register developed compliant to site requirements Daily gear check undertaken Training and VOC process developed, implemented and communicated to all personnel HR recruitment process developed & reviewed periodically Lessons learnt process developed, implemented and timely actioned Health & safety management system to be reviewed periodically Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) | Daily gear check undertaken Cease use of non compliant equipment Arrangements made to replace non compliant equipment Lessons learnt process developed, implemented and timely actioned | MTI Minor Track damage Minimum financial loss | 10 | 1 | 10
environment | Crane Operations (Lifting Tamper and Regulator off Mainline on to Construction Track) | unstable ground | Loss of human life permanent disability Breach of BHP policies and procedures Equipment failure Dropped objects Crane collapse Fouling of track causing track damage and train delays Legislative Reportable incident | Poor planning Sufficient survey report on ground conditions Inclement weather Compaction of ground not completed Scope of works not adhered to Poor supervision Inadequate risk assessment | Single fatality Property damage / Loss Environmental damage / loss Financial loss Project delay | 4 | Incorrect equipment No risk assessment completed No audits / checks undertaken No loading / unloading procedures implemented No civil works to stabilise level ground | Correct surveying of area Ground compaction test completed and signed off Correct planning Risk assessments completed Trained and VOC competent personnel Civil works completed to required standard Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) | Inspect location prior to lift Suspend lifting operations Use neccessary plant to level and compact ground | Major Track damage Project delays Financial loss | 10 | 1 | 10
systems | Crane Operations (Lifting Tamper and Regulator off Mainline on to Construction Track) | Incorrect positioning crane | Loss of human life permanent disability Equipment failure Crane collapse | Poor planning Poor supervision Inadequate risk assessment | Single fatalities Property damage / Loss Environmental damage / loss Financial loss Project delay | 4 | No risk assessment completed No audits, inspection / checks undertaken | Correct surveying of area Correct planning Risk assessments completed Trained and VOC competent personnel Civil works completed to required standard | Perform prelift inspection Use survey data/drawings to relocate to correct location Lower suspended load to ground before relocating | Minor Track damage Project delays Financial loss | 10 | 1 | 10
systems | Crane Operations (Lifting Tamper and Regulator off Mainline on to Construction Track) | Load exceeding SWL | Loss of human life permanent disability Equipment failure Crane collapse Fouling of track causing track damage and train delays Crane damage | Poor planning Poor supervision Inadequate risk assessment Breach of BHP and state law requirements | Single fatalities Property damage / Loss Environmental damage / loss Financial loss Project delay | 4 | No pre-start checks completed Untrained personnel No risk assessment completed No audits / checks undertaken No rigging or operating procedures implemented No training and VOC process in place | Lifting and rigging register developed compliant to site requirements Daily gear check undertaken Training and VOC process developed, implemented and communicated to all personnel HR recruitment process developed & reviewed periodically Lessons learnt process developed, implemented and timely actioned Health & safety management system to be reviewed periodically Review load against SWL | Lifting and rigging register developed compliant to site requirements Daily gear check undertaken Mobilise a crane with greater capacity Operator experience and plant familirality Lower load to ground | Track damage Breaches of state law traffic and Mines Act legislation financial penalties | 10 | 1 | 10
equipment | Crane Operations (Lifting Tamper and Regulator off Mainline on to Construction Track) | Lifting gear failure | Loss of human life Environmental loss, damage and breach Fouling of track causing track damage and train delays Community impact Breach of the department of transport act & legislation | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No lifting procedures implemented poor planning | Multiple fatality Property damage / Loss Environmental damage / loss Financial loss Project delay Financial penalties Project delays | 4 | No pre-start checks completed Untrained personnel No risk assessment completed No audits / checks undertaken No rigging or operating procedures implemented No training and VOC process in place | Exclusion zones implemented Lifting and rigging register developed compliant to site requirements Daily gear check undertaken Training and VOC process developed, implemented and communicated to all personnel High risk activities controlled through audit and checklist system | Exclusion zones implemented TOA in place TPO on site Mobilisation of new plant and equipment Lessons learnt process developed, implemented and timely actioned | Track damage Breaches of state law traffic and Mines Act legislation financial penalties | 3 | 1 | 3
equipment | Crane Operations (Lifting Tamper and Regulator off Mainline on to Construction Track) | Mobile Plant/Vehicle/Pedestrian interface | Pedestrians hit by plant & equipment Loss of human life Project delays Compensation claim Legislative enquiry | Working without correct permits Inadequate TMP Poor communications No Training or VOC process in place Poor or no planning undertaken Unsure of work scope and limitations of boundaries | Pedestrians hit by plant & equipment Loss of human life Project delays Compensation claim Legislative enquiry | 4 | Incorrect equipment and permits not in place Untrained and not VOC'd personnel No risk assessment completed No audits / checks undertaken Prior planning not undertaken No risk assessment undertaken Poor or no supervision | Exclusion Zones TMP communicated, implemented and constantly reviewed Contractor meeting schedule developed and implemented Positive communications procedure developed and training conducted Pre- planning prior to commencing contract | Emergency response plan VHF radios Exclusion Zones TMP communicated, implemented and constantly reviewed | FAC injury Minor plant damage | 10 | 1 | 10
environment | Crane Operations (Lifting Tamper and Regulator off Mainline on to Construction Track) | Adverse weather conditions | Floods Storm damage Loss of productivity Environmental damage Crane Collapse Fouling of track causing track damage and train delays Loss of life ( Human & Animals) Community damage / loss | Cyclone & inclement weather preparedness process not implemented Not ceasing works during inclement weather Emergency management process not in place | Multiple fatality Property damage / Loss Environmental damage / loss | 4 | No due diligence process undertaken regarding the Hierarchy of controls of the hazards in the project environment | Emergency management process implemented Track, building audits and Q& A process system in place Reliable weather forecasting information source i.e. BOM etc Early warning detection systems implemented through warning network | Do not perform lift Ensure housekeeping is in good order Emergency management process implemented Reliable weather forecasting information source i.e. BOM etc Early warning detection systems implemented through warning network | Single fatality Minor Track damage | 3 | 1 | 3
Equipment | Crane Operations (Lifting Tamper and Regulator off Mainline on to Construction Track) | Communications failure | Rail Mounted Equipment/Personnel Interaction. Rail Mounted Equipment/Rail Mounted Equipment Interaction. Derailment Incident. Loss of life Equipment damage | Failure to conduct a full pre-start check (radio etc). Operator not the holder of a current Certificate of Competency, or under the direct supervision of someone with the relevant qualification. Non adherence to Communication protcols. Train Controller competency level inadequate. Non adherence to Train Control procedure. Failure to comply with Safeworking procedure. Incorrect identification of location. Failure to correctly verify location (Track Shorting Cables). Failure to complete a Take 5 risk assessment. | Single Fatality Injury plant and equipment damage | 4 | No pre-start checks completed No risk assessment completed No audits / checks undertaken No training and VOC process in place | Conduct a risk assessment (Take 5). Operater has completed and vaild VOC/licence. Train Controllers hold current required competency levels. Visually checking the trackside location signage to confirm location of crossing and orientation (East & West tracks). Strict adherence to Communications protocols. Strict adherence to Safeworking procedures. Strict adherence to procedure when verifying location with Track Shorting cables Strict adherence to adjacent track procedure Handheld VHF radio to be carried as back-up and also fitted with UHF | Cease work Perform radio check Perform change management risk assessment Sufficient radio battery chargers and spare radios available | Track damage Plant and equipment damage Minor injury | 10 | 1 | 10
equipment | Sleeper Laying | Rail Mounted Mobile Plant/Mobile Plant/Vehicle/Pedestrian interface | Track property, plant and equipment damage injury Loss of life | No Exclusion Zones Failure to follow Track Access Process Failure to Follow TPO directions Failure to follow supervisor instruction | Single Fatality Injury plant and equipment damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Exclusion Zones Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) TMP communicated, implemented and constantly reviewed Contractor meeting schedule developed and implemented Positive communications procedure developed and training conducted Pre- planning prior to commencing contract | Emergency management plan implemented VHF radio communications Exclusion Zones in place Cease work activities Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) | Minor injury Track damage | 10 | 1 | 10
people | Sleeper Laying | Incompetent Operators | Track property, plant and equipment damage injury, loss of life | Incompetent operator Faulty equipment No Exclusion Zones No Spotter | Single Fatality Injury plant and equipment damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Trained and competent personnel identified through recruitment and VOC process Scheduled audits and inspections of safety management system | Scheduled audits and inspections of safety management system Personnel placed on neccessary training course Removal of personnel from site | property damage personal injury | 10 | 1 | 10
equipment | Sleeper Laying | Faulty Mobile Plant/Vehicles | Track property, plant and equipment damage injury, loss of life | Failure to follow Track Access Authority requirements Incompetent operator Faulty equipment No Exclusion Zones No Spotter | Single Fatality Injury plant and equipment damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) Usage of correct parts and equipment maintenance schedule adhered to Training or VOC process in place Asset maintenance schedule developed Only qualified / trained personnel to operate / Maintian plant & equipment | Recover plant/vehicle from vulnerable location Audit plant and equipment on site Competent personnel Inform plant hire company / maintenance workshop | Plant and property damage personal injury | 10 | 1 | 10
environment | Sleeper Laying | Embankments/Uneven ground | Track property, plant and equipment damage injury | Failure to follow TPO Direction Incompetent operator Faulty equipment No Exclusion Zones Incorrect body posture prolonged static postures | Permanent disability Injury plant and equipment damage | 3 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Follow Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) Trained and competent personnel identified through recruitment process procedure for working on uneven surfaces implemented job rotation implemented work redesign considered buffer paths on formation identified with barricading Correct planning and scheduling Contractors to be inducted to site Plant and equipment to comply with BHP Environmental and site compliance inspection | Trained and competent personnel identified through recruitment process Work methodology reconsidered Buffer paths on formation identified with barricading Contractors to be inducted to site Plant and equipment to comply with BHP Environmental and site compliance inspection | minor damage | 10 | 1 | 10
systems | Sleeper Laying | Incorrect manual handling techniques and practices | injury to workers equipment damage | Over exertion Poor posture during lifting, handling Muscle Fatigue Isometric Muscle Movement Prolonged static postures Handling of sharp or awkward materials | Injury causing permanent damage | 3 | Failure to provide adequate training in correct manual handling techniques Failure to provide alternative manual handling equipment or mechanical aids | Risk assessment to be completed prior to starting task Provide PPE to personnel Correct PPE Implementation of safe lifting technique sessions Correct planning prior task Supervision to monitor review Risk assessments | Look out for work mates and speak up to stop the job and provide advice Provide PPE to personnel Correct PPE Implementation of safe lifting technique revision sessions Supervision to monitor review Risk assessments | FAC injury | 10 | 1 | 10
environment | Sleeper Laying | Hydrocarbon spill | environmental event | Contact with hazardous substances. Lack of / Out of Date MSDS's Inadequate Labelling of Substance containers Poor Decanting practices Uncontrolled Ignition sources Storage of incompatible substances Lack of Risk Assessment for Hazardous Substances; Spillage / Leakage of substances. Poor Decanting practices; Poor disposal of substances; Fail to identify less hazardous / alternative substances. | Personal Injury - Inhalation, Ingestion, Skin Contact; environmental event - contamination of area | 3 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Comply with PEAHR condition Registered and licenced contractor to be utilised Trained personnel of handling of hazardous substances Fatigue management procedure implemented and constantly monitored Emergency response and chemical spill training Approved Hazardous Storage facilities and transport vehicles | Use spill kits Bund area to minimise spreading Contact BHPBIO Environmental team Comply with PEAHR conditions | minor disturbance to ballast | 10 | 1 | 10
systems | Sleeper Laying | Unstable Sleeper Stacks | Track property, plant and equipment damage injury | failure to follow stacking procedure unloading. Loading of sleepers Uneven Ground Heavy Objects | Personal injury material damage | 3 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Pre-start checks completed Correct equipment Trained VOC'd personnel Risk assessment completed Audits / checks undertaken Loading / unloading procedures implemented | Use necessary plant and equipment to re-stack Identify new lay-down area Level ground surface Inspect stacks before performing each lift Cordon off with barricading | FAC injury | 10 | 1 | 10
Equipment | Sleeper Laying | Communications failure | Rail Mounted Equipment/Personnel Interaction. SME/Personnel Interaction Loss of life Equipment damage | Failure to conduct a full pre-start check Operator not the holder of a current Certificate of Competency, or under the direct supervision of someone with the relevant qualification. Non adherence to Communication protcols. Train Controller competency level inadequate. Non adherence to Train Control procedure. Failure to comply with Safeworking procedure. Incorrect identification of location. Failure to correctly verify location (Track Shorting Cables). Failure to complete a Take 5 risk assessment. | Single Fatality Injury plant and equipment damage | 4 | No pre-start checks completed No risk assessment completed No audits / checks undertaken No training and VOC process in place | Conduct a risk assessment (Take 5). Operater has completed and vaild VOC/licence. Train Controllers hold current required competency levels. Visually checking the trackside location signage to confirm location of crossing and orientation (East & West tracks). Strict adherence to Communications protocols. Strict adherence to Safeworking procedures. Strict adherence to procedure when verifying location with Track Shorting cables Strict adherence to adjacent track procedure Handheld VHF radio to be carried as back-up and also fitted with UHF | Cease work Perform radio check Perform change management risk assessment Sufficient radio battery chargers and spare radios available | Track damage Plant and equipment damage Minor injury | 10 | 1 | 10
equipment | Laying of Rail | Rail Mounted Mobile Plant/Mobile Plant/Vehicle/Pedestrian interface | Track property, plant and equipment damage injury Loss of life | Failure to provide pre start information on interactions with other contractors Failure to implement Track Access Procedures Failure to follow TPO directions | Single Fatality Injury plant and equipment damage | 5 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Exclusion Zones Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) TMP communicated, implemented and constantly reviewed WP4 form Implemented Contractor meeting schedule developed and implemented Positive communications procedure developed and training conducted Pre- planning prior to commencing contract | Emergency management plan implemented VHF radio communications Exclusion Zones in place Cease work activities Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) | personal injury property damage | 10 | 1 | 10
people | Laying of Rail | Incompetent Operators | Track property, plant and equipment damage injury | Failure to follow procedure regarding VOC and ATO process Failure to provide adequate supervision | Personal injury material damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Trained and competent personnel identified through recruitment and VOC process Scheduled audits and inspections of safety management system and procedures | Scheduled audits and inspections of safety management system Personnel placed on neccessary training course Removal of personnel from site | FAC injury | 10 | 1 | 10
equipment | Laying of Rail | Faulty Rail Mounted Mobile Plant & Mobile Plant | Track property, plant and equipment damage injury | Failure to conduct pre start Scheduled maintenance not conducted | Equipment Damage Personal Injury | 4 | Failure to correctly assess machine conditions and adhere to procedure Failure to provide adequate training Poor planning Inadequate supervision | Usage of correct parts and equipment maintenance schedule adhered to Training or VOC process in place Asset maintenance schedule developed Only qualified / trained personnel to be operate / Mainian plant & equipment | Recover plant/vehicle from vulnerable location Audit plant and equipment on site Competent personnel Inform plant hire company / maintenance workshop | Minor injury Track damage | 10 | 1 | 10
environment | Laying of Rail | Embankments/Uneven ground | Track property, plant and equipment damage injury | Failure to follow Track Access Requirements Incompetent operator Faulty equipment No Exclusion Zones No Spotter | Single Fatality Injury plant and equipment damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) Exclusion zones implemented Pre-start checks completed Correct equipment Trained VOC'd personnel High risk licenced operator Risk assessment completed Audits / checks undertaken Loading / unloading procedures implemented | Trained and competent personnel identified through recruitment process Work methodology reconsidered Buffer paths on formation identified with barricading Contractors to be inducted to site Plant and equipment to comply with BHP Environmental and site compliance inspection | property damage personal injury | 10 | 1 | 10
people | Laying of Rail | Interaction with other contractors | Track property, plant and equipment damage Fatality | Failure to provide pre start information on interactions with other contractors Failure to implement Track Access Procedures Failure to follow TPO directions | Single Fatality Injury plant and equipment damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Exclusion zones implemented General Alert information provided at pre start communications Correct equipment / guards Trained personnel Positive communications, and allocated radio channels used Risk assessment completed Audits / checks undertaken Implement and communicate TMP and scope to all contractors through EPCM alert system, as required | Exclusion zones implemented General Alert information provided at pre start communications Correct equipment / guards Trained personnel Positive communications, and allocated radio channels used Risk assessment completed Audits / checks undertaken Implement and communicate TMP and scope to all contractors through EPCM alert system, as required | Injury Minor Track damage | 10 | 1 | 10
systems | Laying of Rail | Travelling with load | Track property, plant and equipment damage injury | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No loading / unloading procedures implemented | Single Fatality Injury plant and equipment damage | 4 | Incorrect equipment and permits not in place Untrained and not VOC'd personnel No risk assessment completed No audits / checks undertaken Prior planning not undertaken No risk assessment undertaken Poor or no supervision | Exclusion zones implemented TMP communicated, implemented and constantly reviewed Contractor meeting schedule developed and implemented Positive communications procedure developed and training conducted Pre- planning prior to commencing contract | Work crew notified of day's activities at pre-start Radio communication between all work personnel Exclusion zone in place Prelift check and inspection complete | property damage | 10 | 1 | 10
environment | Laying of Rail | Hydrocarbon spill | Track property, plant and equipment damage injury | Contact with hazardous substances. Lack of / Out of Date MSDS's Inadequate Labelling of Substance containers Poor Decanting practices Uncontrolled Ignition sources Storage of incompatible substances Lack of Risk Assessment for Hazardous Substances; Spillage / Leakage of substances. Poor Decanting practices; Poor disposal of substances; Fail to identify less hazardous / alternative substances. | Personal Injury - Inhalation, Ingestion, Skin Contact; environmental event - contamination of area |  | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Registered and licenced contractor to be utilised Trained personnel of handling of hazardous substances Fatigue management procedure implemented and constantly monitored Emergency response and chemical spill training Approved Hazardous Storage facilities and transport vehicles | Use spill kits Bund area to minimise spreading Contact BHPBIO Environmental team Comply with PEAHR conditions |  | 10 | 1 | 10
Equipment | Laying of Rail | Communications failure | Rail Mounted Equipment/Personnel Interaction. SME/Personnel Interaction. Loss of life Equipment damage | Failure to conduct a full pre-start check (radio etc). Operator not the holder of a current Certificate of Competency, or under the direct supervision of someone with the relevant qualification. Non adherence to Communication protcols. Train Controller competency level inadequate. Non adherence to Train Control procedure. Failure to comply with Safeworking procedure. Incorrect identification of location. Failure to correctly verify location (Track Shorting Cables). Failure to complete a Take 5 risk assessment. | Single Fatality Injury plant and equipment damage | 4 | No pre-start checks completed No risk assessment completed No audits / checks undertaken No training and VOC process in place | Conduct a risk assessment (Take 5). Operater has completed and vaild VOC/licence. Train Controllers hold current required competency levels. Visually checking the trackside location signage to confirm location of crossing and orientation (East & West tracks). Strict adherence to Communications protocols. Strict adherence to Safeworking procedures. Strict adherence to procedure when verifying location with Track Shorting cables Strict adherence to adjacent track procedure Handheld VHF radio to be carried as back-up and also fitted with UHF | Cease work Perform radio check Perform change management risk assessment Sufficient radio battery chargers and spare radios available | Track damage Plant and equipment damage Minor injury | 10 | 1 | 10
people | Welding of Rail | Incompetent Welders | Track not built to specifications Unable to utilise tracks Rework to meet specifications Track damage | Incompetent welder Inadequate Supervision Lack of reporting failures Excessive risk tolerance poor environmental conditions Faulty equipment | Track damage Reputational loss Commercial loss | 3 | Failure to comply with procedure Failure to conduct adequate VOC and ATO process Failure to provide adequate supervision | Trained and competent personnel identified through recruitment and VOC process Scheduled audits and inspections of safety management system and procedures | Scheduled audits and inspections of safety management system Personnel placed on neccessary training course Removal of personnel from site | financial loss | 3 | 1 | 3
equipment | Welding of Rail | Rail Mounted Mobile Plant/Mobile Plant/Vehicle/Pedestrian interface | Track property, plant and equipment damage Fatality | No Exclusion Zones Failure to follow Track Access Process Failure to Follow TPO directions Failure to follow supervisor instruction | Fatality equipment damage reputational loss | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to understand and sign onto WP4 Form Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Exclusion zones in place Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) WP4 Form implemented and adhered to Contractor meeting schedule developed and implemented Positive communications procedure developed and training conducted Pre- planning prior to commencing contract | Emergency management plan implemented VHF radio communications Exclusion Zones in place Cease work activities Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) | personal injury equipment damage | 10 | 1 | 10
equipment | Welding of Rail | Faulty Rail Mounted Mobile Plant & Mobile Plant | Track property, plant and equipment damage injury | Faulty equipment Excessive risk tolerance poor environmental conditions inadequate Supervision | Track damage Reputational loss Commercial loss | 4 | Failure to comply with procedure Failure to conduct pre starts and machine maintenance Failure to provide adequate supervision | Usage of correct parts and equipment maintenance schedule adhered to Training or VOC process in place Asset maintenance schedule developed Only qualified / trained personnel to be operate / Mainian plant & equipment | Recover plant/vehicle from vulnerable location Audit plant and equipment on site Competent personnel Inform plant hire company / maintenance workshop |  | 10 | 1 | 10
systems | Welding of Rail | Incorrect manual handling techniques and practices | Track property, plant and equipment damage injury | • Over-exertion (excessive manual lifting force); • Poor posture during lifting/handling; • Muscle fatigue; • Repetitious movement; • Prolonged static postures; • Handling of sharp / hazardous loads; | • Personal Injury - Slip, Trip, Fall; • Personal Injury - Musculoskeletal injury (Strain/disc injury); • Personal Injury - Hand injury (Crush / Laceration). | 3 | Incorrect body posture Isometric muscle movement Inadequate training in manual handling, correct body posture techniques | Risk assessment to be completed prior to starting task Provide PPE to personnel Correct PPE job rotation process Implementation of safe lifting technique sessions Correct planning prior task Supervision to monitor review Risk assessments | Look out for work mates and speak up to stop the job and provide advice Provide PPE to personnel Correct PPE Implementation of safe lifting technique revision sessions Supervision to monitor review Risk assessments | FAC injury | 3 | 1 | 3
equipment | Welding of Rail | Flames, Sparks from Welding, Cutting and Grinding | Personal injury | Inadequate training failure to follow process Incorrect PPE failure to implement exclusion zones | Eye Injury Hand Injury Burns Foreign body lodgement | 4 | Inadequate training and VOC< ATO process Failure to follow procedure Inadequate PPE inadequate supervision | Exclusion zone implemented around work area. Screens/Barriers erected Tested and tagged equipment, Welding screens utilised where possible; Provision of emergency equipment, including fire extinguishers and first aid kits; Restraint devices for cords/leads; Gas bottles restrained in an upright position by chains; Gas bottles transported in an upright position by suitable trolleys or other mechanical aids; Provision of appropriate storage facilities for gasses (e.g. segregation from non-compatible substances); | Additional PPE worn to standard issue Exclusion zone implemented around work area. Screens/Barriers erected Tested and tagged equipment, Welding screens utilised where possible; Provision of emergency equipment, including fire extinguishers and first aid kits; Provision of appropriate storage facilities for gasses (e.g. segregation from non-compatible substances); | personal injury | 10 | 1 | 10
Equipment | Welding of Rail | Communications failure | Rail Mounted Equipment/Personnel Interaction. Rail Mounted Equipment/Rail Mounted Equipment Interaction. Derailment Incident. Loss of life Equipment damage | Failure to conduct a full pre-start check (radio etc). Operator not the holder of a current Certificate of Competency, or under the direct supervision of someone with the relevant qualification. Non adherence to Communication protcols. Train Controller competency level inadequate. Non adherence to Train Control procedure. Failure to comply with Safeworking procedure. Incorrect identification of location. Failure to correctly verify location (Track Shorting Cables). Failure to complete a Take 5 risk assessment. | Single Fatality Injury plant and equipment damage | 4 | No pre-start checks completed No risk assessment completed No audits / checks undertaken No training and VOC process in place | Conduct a risk assessment (Take 5). Operater has completed and vaild VOC/licence. Train Controllers hold current required competency levels. Visually checking the trackside location signage to confirm location of crossing and orientation (East & West tracks). Strict adherence to Communications protocols. Strict adherence to Safeworking procedures. Strict adherence to procedure when verifying location with Track Shorting cables Strict adherence to adjacent track procedure Handheld VHF radio to be carried as back-up and also fitted with UHF | Cease work Perform radio check Perform change management risk assessment Sufficient radio battery chargers and spare radios available | Track damage Plant and equipment damage Minor injury | 10 | 1 | 10
people | Grinding of Rail | Incompetent Operator | Single Fatality Project delay Track damage Legislative Reportable incident Financial loss Plant / truck rollover Load failure / dropped objects | Failure to follow Track Access Requirements No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No VOC process developed HR Recruitment process inadequate Insufficient risk assessment | Single Fatality Project delay Track damage Legislative Reportable incident Financial loss Crane collapse Insufficient risk assessment | 4 | No pre-start checks completed Incorrect equipment used Untrained personnel No risk assessment completed No audits / checks undertaken No rigging or operating procedures implemented No training and VOC process in place | Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) Trained and competent personnel identified through recruitment and VOC process Scheduled audits and inspections of safety management system | Scheduled audits and inspections of safety management system Personnel placed on neccessary training course Removal of personnel from site |  | 10 | 1 | 10
systems | Grinding of Rail | Incorrect manual handling techniques and practices | Personal injury leading to permanent damage | Over-exertion (excessive manual lifting force); Poor posture during lifting/handling; Muscle fatigue; Repetitious movement; Prolonged static postures; Handling of sharp / hazardous loads; | Personal Injury - Slip, Trip, Fall; Personal Injury - Musculoskeletal injury (Strain/disc injury); Personal Injury - Hand injury (Crush / Laceration). | 4 | Incorrect body posture Isometric muscle movement Inadequate training in manual handling, correct body posture techniques | Use of mechanical aids where possible this may include: - Cranes; - Trolleys; - Hoists. Optimal storage/transport of equipment and materials Correct Manual Handling Techniques Job rotation | Look out for work mates and speak up to stop the job and provide advice Provide PPE to personnel Correct PPE Implementation of safe lifting technique revision sessions Supervision to monitor review Risk assessments | personal injury | 10 | 1 | 10
Equipment | Grinding of Welds | Communications failure | Rail Mounted Equipment/Personnel Interaction. SME/Personnel Interaction. Derailment Incident. Loss of life Equipment damage | Failure to conduct a full pre-start check Operator not the holder of a current Certificate of Competency, or under the direct supervision of someone with the relevant qualification. Non adherence to Communication protcols. Train Controller competency level inadequate. Non adherence to Train Control procedure. Failure to comply with Safeworking procedure. Incorrect identification of location. Failure to correctly verify location (Track Shorting Cables). Failure to complete a Take 5 risk assessment. | Single Fatality Injury plant and equipment damage | 4 | No pre-start checks completed No risk assessment completed No audits / checks undertaken No training and VOC process in place | Conduct a risk assessment (Take 5). Operater has completed and vaild VOC/licence. Train Controllers hold current required competency levels. Visually checking the trackside location signage to confirm location of crossing and orientation (East & West tracks). Strict adherence to Communications protocols. Strict adherence to Safeworking procedures. Strict adherence to procedure when verifying location with Track Shorting cables Strict adherence to adjacent track procedure Handheld VHF radio to be carried as back-up and also fitted with UHF | Cease work Perform radio check Perform change management risk assessment Sufficient radio battery chargers and spare radios available | Track damage Plant and equipment damage Minor injury | 10 | 1 | 10
environment | Clipping Up of Rail | Embankments/Uneven ground | Personal injury leading to permanent damage | • Over-exertion (excessive manual lifting force); • Poor posture during lifting/handling; • Muscle fatigue; • Repetitious movement; • Prolonged static postures; • Handling of sharp / hazardous loads; | Personal Injury - Slip, Trip, Fall; Personal Injury - Musculoskeletal injury (Strain/disc injury); Personal Injury - Hand injury (Crush / Laceration). | 4 | Incorrect body posture Isometric muscle movement Inadequate training in manual handling, correct body posture techniques | Trained and competent personnel identified through recruitment process procedure for working on uneven surfaces implemented job rotation implemented work redesign considered buffer paths on formation identified with barricading Correct planning and scheduling Contractors to be inducted to site Plant and equipment to comply with BHP Environmental and site compliance inspection | Trained and competent personnel identified through recruitment process Work methodology reconsidered Buffer paths on formation identified with barricading Contractors to be inducted to site Plant and equipment to comply with BHP Environmental and site compliance inspection |  | 10 | 1 | 10
systems | Clipping Up of Rail | Incorrect manual handling techniques and practices | Personal injury leading to permanent damage | • Over-exertion (excessive manual lifting force); • Poor posture during lifting/handling; • Muscle fatigue; • Repetitious movement; • Prolonged static postures; • Handling of sharp / hazardous loads; | • Personal Injury - Slip, Trip, Fall; • Personal Injury - Musculoskeletal injury (Strain/disc injury); • Personal Injury - Hand injury (Crush / Laceration). | 3 | Incorrect body posture Isometric muscle movement Inadequate training in manual handling, correct body posture techniques | Job rotation system to be implemented Risk assessment to be completed prior to starting task Provide PPE to personnel Correct PPE Implementation of safe lifting technique sessions Correct planning prior task Supervision to monitor review Risk assessments | Look out for work mates and speak up to stop the job and provide advice Provide PPE to personnel Correct PPE Implementation of safe lifting technique revision sessions Supervision to monitor review Risk assessments | FAC injury | 10 | 1 | 10
people | Clipping Up of Rail | Interaction with other contractors | Track property, plant and equipment damage Fatality | Failure to provide pre start information on interactions with other contractors Failure to implement Track Access Procedures Failure to follow TPO directions | Single Fatality Injury plant and equipment damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Pre start to communicate General alerts, contractor movements Correct equipment / guards Trained personnel Positive communications, and allocated radio channels used Risk assessment completed Audits / checks undertaken Implement and communicate TMP and scope to all contractors through EPCM alert system, as required | Pre start to communicate General alerts, contractor movements Designated and demarcated work areas Radio communication signs in place to notify/remind work crews Positive communications, and allocated radio channels used Implement and communicate TMP and scope to all contractors through EPCM alert system, as required | personal injury financial loss | 10 | 1 | 10
people | Ballasting | Incompetent Ballast Train Operator | Single Fatality Project delay Track damage Legislative Reportable incident Financial loss Plant / truck rollover Load failure / dropped objects | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No VOC process developed HR Recruitment process inadequate Insufficient risk assessment | Single Fatality Project delay Track damage Legislative Reportable incident Financial loss Crane collapse Insufficient risk assessment | 4 | No pre-start checks completed Incorrect equipment used Untrained personnel No risk assessment completed No audits / checks undertaken No rigging or operating procedures implemented No training and VOC process in place | Trained and competent personnel identified through recruitment and VOC process Scheduled audits and inspections of safety management system | Scheduled audits and inspections of safety management system Personnel placed on neccessary training course Removal of personnel from site | property damage personal injury | 10 | 1 | 10
equipment | Ballasting | Ballast Train/Mobile Plant/Vehicle/Pedestrian interface | Track property, plant and equipment damage injury Loss of life | Failure to provide pre start information on interactions with other contractors Failure to implement Track Access Procedures Failure to follow TPO directions | Single Fatality Injury plant and equipment damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) Contractor meeting schedule developed and implemented Positive communications procedure developed and training conducted Pre- planning prior to commencing contract | Emergency management plan implemented VHF radio communications Exclusion Zones in place Cease work activities Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) | personal injury property damage | 10 | 1 | 10
equipment | Ballasting | Faulty Ballast Train & Mobile Plant | Track property, plant and equipment damage injury | Faulty equipment Excessive risk tolerance poor environmental conditions inadequate Supervision | Track damage Reputational loss Commercial loss | 3 | Failure to comply with procedure Failure to conduct pre starts and machine maintenance Failure to provide adequate supervision | Usage of correct parts and equipment maintenance schedule adhered to Training or VOC process in place Asset maintenance schedule developed Only qualified / trained personnel to be operate / Mainian plant & equipment | Recover plant/vehicle from vulnerable location Audit plant and equipment on site Competent personnel Inform plant hire company / maintenance workshop | property damage | 10 | 1 | 10
systems | Ballasting | Incorrect manual handling techniques and practices | Track property, plant and equipment damage injury | • Over-exertion (excessive manual lifting force); • Poor posture during lifting/handling; • Muscle fatigue; • Repetitious movement; • Prolonged static postures; • Handling of sharp / hazardous loads; | • Personal Injury - Slip, Trip, Fall; • Personal Injury - Musculoskeletal injury (Strain/disc injury); • Personal Injury - Hand injury (Crush / Laceration). | 3 | Incorrect body posture Isometric muscle movement Inadequate training in manual handling, correct body posture techniques | Risk assessment to be completed prior to starting task Provide PPE to personnel Correct PPE Implementation of safe lifting technique sessions Correct planning prior task Supervision to monitor review Risk assessments | Look out for work mates and speak up to stop the job and provide advice Provide PPE to personnel Correct PPE Implementation of safe lifting technique revision sessions Supervision to monitor review Risk assessments | personal injury | 10 | 1 | 10
environment | Ballasting | Hydrocarbon spill | environmental event | Contact with hazardous substances. Lack of / Out of Date MSDS's Inadequate Labelling of Substance containers Poor Decanting practices Uncontrolled Ignition sources Storage of incompatible substances Lack of Risk Assessment for Hazardous Substances; Spillage / Leakage of substances. Poor Decanting practices; Poor disposal of substances; Fail to identify less hazardous / alternative substances. | Personal Injury - Inhalation, Ingestion, Skin Contact; environmental event - contamination of area | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Registered and licenced contractor to be utilised Trained personnel of handling of hazardous substances Fatigue management procedure implemented and constantly monitored Emergency response and chemical spill training Approved Hazardous Storage facilities and transport vehicles | Use spill kits Bund area to minimise spreading Contact BHPBIO Environmental team Comply with PEAHR conditions |  | 10 | 1 | 10
Equipment | Ballasting | Communications failure | Rail Mounted Equipment/Personnel Interaction. Rail Mounted Equipment/Rail Mounted Equipment Interaction. Derailment Incident. Loss of life Equipment damage | Failure to conduct a full pre-start check Operator not the holder of a current Certificate of Competency, or under the direct supervision of someone with the relevant qualification. Non adherence to Communication protcols. Train Controller competency level inadequate. Non adherence to Train Control procedure. Failure to comply with Safeworking procedure. Incorrect identification of location. Failure to correctly verify location (Track Shorting Cables). Failure to complete a Take 5 risk assessment. | Single Fatality Injury plant and equipment damage | 4 | No pre-start checks completed No risk assessment completed No audits / checks undertaken No training and VOC process in place | Conduct a risk assessment (Take 5). Operater has completed and vaild VOC/licence. Train Controllers hold current required competency levels. Visually checking the trackside location signage to confirm location of crossing and orientation (East & West tracks). Strict adherence to Communications protocols. Strict adherence to Safeworking procedures. Strict adherence to procedure when verifying location with Track Shorting cables Strict adherence to adjacent track procedure Handheld VHF radio to be carried as back-up and also fitted with UHF | Cease work Perform radio check Perform change management risk assessment Sufficient radio battery chargers and spare radios available | Track damage Plant and equipment damage Minor injury | 10 | 1 | 10
| Tamping and Regulating | Moving plant to and from site (on track) | Rail Mounted Equipment/vehicle Interaction. Plant Damage. Location damage Collision | Complacency Familiarity Inexperienced Unfit for Work Failure to Adhere to procedure. Operated out side design rules Uneven ground, Travelling too fast, Plant brake down. Not parked in a position of safety Other drivers complacency/driving practices. Non adherence to existing procedures/Work Instructions. Failure to complete a Take 5 risk assessment. Rail Mounted Equipment/vehicle Interaction. | Single Fatality Project delay Track damage Legislative Reportable incident Financial loss Insufficient risk assessment | 4 | No pre-start checks completed Incorrect equipment used Untrained personnel No risk assessment completed No audits / checks undertaken No rigging or operating procedures implemented No training and VOC process in place | TMM prestart completed and passed TMM personnel completed and pass prestart/ fit for work TMMs fitted with working UHF and VHF radios TMMs maintenance records TMP planned and approved TMMs approved to be on rail network Trained personnel with VOC/licence Planned track maintenance activities performed | Maintain communication through UHF and VHF radios TMP planned and approved Only planned track maintenance activities performed TMMs approved to be on rail network | property damage personal injury | 10 | 1 | 10
people | Tamping and Regulating | Incompetent Tamper/Regulator Operator | Personal injury Project delay Track damage Legislative Reportable incident Financial loss Plant / truck rollover Load failure / dropped objects | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No VOC process developed HR Recruitment process inadequate insufficient risk assessment | Single Fatality Project delay Track damage Legislative Reportable incident Financial loss Insufficient risk assessment | 4 | No pre-start checks completed Incorrect equipment used Untrained personnel No risk assessment completed No audits / checks undertaken No rigging or operating procedures implemented No training and VOC process in place | Exclusion zones implemented Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) Trained and competent personnel identified through recruitment and VOC process Scheduled audits and inspections of safety management system | Scheduled audits and inspections of safety management system Personnel placed on neccessary training course Removal of personnel from site | property damage personal injury | 10 | 1 | 10
equiipment | Tamping and Regulating | Tamper/Regulator/Mobile Plant/Vehicle/Pedestrian interface | Track property, plant and equipment damage injury Loss of life | Failure to provide pre start information on interactions with other contractors Failure to implement Track Access Procedures Failure to follow TPO directions | Single Fatality Injury plant and equipment damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) Contractor meeting schedule developed and implemented Positive communications procedure developed and training conducted Pre- planning prior to commencing contract | Emergency management plan implemented VHF radio communications Exclusion Zones in place Cease work activities Operate under TPO Direction and with appropriate level of track protection in place(Refer RRB M02) | property damage personal injury | 10 | 1 | 10
equipment | Tamping and Regulating | Faulty Tamper/Regulator/Mobile Plant | Track property, plant and equipment damage injury | Faulty equipment Excessive risk tolerance poor environmental conditions inadequate Supervision | Track damage Reputational loss Commercial loss | 4 | Failure to comply with procedure Failure to conduct pre starts and machine maintenance Failure to provide adequate supervision | Usage of correct parts and equipment maintenance schedule adhered to Training or VOC process in place Asset maintenance schedule developed Only qualified / trained personnel to be operate / Mainian plant & equipment | Recover plant/vehicle from vulnerable location Audit plant and equipment on site Competent personnel Inform plant hire company / maintenance workshop |  | 10 | 1 | 10
systems | Tamping, Regulating & FBW | Incorrect manual handling techniques and practices | Personal injury leading to permanent damage | Over-exertion (excessive manual lifting force); Poor posture during lifting/handling; Muscle fatigue; Repetitious movement; Prolonged static postures; Handling of sharp / hazardous loads; | Personal Injury - Slip, Trip, Fall; Personal Injury - Musculoskeletal injury (Strain/disc injury); Personal Injury - Hand injury (Crush / Laceration). | 3 | Incorrect body posture Isometric muscle movement Inadequate training in manual handling, correct body posture techniques | Job rotation to be in place Risk assessment to be completed prior to starting task Provide PPE to personnel Correct PPE Implementation of safe lifting technique sessions Correct planning prior task Supervision to monitor review Risk assessments | Look out for work mates and speak up to stop the job and provide advice Provide PPE to personnel Correct PPE Implementation of safe lifting technique revision sessions Supervision to monitor review Risk assessments | FAC injury | 10 | 1 | 10
environment | Tamping, Regulating & FBW | Inhalation of dust | Track property, plant and equipment damage injury | Hot, dry conditions, movement of ballast, tamping plant movements passing traffic, trains | • Personal Injury - Inhalation, Ingestion; • environmental event - contamination of area | 3 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Dust suppression controls in place Dust masks where required exclusion zones in place | First aid administered to IP Remove IP from site and place IP indoors | FAC injury | 10 | 1 | 10
environment | Tamping, Regulating & FBW | Hydrocarbon spill | environmental event | Contact with hazardous substances. Lack of / Out of Date MSDS's Inadequate Labelling of Substance containers Poor Decanting practices Uncontrolled Ignition sources Storage of incompatible substances Lack of Risk Assessment for Hazardous Substances; Spillage / Leakage of substances. Poor Decanting practices; Poor disposal of substances; Fail to identify less hazardous / alternative substances. | Personal Injury - Inhalation, Ingestion, Skin Contact; environmental event - contamination of area | 3 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | Registered and licenced contractor to be utilised Trained personnel of handling of hazardous substances Fatigue management procedure implemented and constantly monitored Emergency response and chemical spill training Approved Hazardous Storage facilities and transport vehicles | Use spill kits Bund area to minimise spreading Contact BHPBIO Environmental team Comply with PEAHR conditions | Environmental damage | 10 | 1 | 10
| Tamping, Regulating & FBW | Operating TMMs on Mainline | Rail Mounted Equipment/Personnel Interaction. Rail Mounted Equipment/Rail Mounted Equipment Interaction. Derailment Incident. Loss of life Equipment damage | Axle Failure, Tyres/Wheels wear beyond limits. Uncertified Ropes causing attachments to fall. Potential for run away. Speeding when travelling Complacency Familiarity Inexperienced Unfit for Work Operated out side design rules | Single Fatality Injury plant and equipment damage | 4 | No pre-start checks completed No risk assessment completed No audits / checks undertaken No training and VOC process in place Poor Planning | Safe-Starts, Pre-Starts, Services and Inspection to be performed as per schedule. All testing & tagging to be current. TMM & FBW to be operated in accordance with OMM Ensure TMMs approved scheduled inspection for serviceability is completed. Ensure TMMs critical component checks is completed. Machine is to be tagged out idf unserviceable Warning stickers fitted. Strict adherence to Safeworking procedures. Operate under Train control or TPO Direction and with appropriate level of track protection in place(Refer RRB M02) Ensure work group is managed to avoid interacting with larger Surface Mobile Plant. Licenced and Competent operators only. Operator to hold a current nationally recognized competency for Track Machine Operation (TMO) Exit TMM on to track live side shall not occur without adjacent track | Daily activities to be communicated to work crew during safe start Work crew to understand procedure for working adjacent to track Operator to hold valid VOC Operator to be trained in BHPBIO procedures for track Operator to maintain communiction with train control and TPO | Track damage Plant and equipment damage Minor injury | 10 | 1 | 10
Equipment | Tamping, Regulating & FBW | Communications failure | Rail Mounted Equipment/Personnel Interaction. Rail Mounted Equipment/Rail Mounted Equipment Interaction. Derailment Incident. Loss of life Equipment damage | Failure to conduct a full pre-start check Operator not the holder of a current Certificate of Competency, or under the direct supervision of someone with the relevant qualification. Non adherence to Communication protcols. Train Controller competency level inadequate. Non adherence to Train Control procedure. Failure to comply with Safeworking procedure. Incorrect identification of location. Failure to correctly verify location (Track Shorting Cables). Failure to complete a Take 5 risk assessment. | Single Fatality Injury plant and equipment damage | 4 | No pre-start checks completed No risk assessment completed No audits / checks undertaken No training and VOC process in place | Conduct a risk assessment (Take 5). Operater has completed and vaild VOC/licence. Train Controllers hold current required competency levels. Visually checking the trackside location signage to confirm location of crossing and orientation (East & West tracks). Strict adherence to Communications protocols. Strict adherence to Safeworking procedures. Strict adherence to procedure when verifying location with Track Shorting cables Strict adherence to adjacent track procedure Handheld VHF radio to be carried as back-up and also fitted with UHF | Cease work Perform radio check Perform change management risk assessment Sufficient radio battery chargers and spare radios available | Track damage Plant and equipment damage Minor injury | 10 | 1 | 10
DO NOT REMOVE
[17 empty] | Severity | Likelihood | MFL Level | Entered in to 1SAP
[17 empty] | 1000 | 10 | 1 |  | Yes
[17 empty] | 300 | 3 | 2 |  | No
[17 empty] | 100 | 1 | 3
[17 empty] | 30 | 0.3 | 4
[17 empty] | 10 | 0.1 | 5
[17 empty] | 3 | 0.03 | 6
[17 empty] | 1 |  | 7

## Risk reduction action plan
Risk Redution Action Plan |  |  | Weeli Wolli Creek Newman Mainline 291km Bridge - Earthworks, Siteworks
No | Risk Assessment Event | Action | Responsiblility | Due Date | 1SAP Notification number | Status | Comments / Progress
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21

## GLD.017 Risk matrix
Risk Assessment Matrix (RRR)

## BowTie - Example
Site / Department: | [6 empty] | BOW-TIE DIAGRAM | [7 empty] | DATE:
CONTROL STATUS: |  | Effective | [9 empty] | RISK OWNER:
|  |  | RISK ISSUE: (RISK SOURCE) |  |  |  | Lifting
CAUSES | [12 empty] | IMPACTS
1 | Mechanical failure of crane | [11 empty] | 1 | Fatality
2 | Unauthorised modifications to crane | [11 empty] | 2 | Equipment damage
3 | Overloading / overextending crane | [11 empty] | 3 | Loss of production
4 | Ground / foundation failure | [11 empty] | 4
5 | Another piece of equipment/load enters in path of moving load | [11 empty] | 5
6 | Failure to control movement of crane | [11 empty] | 6
7 | Failure of lifting equipment (slings, chains, hooks) | [11 empty] | 7
8 | Poor rigging/slinging of load | [11 empty] | 8
9 | Load becomes entangled/caught on structure or strikes structure | [11 empty] | 9
10 | Uneven loads between two cranes |  |  | LIKELIHOOD |  | 1 |  | MFL |  |  |  |  | 10
11 | Sudden crane movements |  |  | SEVERITY |  | 30 |  | FATALITIES |  | 1
12 |  |  |  | RRR |  | 30 |  |  | US$M | 50 | 50
EXISTING PREVENTIVE CONTROLS |  |  | LINK TO CAUSES | C/C | CONTROL OWNER |  |  | EXISTING MITIGATING CONTROLS | [6 empty] | LINK TO IMPACTS | C/C | CONTROL OWNER
1 | Crane Inspection and Maintenance |  | 1,2,3,7 | Y |  |  |  | 1 | EMERGENCY RESPONSE | [5 empty] | 1 | Y
2 | Pre lift assessment and control of lift area |  | 7,8,9 | Y |  |  |  | 2
3 | Lifting gear inspection |  | 1,2,3,4,5,6,7,8 | Y |  |  |  | 3
4 | Crane Operation Controls |  | 1-11 | Y |  |  |  | 4
5 | Lifting Training and Competency |  | 1-11 | Y |  |  |  | 5
6 | Pre-job planning |  | 4,5,6,8,10,11 | N |  |  |  | 6
7 | Compacting ground where necessary |  | 4,5,6,10,11 | N |  |  |  | 7
8 | Change of scope / operating conditions - Risk re-assessed |  | 1,2,3,4,5,6,9,10,11 | N |  |  |  | 8
9 | [7 empty] | 9
10 | [7 empty] | 10
11 | [7 empty] | 11
IMPROVEMENT TASKS |  |  |  | DUE DATE | TASK OWNER |  |  | IMPROVEMENT TASKS | [6 empty] | DUE DATE | TASK OWNER
1 | [7 empty] | 1
2 | [7 empty] | 2
3 | [7 empty] | 3
4 | [7 empty] | 4
5 | [7 empty] | 5
6 | [7 empty] | 6
7 | [7 empty] | 7
Justification MFL: Single fatality based on the assumption that there will be not more than 2 people working and only 1 getting afftected. Severity: Level 4, with single fatality as a consequence after taking in to account all the controls in place. Likelihood: This type of event could occur within 5 years period.
EXISTING PREVENTATIVE CONTROLS
EXISTING MITIGATING CONTROLS
Event
Incident during Lifting operation
BOW-TIE EXAMPLE

## Sheet1
Single Fatality Project delay Infrastructure damage Legerslative Reportable incident Financial loss Plant / truck rollover Insurficient risk assessment | Poor planning Sicificient survey report Inclement weather Compaction test not completed Scope of works not adhered to Poor supervision | Single fatality Property damage / Loss Environmental damage / loss Financial loss Project delay | Incorrect equipment Untrained and not VOC'd personnel No risk assessment completed No audits / checks undertaken No loading / unloading procedures implemented No civil works to stablise ground
PEAHR breaches Environmental breaches of state law Acts & regulations Breaches of transport state law regulations Project delay and finicial penalties Chemical spills effecting land /Marine environment Community impact Explosion and uncontrolled release of toxic substances | Not containing chemical spills in to natural course waterways Not following environmental procedure Personnel unaware of PEAHR requirments Personnel not trained spill response Contractor not approved or licenced to transport to carry hazardous materials No spill kits in place Chemical storage container not adequatly bunded | Environmental damage / loss Financial penalties Project delays Community impact Fire & explosion Uncontrolled release of toxic substances Pollution of the environment , land and marine Multiple fatalities | Chemical management procedure not implemented Inadequate training for personnel Not using a registered contractor Hazardous materials being transported without appropreaite licences and approvals Inadequate chemical storage facilities

## Sheet2
Weeli Wolli Creek Newman Mainline 291km Bridge - Earthworks, Siteworks
KPI | Activity/Task (Description) | Hazard/ Aspect | Unplanned/unwanted Event (Issue) | Contributing Factors/Causes Root Causes - Latent Causes - Direct Causes | Maximum Foreseeable Loss (Most plausible worst case scenario - controls not in place) | Severity Level (Based on MFL) | Basis for MFL | Current Controls | Mitigating controls | Impact (Most plausible worst case scenario - with controls in place) | Residual Risk |  |  | New Actions / Further Requirements | Actioned by Who? (Name and Surname) | Actioned By When
Mobilisation | Training | Untrained/Inexperienced Personnel | potential delay to start/ completion of works Damaged reputation | Inadequate training Failure to follow procedures Failure to follow BHP procedures | potential delay to start/completion of works | 2 | • Personnel not inducted (Client, company or legislative inductions not provided); • Inadequate supervision; • Non-compliance with site safety procedures, including PPE; | BHP References 09-003 Induction and Orientation 09-004 Training and Competency 09-008 Site Access & Security 09-013 Mobilisation 09-030 Fitness for Work SPR-HR-GEN-005 BHP Approved Training Providers Downer References DA-HR-PR001 Recruitment and Induction DA-ZH-PR003 Training and Competency Management Downer Health and Safety Management Plan | Registered Training Organisation (RTO) and experienced personnel to conduct company training for all personnel involved in the project Company training matrix implemented and maintained | minor delays to work commencement | 3 | 0.3 | 0.9
Mobilisation | Mobilisation of personnel to site | Unfamiliar travel routes for personnel entering site; Travel to remote locations - reduced services, communications, emergency response. | Personnel not arriving to site when required / expected; | TMP not communicated to new personnel or not TMP in place Personnel not familiar with remote area environment and conditions | delays in commencement of planned works Personal injury Equipment damage | 3 | More than one person travelling in one vehicle Plant / vehicles and equipment not suitable for task Personnel unaware of PEAHR and remote travel requirements | BHP References 09-004 Training and Competency 09-011 Light Vehicles, Buses & Mobile Plant 09-012 Traffic Management Downer References DA-ZH-PR003 Training and Competency Management Downer Traffic Management Plan | Downer Bus to be utilised for all personnel unfamiliar with site or travel routes Journey management protocols for vehicle journeys (journey controller appointed and checks made to verify safe arrival to project) Travel instruction/directions provided to personnel prior to departure (including provision of maps as required); Inspection and maintenance of company light vehicles (minimum weekly inspection for light vehicles)Vehicle and Trailer Weekly Inspection; Alternative driver system to be implemented Downer bus to deliver personnel to site from camp and airport. | personal injury property damage | 10 | 1 | 10
competence | Mobilisation of personnel to site | Speeding other vehicles on the road | Infrastructure property, plant and equipment damage Loss of life, human / fauna Breaching WA Traffic road rules BHP site requirements and legislation | Not diving to road conditions, Not complying to state law road rule , BHP TCP' TMP. Driver affected by drugs & alcohol and fatigue | Multiple fatalities Infrastructure damage Breaches of state law regulations and BHP site requirements Native fauna and cattle loss | 4 | More than one person travelling in one vehicle Plant / vehicles and equipment not suitable for long distance travel Driver complacency | BHP References 09-004 Training and Competency 09-011 Light Vehicles, Buses & Mobile Plant 09-012 Traffic Management 09-049 Guarding, Barricading, Signage and Housekeeping Downer References DA-ZH-PR003 Training and Competency Management Downer Traffic Management Plan | Vehicles transported in where possible alternative driver program implemented Bus transportation utilised for workers not familiar with site Travel packages provided speed monitoring conducted through journey management DETEC training Current Australian drivers licence applicable to vehicle being driven BHP requirements dictates all personnel under 21 years of age not to drive light vehicles and trucks | Single fatality Infrastructure damage Breaches of state law traffic and Mines Act legislation | 10 | 3 | 30
track construction | Utilisation of Plant, SME and Equipment | Incompetent operators | Single Fatality Project delay Infrastructure damage Legislative Reportable incident Financial loss Plant / truck rollover | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No VOC process developed HR Recruitment process inadequate Insufficient risk assessment | Single Fatality Project delay Infrastructure damage Legislative Reportable incident Financial loss Plant / truck rollover collision Insufficient risk assessment | 4 | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No loading / unloading operating procedures implemented Poor training and VOC process in place | BHP References 09-003 Induction and Orientation 09-004 Training & Competency 09-011 Light Vehicles, Buses & Mobile Plant Downer References DA-ZH-PR003 Training and Competency Management DA-HR-PR001 Recruitment and Induction DA-ZH-ST057 Vehicles and Mobile Plant | Trained and competent personnel identified through recruitment and VOC process Scheduled audits and inspections of safety management system | Minor equipment and property damage FAC injury | 10 | 0.3 | 3
environment | Preparation of and working in field conditions | Uneven / unprepared ground | Project delay Infrastructure damage Legislative Reportable incident Financial loss Plant / truck rollover Insufficient risk assessment | Poor planning insufficient geotech & survey report Inclement weather Not preparing ground to comply with load and geotech requirements Scope of works not adhered to Poor supervision | Single fatality Property damage / Loss Environmental damage / loss Financial loss Project delay | 3 | Incorrect equipment Untrained and not VOC'd personnel No risk assessment completed No audits / checks undertaken No loading / unloading procedures implemented No civil works to stabilise ground | BHP References 09-005 Hazard and Risk Management 09-014 Loading & Unloading SPR-IHS-SAF-006 Personal Protective Equipment Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DA-ZH-PR052 Personal Protective Equipment | Correct surveying of area Ground compaction test completed and signed off Correct planning Risk assessments completed Trained and VOC competent personnel Civil works completed to required standard | Infrastructure damage Project delays Financial loss | 10 | 0.3 | 3
environment | Preparation of and working in field conditions | unstable ground | Loss of human life permanent disability Breach of BHP policies and procedures Equipment failure Dropped objects Crane collapse Legislative Reportable incident | Poor planning insufficient survey report on ground conditions Inclement weather Compaction of ground not completed Scope of works not adhered to Poor supervision Inadequate risk assessment | Single fatality Property damage / Loss Environmental damage / loss Financial loss Project delay | 4 | Incorrect equipment No risk assessment completed No audits / checks undertaken No loading / unloading procedures implemented No civil works to stabilise level ground | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management SPR-IHS-SAF-029 Cranage, Lifting & Slinging Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DEDI-ZH-047-CG Cranes and Lifting Equipment | Correct surveying of area Ground compaction test completed and signed off Correct planning Risk assessments completed Trained and VOC competent personnel Civil works completed to required standard | Major Infrastructure damage Project delays Financial loss | 10 | 1 | 10
environment | Adverse weather conditions | Adverse weather conditions | Floods Storm damage Loss of productivity Environmental damage Infrastructure damage Loss of life ( Human & Animals) Community damage / loss | Cyclone & inclement weather preparedness process not implemented Not ceasing works during inclement weather Emergency management process not in place | Multiple fatality Property damage / Loss Environmental damage / loss | 4 | No due diligence process undertaken regarding the Hierarchy of controls of the hazards in the project environment | BHP References S 09-005 Hazard and Risk Management SPR-IHS-SAF-029 Cranage, Lifting & Slinging PR-OHN-SAF-026 Tropical Cyclone Preparedness and Response SPR-PHS-SAFES-001 Port & Rail Cyclone Procedure 09-027 Working in Hot and Cold Downer References DA-ZH-PR028 Zero Harm Risk Management DEDI-ZH-047-CG Cranes and Lifting Equipment DA-ZH-PR093 Working in Extremes of Temperature Downer Cyclone Procedure | Emergency management process implemented Infrastructure, building audits and Q& A process system in place Reliable weather forecasting information source i.e. BOM etc Early warning detection systems implemented through warning network | Single fatality Minor Infrastructure damage | 3 | 1 | 3
environment | Utilisation of Plant, SME and Equipment | Hydrocarbon spill | Environmental breaches of state law Acts & regulations Breaches of transport state law regulations Project delay and financial penalties Chemical spills effecting land /Marine environment Community impact Explosion and uncontrolled release of toxic substances | Not containing chemical spills in to natural course waterways Not following environmental procedure Personnel unaware of PEAHR requirements Personnel not trained spill response Contractor not approved or licenced to transport to carry hazardous materials No spill kits in place Chemical storage container not adequately bunded | Environmental damage / loss Financial penalties Project delays Community impact Fire & explosion Uncontrolled release of toxic substances Pollution of the environment , land and marine Multiple fatalities | 3 | Chemical management procedure not implemented Inadequate training for personnel Not using a registered contractor Hazardous materials being transported without appropriate licences and approvals Inadequate chemical storage facilities | BHP References 09-005 Hazard and Risk Management SPR-IEN-HC-001 WAIO Hydrocarbon and Hazardous Chemicals Management WIN-IEN-HC-001 Major/Minor Spill Response 13-100 Environmental Management Plan Downer References DA-ZH-PR024 Hazardous Chemicals and Dangerous Goods DA-ZH-PR028 Zero Harm Risk Management Downer Environmental Management Plan | Trained personnel of handling of hazardous substances Fatigue management procedure implemented and constantly monitored Emergency response and chemical spill training Client approved Hazardous Storage facilities and transport vehicles Chemical separation procedure compliance Chemical handling tool box training MSDS register, reviewed periodically Competent licenced waste contractors to be utilised | Minor spills |  |  | 0
environment | Dust | Inhalation of dust | Injury / Illness , dust inhalation causing chest infection | No environmental risk assessment completed No personal risk assessment completed Failure to provide PPE to personnel Incorrect PPE Failure to implement dust monitoring / or schedule Open cab to Equipment | Chest infection /Lost time Injury Workers Compensation claim | 3 | No Environmental risk assessment completed prior to starting task Failure to provide PPE to personnel Incorrect PPE Failure to implement dust monitoring / or schedule Open cab to Plant Poor planning Inadequate supervision | BHP References 09-005 Hazard and Risk Management 09-040 Dust and Fibrous Materials 13-100 Environmental Management Plan SPR-IHS-SAF-006 Personal Protective Equipment Downer References DA-ZH-PR028 Zero Harm Risk Management DA-ZH-ST052 Personal Protective Equipment DA-ZH-ST070 Air Quality Management Downer Environmental Management Plan | Environmental risk assessment to be completed prior to starting task Provide correct PPE to personnel Implementation of dust monitoring and schedule Closed cab to be sourced and mobilised to site to replace Correct time allocated to planning , prior to commencing job | Minor dust suppression required | 3 | 1 | 3
environment | Noise | Noise induced hearing loss | Injury / Illness Permanent hearing disability / loss | No environmental risk assessment completed No personal risk assessment completed Failure to provide PPE to personnel Incorrect PPE Failure to implement noise monitoring / or schedule | Chest infection /Lost time Injury Workers Compensation claim |  | No Environmental risk assessment completed prior to starting task Failure to provide PPE to personnel Incorrect PPE Failure to implement dust monitoring / or schedule Poor planning Inadequate supervision | BHP References 09-005 Hazard and Risk Management 09-040 Dust and Fibrous Materials SPR-IHS-SAF-006 Personal Protective Equipment SPR-IHS-SAFHY-009 Occupational Hygiene Exposure Assessment and Control Downer References DA-ZH-PR028 Zero Harm Risk Management DA-ZH-ST052 Personal Protective Equipment | Environmental risk assessment to be completed prior to starting task Provide correct PPE to personnel Implementation of noise monitoring and schedule Closed cab to be sourced and mobilised to site to replace open cabs Correct time allocated to planning , prior to commencing job | Minor hearing loss Community disturbance | 3 | 1 | 3
environment | Hazardous substances | Contact with hazardous substances Storage of hazardous substances | PEAHR breaches Environmental breaches of state law Acts & regulations Chemical spills effecting Marine environment Community impact Chemical injury poisoning / burns Explosion | Not containing chemical spills in to natural course waterways Not following environmental procedure Personnel unaware of PEAHR requirements Personnel not trained spill response Contractor not approved or licenced to transport to use hazardous materials Not complying with MSDS | Environmental damage / loss Fire & explosion Uncontrolled release of toxic substances Pollution of the environment , land and marine Single fatality | 3 | Chemical management procedure not implemented Inadequate training for personnel Not using a registered contractor Hazardous materials being transported without appropriate licences Not complying with MSDS | BHP References 09-010 - Hazardous Materials Management SPR-IEN-HC-001 WAIO Hydrocarbon and Hazardous Chemicals Management WIN-IEN-HC-001 Major/Minor Spill Response 13-100 Environmental Management Plan Downer References DA-ZH-PR024 Hazardous Chemicals and Dangerous Goods DA-ZH-PR054 Hazardous Chemicals and Dangerous Goods Storage Principles and Transportation DA-ZH-PR028 Zero Harm Risk Management Downer Environmental Management Plan | Trained personnel of handling of hazardous substances Fatigue management procedure implemented and constantly monitored Emergency response and chemical spill training Approved Hazardous Storage facilities and transport vehicles MSDS register to be implemented and reviewed periodically | Infrastructure damage Breaches of state law traffic and Mines Act legislation financial penalties Pollution of the environment , land and marine | 10 | 1 | 10
environment | Hazardous substances | Removal and disposal | PEAHR breaches Environmental breaches of state law Acts & regulations Breaches of transport state law regulations Project delay and financial penalties Chemical spills effecting land /Marine environment Community impact Explosion and uncontrolled release of toxic substances | Not containing chemical spills in to natural course waterways Not following environmental procedure Personnel unaware of PEAHR requirements Personnel not trained spill response Contractor not approved or licenced to transport to carry hazardous materials | Environmental damage / loss Financial penalties Project delays Community impact Fire & explosion Uncontrolled release of toxic substances Pollution of the environment , land and marine Multiple fatalities | 3 | Chemical management procedure not implemented Inadequate training for personnel Not using a registered contractor Hazardous materials being transported without appropriate licences and approvals | BHP References 09-010 - Hazardous Materials Management SPR-IEN-HC-001 WAIO Hydrocarbon and Hazardous Chemicals Management WIN-IEN-HC-001 Major/Minor Spill Response 13-100 Environmental Management Plan Downer References DA-ZH-PR024 Hazardous Chemicals and Dangerous Goods DA-ZH-PR054 Hazardous Chemicals and Dangerous Goods Storage Principles and Transportation DA-ZH-PR028 Zero Harm Risk Management Downer Environmental Management Plan | Registered and licenced contractor to be utilised Trained personnel of handling of hazardous substances Fatigue management procedure implemented and constantly monitored Emergency response and chemical spill training Approved Hazardous Storage facilities and transport vehicles | Minor spills | 3 | 0.3 | 0.9
environment | Working in heat, cold, rain | Personnel not acclimatised to environment | Single fatality Heat stroke Heat stress Dehydration Equipment damage | Insufficient fluids intake Working in extreme climatic conditions Extended hours of work Sudden change of environment Peer pressure Failure to acclimatise to conditions No training / information given | Heat stroke | 3 | Insufficient fluids intake Working in extreme climatic conditions Extended hours of work Sudden change of environment Peer pressure Failure to acclimatise to conditions No training / information given | BHP References 09-003 Induction and Orientation 09-004 Training & Competency 09-027 Working in Hot and Cold 09-030 Fitness for Work Downer References DA-HR-PR001 Recruitment and Induction DA-ZH-PR003 Training and Competency Management DA-HR-PR001 Recruitment and Induction DA-ZH-PR093 Working in Extremes of Temperature | Increase fluids intake Working in extreme climatic conditions Reduce working hours of work 12-10 Use buddy system for new starters Acclimatise to conditions slowly Training / information i.e. tool boxes | Minor dehydration | 10 | 1 | 10 | Live document; hazards to be indentified through review | CM PM Safety | TBA
environment | Working in bush environment | Snakes, spiders, bee bites etc | personal injury | First aid courses not available No Native wildlife awareness training New employee to area | Allergic reaction Coma / Shock | 3 | First aid training not available No Native wildlife awareness training New employee to area | BHP References 13-100 Environmental Management Plan Downer References DA-ZH-ST071 Flora and Fauna Management Downer Environmental Management Plan | Native fauna training to all personnel Nationally accredited Senior first aid training for personnel Emergency response plan implemented, tested and reviewed periodically First aid kits in all offices, plant , and LV's Administration information on notice boards | FAC injury | 3 | 0.3 | 0.9
environment | Commuting to and from Camp | Fauna Weather | Infrastructure property, plant and equipment damage Loss of life, human / fauna Breaching WA Traffic road rules BHP site requirements and legislation | Not driving to road conditions, Not complying to state law road rule , BHP TCP' TMP. Driver affected by drugs & alcohol and fatigue | fatality Infrastructure damage Breaches of state law regulations and BHP site requirements Native fauna and cattle loss | 4 | Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | BHP References SPR-OHN-SAF-026 Tropical Cyclone Preparedness and Response SPR-PHS-SAFES-001 Port & Rail Cyclone Procedure 09-027 Working in Hot and Cold Downer References DA-ZH-PR093 Working in Extremes of Temperature Downer Cyclone Procedure | Pre start meetings to communicate pertinent information on predicted weather and durations Personnel to relocate into safe areas Subscription to early warning network Speed monitoring and random testing, Starting times to be assessed to miss identified issue times, e.g. dawn and dusk. Speed limits to enable adequate braking distance | Infrastructure damage personal injury | 3 | 0.3 | 0.9
environment | Cyclones and storms | Equipment and buildings not secured correctly to BHP standards | Infrastructure property, plant and equipment damage Loss of life, human / fauna | Force majeure weather event Standards for buildings in cyclone zones not adhered to | Multiple fatalities Infrastructure damage Native fauna and cattle loss | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | BHP References SPR-OHN-SAF-026 Tropical Cyclone Preparedness and Response SPR-PHS-SAFES-001 Port & Rail Cyclone Procedure Downer References DA-ZH-PR093 Working in Extremes of Temperature Downer Cyclone Procedure | Pre start meetings to communicate pertinent information on predicted weather and durations Personnel to relocate into safe areas Subscription to early warning network | Infrastructure damage | 10 | 0.3 | 3
environment | Sleeper Laying | Embankments/Uneven ground | Infrastructure property, plant and equipment damage injury | Failure to follow TPO Direction Incompetent operator Faulty equipment No Exclusion Zones Incorrect body posture prolonged static postures | Permanent disability Injury plant and equipment damage | 3 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management 09-049 Guarding, Barricading, Signage and Housekeeping SPR-IHS-SAF-006 Personal Protective Equipment Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DA-ZH-PR052 Personal Protective Equipment | Follow TPO Direction and process Trained and competent personnel identified through recruitment process procedure for working on uneven surfaces implemented job rotation implemented work redesign considered buffer paths on formation identified with barricading Correct planning and scheduling Contractors to be inducted to site Plant and equipment to comply with BHP Environmental and site compliance inspection | minor damage | 10 | 1 | 10
environment | Laying of Rail | Embankments/Uneven ground | Infrastructure property, plant and equipment damage injury | Failure to follow Track Access Requirements Incompetent operator Faulty equipment No Exclusion Zones No Spotter | Single Fatality Injury plant and equipment damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management 09-049 Guarding, Barricading, Signage and Housekeeping SPR-IHS-SAF-006 Personal Protective Equipment Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DA-ZH-PR052 Personal Protective Equipment | TPO direction and process Exclusion zones implemented Pre-start checks completed Correct equipment Trained VOC'd personnel High risk licenced operator Risk assessment completed Audits / checks undertaken Loading / unloading procedures implemented | property damage personal injury | 10 | 1 | 10
track construction | Clipping Up of Rail | Manual Handling | Personal injury leading to permanent damage | • Over-exertion (excessive manual lifting force); • Poor posture during lifting/handling; • Muscle fatigue; • Repetitious movement; • Prolonged static postures; • Handling of sharp / hazardous loads; | Personal Injury - Slip, Trip, Fall; Personal Injury - Musculoskeletal injury (Strain/disc injury); Personal Injury - Hand injury (Crush / Laceration). | 4 | Incorrect body posture Isometric muscle movement Inadequate training in manual handling, correct body posture techniques | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management 09-049 Guarding, Barricading, Signage and Housekeeping SPR-IHS-SAF-006 Personal Protective Equipment Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DA-ZH-PR052 Personal Protective Equipment | Trained and competent personnel identified through recruitment process procedure for working on uneven surfaces implemented job rotation implemented work redesign considered buffer paths on formation identified with barricading Correct planning and scheduling Contractors to be inducted to site Plant and equipment to comply with BHP Environmental and site compliance inspection |  | 10 | 1 | 10
track construction | Rail Stored Energy | Manual/Mechanical Handling | Personal injury leading to permanent damage | • In adequate education and awareness of rail/steel movement in changing temperature conditions when rail is unrestrained(clipper up) ; • In correct handing conditions with machinery; • incorrect unclipping/clipping up procedure | Personal Injury - leg/torso injury (Crush / Laceration). | 4 | Incorrect body posture Isometric muscle movement Inadequate training in manual handling, correct body posture techniques | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management 09-049 Guarding, Barricading, Signage and Housekeeping SPR-IHS-SAF-006 Personal Protective Equipment Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DA-ZH-PR052 Personal Protective Equipment | Experienced, trained and competent personnel identified through recruitment process procedure for clipping unclipping, cutting rail work redesign considered control of worksite to be maintained Correct planning and communication of plan to all work groups Correct Plant and equipment to carry out rail threading and movement |  | 10 | 1 | 10
environment | Tamping and Regulating | Hydrocarbon spill | environmental event | Contact with hazardous substances. Lack of / Out of Date MSDS's Inadequate Labelling of Substance containers Poor Decanting practices Uncontrolled Ignition sources Storage of incompatible substances Lack of Risk Assessment for Hazardous Substances; Spillage / Leakage of substances. Poor Decanting practices; Poor disposal of substances; Fail to identify less hazardous / alternative substances. | Personal Injury - Inhalation, Ingestion, Skin Contact; environmental event - contamination of area | 3 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | BHP References 09-005 Hazard and Risk Management SPR-IEN-HC-001 WAIO Hydrocarbon and Hazardous Chemicals Management WIN-IEN-HC-001 Major/Minor Spill Response 13-100 Environmental Management Plan Downer References DA-ZH-PR024 Hazardous Chemicals and Dangerous Goods DA-ZH-PR028 Zero Harm Risk Management Downer Environmental Management Plan | Registered and licenced contractor to be utilised Trained personnel of handling of hazardous substances Fatigue management procedure implemented and constantly monitored Emergency response and chemical spill training Approved Hazardous Storage facilities and transport vehicles | Environmental damage | 10 | 1 | 10
environment | Earthworks/ Mobile Equipment/excavations | Uneven Ground | • Truck/Mobile Plant roll over • Property damage | • No risk assessment completed on ground conditions prior to loading/unloading • Insufficient surveying of area • Inclement weather • Poor planning | Single Fatalities Infrastructure Damage Project Delay Reputation Damage | 4 | Single fatality /permanent body impairment to operator of truck/mobile plant | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management 09-011 Light Vehicles, Buses & Mobile Plant 09-39 Bulk Earthworks and Civil Works Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DA-ZH-ST057 Vehicles and Mobile Plant | • Designated Loading and loading area to be established and resources available to establish • Compaction testing to be completed during establishing of designated loading/unloading area | Infrastructure Damage | 10 | 1 | 10
environment | Earthworks/ Mobile Equipment/excavations | Inclement weather | • Water damage to critical infrastructure limiting production and access/egress to site • Site closure from cyclone | • Weather conditions - Cyclones/Hail/Rain • Poor work area set up - drainage • Crib huts not cyclone rated | Multiple Fatalities Infrastructure Damage Environment Damage | 5 | Sever Cyclonic conditions have the potential to cause mass infrastructure damage and multiple fatalities | BHP References SPR-OHN-SAF-026 Tropical Cyclone Preparedness and Response SPR-PHS-SAFES-001 Port & Rail Cyclone Procedure 09-027 Working in Hot and Cold Downer References DA-ZH-PR093 Working in Extremes of Temperature Downer Cyclone Procedure | • Cyclone Procedure in place and resources to communicate and implement available • Emergency Preparedness Plan in place and resources to communicate and implement available | Infrastructure Damage Environment Damage | 3 | 0.3 | 0.9
equiipment | Tamping and Regulating | Tamper/Regulator/Mobile Plant/Vehicle/Pedestrian interface | Infrastructure property, plant and equipment damage injury Loss of life | Failure to provide pre start information on interactions with other contractors Failure to implement Track Access Procedures Failure to follow TPO directions | Single Fatality Injury plant and equipment damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | BHP References 09-003 Induction and Orientation 09-004 Training & Competency 09-005 Hazard and Risk Management 09-011 Light Vehicles, Buses & Mobile Plant 09-012 Traffic Management 09-036 Rail Safety 09-048 Communication and Consultation Downer References DA-ZH-PR003 Training and Competency Management DA-HR-PR001 Recruitment and Induction DA-ZH-PR013 Communication and Consultation DA-ZH-ST057 Vehicles and Mobile Plant DA-ZH-PR135 Traffic Management DA-ZH-PR107 Plant and Pedestrian Interface DI-ZH-PO003 Rail Safety Policy | TPO direction followed Track Access procedure in place WP4 Form implemented and adhered to TMP communicated, implemented and constantly reviewed Contractor meeting schedule developed and implemented Positive communications procedure developed and training conducted Pre- planning prior to commencing contract | property damage personal injury | 10 | 1 | 10
equipment | Equipment compliance and mobilisation | Light Vehicles, Fixed Plant & Mobile Plant not meeting BHP Standards | Potential delay to start / completion of works; Damaged reputation | No pre- mobilisation checks prior to mobilisation Client documentation not accessed by contractor No asset maintenance schedule in place Procedures not followed Road traffic hazards i.e. overhead services, route restrictions, other vehicles; Load restraint | Potential delay to start/ completion of works | 2 | No due diligence process undertaken regarding equipment mobilisation and project requirements | BHP References 09-011 Light Vehicles, Buses & Mobile Plant 09-037 Pressurized Equipment 09-060 Light Vehicle Rollover Protection Requirements SPR-IHS-000-001 Light and Road Going Vehicle Use SPR-IHS-SAF-027 WAIO Requirements for Portable/Mobile Lighting Plants, Electrical Generators, Welding Machines, Electrical Distribution Boards, Compressors, Water Pumps and Fuel Trailers SPR-IHS-SAF-098 WA Iron Ore Requirements for Light Vehicles and Surface Mobile Equipment Downer References DA-ZH-PR028 Zero Harm Risk Management DA-ZH-PR057 Vehicles and Mobile Plant | Asset management plan implemented Vehicle compliance process implemented and adhered to All personnel involved in loading / unloading are wearing appropriate PPE Discuss unloading areas with site supervisor prior to arrival; Site specific hazards identified by personnel on site. | minor delays to work commencement | 3 | 0.3 | 0.9
equipment | Mobilisation to site | Non compliant light / heavy vehicles | Infrastructure property, plant and equipment damage Not complying with WA Traffic road rules, BHP site requirements and legislation | No pre- mobilisation checks prior to mobilisation Client documentation not accessed by contractor No asset maintenance schedule in place Procedures not followed Road traffic hazards i.e. overhead services, route restrictions, other vehicles; Load restraint | property damage loss of reputation | 2 | Plant / vehicles and equipment not suitable for task Company's assets not maintained | BHP References 09-011 Light Vehicles, Buses & Mobile Plant 09-060 Light Vehicle Rollover Protection Requirements SPR-IHS-000-001 Light and Road Going Vehicle Use SPR-IHS-SAF-098 WA Iron Ore Requirements for Light Vehicles and Surface Mobile Equipment Downer References DA-ZH-PR028 Zero Harm Risk Management DA-ZH-PR057 Vehicles and Mobile Plant | Company to ensure mobilisation plan is in place and complied with prior to commencement of works Recruitment and planning personnel trained and competent Document control process in place and maintained | property damage | 3 | 1 | 3
equipment | Mobilisation of plant / equipment to site | Hydrocarbon spill | PEAHR breaches Environmental breaches of state law Acts & regulations Breaches of transport state law regulations Project delay and financial penalties Chemical spills effecting land /Marine environment Community impact Explosion and uncontrolled release of toxic substances | Not containing chemical spills in to natural course waterways Not following environmental procedure Personnel unaware of PEAHR requirements Personnel not trained spill response Contractor not approved or licenced to transport to carry hazardous materials | Environmental damage / loss Financial penalties Project delays Community impact Fire & explosion Uncontrolled release of toxic substances Pollution of the environment , land and marine Multiple fatalities | 4 | Chemical management procedure not implemented Inadequate training for personnel Not using a registered contractor Hazardous materials being transported without appropriate licences and approvals | BHP References 09-010 - Hazardous Materials Management SPR-IEN-HC-001 WAIO Hydrocarbon and Hazardous Chemicals Management WIN-IEN-HC-001 Major/Minor Spill Response 13-100 Environmental Management Plan Downer References DA-ZH-PR024 Hazardous Chemicals and Dangerous Goods DA-ZH-PR054 Hazardous Chemicals and Dangerous Goods Storage Principles and Transportation DA-ZH-PR028 Zero Harm Risk Management Downer Environmental Management Plan | Trained personnel of handling of hazardous substances Fatigue management procedure implemented and constantly monitored Emergency response and chemical spill training Client approved Hazardous Storage facilities and transport vehicles | Single fatalities and major Infrastructure damage Breaches of state law traffic and Mines Act legislation financial penalties Pollution of the environment , land and marine | 3 | 1 | 3
equipment | Unloading / Loading | Loose / unsecured loads | Loss of human life Environmental loss, damage and breach Infrastructure damage Community impact Breach of the department of transport act & legislation Financial penalties Project delays | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No loading / unloading procedures implemented | Personal injury Property damage / Loss Environmental damage / loss Financial loss Project delay | 3 | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No loading / unloading procedures implemented | BHP References 09-014 Loading and Unloading 09-005 Hazard and Risk Management Downer References DA-ZH-PR028 Zero Harm Risk Management | Trained and competent personnel identified through recruitment process Correct planning and scheduling Contractors to be inducted to site Plant and equipment to comply with BHP Environmental and site compliance inspection TOA/TWA | Infrastructure damage Breaches of state law traffic and Mines Act legislation Project delays Financial loss | 3 | 0.3 | 0.9
equipment | Unloading / Loading | Unsafe Loading and unloading | Personal injury Environmental loss, damage and breach Infrastructure damage Community impact Breach of the department of transport act & legislation Financial penalties Project delays | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No loading / unloading procedures implemented | Personal injury Property damage / Loss Environmental damage / loss Financial loss Project delay | 4 | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No loading / unloading procedures implemented | BHP References 09-005 Hazard and Risk Management 09-011 Light Vehicles, Buses & Mobile Plant 09-014 Loading & Unloading Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DA-ZH-PR057 Vehicles and Mobile Plant | Trained and competent personnel identified through recruitment process Correct planning and scheduling Contractors to be inducted to site Plant and equipment to comply with BHP Environmental and site compliance inspection TOA/TWA | Infrastructure damage Breaches of state law traffic and Mines Act legislation Project delays Financial loss | 10 | 0.3 | 3
equipment | Crane Operations | Non compliant equipment | Loss of human life permanent disability Breach of BHP policies and procedures Equipment failure Dropped objects | Tag & testing and inspections not completed by competent persons Lifting certifications not submitted State law Statutory check not undertaken | Loss of human life permanent disability Breach of BHP policies and procedures Financial loss Company's loss of reputation and future contracts | 4 | Lifting and rigging gear not compliant Daily gear check not undertaken Poor training and absent VOC process HR recruitment process inadequate | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management SPR-IHS-SAF-024 Isolation and Permit to Work- Isolation, Lockout and Tagging SPR-IHS-SAF-029 Cranage, Lifting & Slinging Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DEDI-ZH-047-CG Cranes and Lifting Equipment | Lifting and rigging register developed compliant to site requirements Daily gear check undertaken Training and VOC process developed, implemented and communicated to all personnel HR recruitment process developed & reviewed periodically Lessons learnt process developed, implemented and timely actioned Health & safety management system to be reviewed periodically | MTI Minor Infrastructure damage Minimum financial loss | 10 | 1 | 10
equipment | Crane Operations | Lifting gear failure | Loss of human life Environmental loss, damage and breach Infrastructure damage Community impact Breach of the department of transport & ORS act & legislation | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No lifting procedures implemented poor planning | Multiple fatality Property damage / Loss Environmental damage / loss Financial loss Project delay Financial penalties Project delays | 4 | No pre-start checks completed Untrained personnel No risk assessment completed No audits / checks undertaken No rigging or operating procedures implemented No training and VOC process in place | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management SPR-IHS-SAF-024 Isolation and Permit to Work- Isolation, Lockout and Tagging SPR-IHS-SAF-029 Cranage, Lifting & Slinging Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DEDI-ZH-047-CG Cranes and Lifting Equipment | Exclusion zones implemented Lifting and rigging register developed compliant to site requirements Daily gear check undertaken Training and VOC process developed, implemented and communicated to all personnel High risk activities controlled through audit and checklist system TWA/TOA | Infrastructure damage Breaches of state law traffic and Mines Act legislation financial penalties | 3 | 1 | 3
equipment | Crane Operations | Mobile Plant/Vehicle/Pedestrian interface | Pedestrians hit by plant & equipment Loss of human life Project delays Compensation claim Legislative enquiry | Working without correct permits Inadequate TMP Poor communications No Training or VOC process in place Poor or no planning undertaken Unsure of work scope and limitations of boundaries No Track Protection | Pedestrians hit by plant & equipment Loss of human life Project delays Compensation claim Legislative enquiry Damage in infrastructure | 4 | Incorrect equipment and permits not in place Untrained and not VOC'd personnel No risk assessment completed No audits / checks undertaken Prior planning not undertaken No risk assessment undertaken Poor or no supervision | BHP References 09-004 Training & Competency 09-005 Hazard and Risk Management 09-011 Light Vehicles, Buses & Mobile Plant 09-012 Traffic Management 09-048 Communication and Consultation Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR013 Communication and Consultation DA-ZH-ST057 Vehicles and Mobile Plant DA-ZH-PR135 Traffic Management DA-ZH-PR107 Plant and Pedestrian Interface Downer Traffic Management Plan | Exclusion Zones TMP communicated, implemented and constantly reviewed Contractor meeting schedule developed and implemented Positive communications procedure developed and training conducted Pre- planning prior to commencing contract TOA/TWA | FAC injury Minor plant damage | 10 | 1 | 10
equipment | Forklift Operations | Mobile Plant/Vehicle/Pedestrian interface | Pedestrians hit by plant & equipment Loss of human life | Working without correct permits Inadequate TMP Poor communications No Training or VOC process in place Poor or no planning undertaken Unsure of work scope and limitations of boundaries | Pedestrians hit by plant & equipment Loss of human life Project delays Compensation claim Legislative enquiry | 3 | Incorrect equipment and permits not in place Untrained and not VOC'd personnel No risk assessment completed No audits / checks undertaken Prior planning not undertaken No risk assessment undertaken Poor or no supervision | BHP References 09-003 Induction and Orientation 09-004 Training & Competency 09-005 Hazard and Risk Management 09-011 Light Vehicles, Buses & Mobile Plant 09-012 Traffic Management 09-048 Communication and Consultation Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR022 Visitor and Contractor Management DA-HR-PR001 Recruitment and Induction DA-ZH-PR013 Communication and Consultation DA-ZH-ST057 Vehicles and Mobile Plant DA-ZH-PR135 Traffic Management DA-ZH-PR107 Plant and Pedestrian Interface Downer Traffic Management Plan | Exclusion zones implemented TMP communicated, implemented and constantly reviewed Contractor meeting schedule developed and implemented Positive communications procedure developed and training conducted Pre- planning prior to commencing contract | FAC injury Minor plant damage | 10 | 1 | 10
equipment | Hand and power tools | Faulty / damaged tools | Loss of human life permanent disability Breach of BHP policies and procedures Equipment failure Dropped objects | Tag & testing not completed by competent persons Daily prestart checks not completed High risk work conducted out of service equipment | permanent disability Breach of BHP policies and procedures Financial loss | 3 | Tag & testing not completed by competent persons Daily prestart checks not completed High risk work conducted out of service equipment | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management 09-017 Power and Hand Tools SPR-IHS-SAF-024 Isolation and Permit to Work- Isolation, Lockout and Tagging Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DA-ZH-ST098 Fixed Plant and Powered Hand Tools | Compliance register schedule implemented Competent persons identified to tag & test equipment Daily pre start checks Training and VOC competencies on Power tools, for all operators of power equipment Correct PPE | Minor FAC | 10 | 1 | 10
equipment | Sleeper Laying | Rail Mounted Mobile Plant/Mobile Plant/Vehicle/Pedestrian interface | Infrastructure property, plant and equipment damage injury Loss of life | No Exclusion Zones Failure to follow Track Access Process Failure to Follow TPO directions Failure to follow supervisor instruction | Single Fatality Injury plant and equipment damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | BHP References 09-003 Induction and Orientation 09-004 Training & Competency 09-005 Hazard and Risk Management 09-011 Light Vehicles, Buses & Mobile Plant 09-012 Traffic Management 09-036 Rail Safety 09-048 Communication and Consultation Downer References DA-ZH-PR003 Training and Competency Management DA-HR-PR001 Recruitment and Induction DA-ZH-PR013 Communication and Consultation DA-ZH-ST057 Vehicles and Mobile Plant DA-ZH-PR135 Traffic Management DA-ZH-PR107 Plant and Pedestrian Interface DI-ZH-PO003 Rail Safety Policy Downer Traffic Management Plan | Exclusion Zones TPO Directions implemented TMP communicated, implemented and constantly reviewed Contractor meeting schedule developed and implemented Positive communications procedure developed and training conducted Pre- planning prior to commencing contract | Minor injury infrastructure damage | 10 | 1 | 10
equipment | Sleeper Laying | Faulty Mobile Plant/Vehicles | Infrastructure property, plant and equipment damage injury, loss of life | Failure to follow Track Access Authority requirements Incompetent operator Faulty equipment No Exclusion Zones No Spotter | Single Fatality Injury plant and equipment damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | BHP References 09-004 Training & Competency 09-005 Hazard and Risk Management 09-011 Light Vehicles, Buses & Mobile Plant SPR-IHS-SAF-024 Isolation and Permit to Work- Isolation, Lockout and Tagging Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-ST057 Vehicles and Mobile Plant | TPO Direction and process Usage of correct parts and equipment maintenance schedule adhered to Training or VOC process in place Asset maintenance schedule developed Only qualified / trained personnel to be operate / Mainian plant & equipment | Plant and property damage personal injury | 10 | 1 | 10
equipment | Laying of Rail | Rail Mounted Mobile Plant/Mobile Plant/Vehicle/Pedestrian interface | Infrastructure property, plant and equipment damage injury Loss of life | Failure to provide pre start information on interactions with other contractors Failure to implement Track Access Procedures Failure to follow TPO directions Uncontrolled energy | Single Fatality Injury plant and equipment damage | 5 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | BHP References 09-003 Induction and Orientation 09-004 Training & Competency 09-005 Hazard and Risk Management 09-011 Light Vehicles, Buses & Mobile Plant 09-012 Traffic Management 09-036 Rail Safety 09-048 Communication and Consultation Downer References DA-ZH-PR003 Training and Competency Management DA-HR-PR001 Recruitment and Induction DA-ZH-PR013 Communication and Consultation DA-ZH-ST057 Vehicles and Mobile Plant DA-ZH-PR135 Traffic Management DA-ZH-PR107 Plant and Pedestrian Interface DI-ZH-PO003 Rail Safety Policy Downer Traffic Management Plan | Exclusion Zones TPO Directions implemented TMP communicated, implemented and constantly reviewed WP4 form Implemented Contractor meeting schedule developed and implemented Positive communications procedure developed and training conducted Pre- planning prior to commencing contract | personal injury property damage | 10 | 1 | 10
equipment | Laying of Rail | Faulty Rail Mounted Mobile Plant & Mobile Plant | Infrastructure property, plant and equipment damage injury | Failure to conduct pre start Scheduled maintenance not conducted | Equipment Damage Personal Injury | 4 | Failure to correctly assess machine conditions and adhere to procedure Failure to provide adequate training Poor planning Inadequate supervision | BHP References 09-004 Training & Competency 09-005 Hazard and Risk Management 09-011 Light Vehicles, Buses & Mobile Plant SPR-IHS-SAF-024 Isolation and Permit to Work- Isolation, Lockout and Tagging Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-ST057 Vehicles and Mobile Plant | Usage of correct parts and equipment maintenance schedule adhered to Training or VOC process in place Asset maintenance schedule developed Only qualified / trained personnel to be operate / Maintain plant & equipment Spotters | Minor injury infrastructure damage | 10 | 1 | 10
equipment | Welding of Rail | Rail Mounted Mobile Plant/Mobile Plant/Vehicle/Pedestrian interface | Infrastructure property, plant and equipment damage Fatality Bush fire | No Exclusion Zones Failure to follow Track Access Process Failure to Follow TPO directions Failure to follow supervisor instruction No Hot works preparation | Fatality equipment damage reputational loss | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to understand and sign onto WP4 Form Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | BHP References 09-003 Induction and Orientation 09-004 Training & Competency 09-005 Hazard and Risk Management 09-011 Light Vehicles, Buses & Mobile Plant 09-012 Traffic Management 09-036 Rail Safety 09-048 Communication and Consultation Downer References DA-ZH-PR003 Training and Competency Management DA-HR-PR001 Recruitment and Induction DA-ZH-PR013 Communication and Consultation DA-ZH-ST057 Vehicles and Mobile Plant DA-ZH-PR135 Traffic Management DA-ZH-PR107 Plant and Pedestrian Interface DI-ZH-PO003 Rail Safety Policy | Exclusion zones in place TPO direction followed Track Access procedure in place WP4 Form implemented and adhered to TMP communicated, implemented and constantly reviewed Contractor meeting schedule developed and implemented Positive communications procedure developed and training conducted Pre- planning prior to commencing contract Hotworks Training and Control Monitor weather broadcasts and fire bans | personal injury equipment damage | 10 | 1 | 10
equipment | Welding of Rail | Faulty Rail Mounted Mobile Plant & Mobile Plant | Infrastructure property, plant and equipment damage injury | Faulty equipment Excessive risk tolerance poor environmental conditions inadequate Supervision | Infrastructure damage Reputational loss Commercial loss | 4 | Failure to comply with procedure Failure to conduct pre starts and machine maintenance Failure to provide adequate supervision | BHP References 09-004 Training & Competency 09-005 Hazard and Risk Management 09-011 Light Vehicles, Buses & Mobile Plant SPR-IHS-SAF-024 Isolation and Permit to Work- Isolation, Lockout and Tagging Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-ST057 Vehicles and Mobile Plant | Usage of correct parts and equipment maintenance schedule adhered to Training or VOC process in place Asset maintenance schedule developed Only qualified / trained personnel to be operate / Mainian plant & equipment |  | 10 | 1 | 10
equipment | Welding of Rail | Flames, Sparks from Welding, Cutting and Grinding | Personal injury bushfire Infrastructure damage | Inadequate training failure to follow process Incorrect PPE failure to implement exclusion zones no hot works training | Eye Injury Hand Injury Burns Foreign body lodgement | 4 | Inadequate training and VOC< ATO process Failure to follow procedure Inadequate PPE inadequate supervision | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management 09-028 Manual Handling 09-049 Guarding, Barricading, Signage and Housekeeping SPR - IHS-SAF006-Personal Protective Equipment (PPE) SPR - IHS-SAF-034-Hot Work Permit SPR - IHS-SAF-071-Hot Work Overview Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DA-ZH-ST041 Hot Work DA-ZH-PR052 Personal Protective Equipment DA-ZH-PR085 Manual Handling and Ergonomics | Exclusion zone implemented around work area. Screens/Barriers erected Tested and tagged equipment, Welding screens utilised where possible; Provision of emergency equipment, including fire extinguishers and first aid kits; Restraint devices for cords/leads; Gas bottles restrained in an upright position by chains; Gas bottles transported in an upright position by suitable trolleys or other mechanical aids; Provision of appropriate storage facilities for gasses (e.g. segregation from non-compatible substances); Monitor local fire bans ahead of planned tasks | personal injury | 10 | 1 | 10
equipment | Ballasting | Ballast Train/Mobile Plant/Vehicle/Pedestrian interface | Infrastructure property, plant and equipment damage injury Loss of life | Failure to provide pre start information on interactions with other contractors Failure to implement Track Access Procedures Failure to follow TPO directions | Single Fatality Injury plant and equipment damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | BHP References 09-003 Induction and Orientation 09-004 Training & Competency 09-005 Hazard and Risk Management 09-011 Light Vehicles, Buses & Mobile Plant 09-012 Traffic Management 09-036 Rail Safety 09-048 Communication and Consultation Downer References DA-ZH-PR003 Training and Competency Management DA-HR-PR001 Recruitment and Induction DA-ZH-PR013 Communication and Consultation DA-ZH-ST057 Vehicles and Mobile Plant DA-ZH-PR135 Traffic Management DA-ZH-PR107 Plant and Pedestrian Interface DI-ZH-PO003 Rail Safety Policy | TPO direction followed Track Access procedure in place WP4 Form implemented and adhered to TMP communicated, implemented and constantly reviewed Contractor meeting schedule developed and implemented Positive communications procedure developed and training conducted Pre- planning prior to commencing contract Barricading Exclusion Zones | personal injury property damage | 10 | 1 | 10
equipment | Ballasting | Faulty Ballast Train & Mobile Plant | Infrastructure property, plant and equipment damage injury | Faulty equipment Excessive risk tolerance poor environmental conditions inadequate Supervision | Infrastructure damage Reputational loss Commercial loss | 3 | Failure to comply with procedure Failure to conduct pre starts and machine maintenance Failure to provide adequate supervision | BHP References 09-004 Training & Competency 09-005 Hazard and Risk Management 09-011 Light Vehicles, Buses & Mobile Plant SPR-IHS-SAF-024 Isolation and Permit to Work- Isolation, Lockout and Tagging Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-ST057 Vehicles and Mobile Plant | Usage of correct parts and equipment maintenance schedule adhered to Training or VOC process in place Asset maintenance schedule developed Only qualified / trained personnel to be operate / Maintain plant & equipment Exclusion zones | property damage | 10 | 1 | 10
equipment | Tamping and Regulating | Faulty Tamper/Regulator/Mobile Plant | Infrastructure property, plant and equipment damage injury | Faulty equipment Excessive risk tolerance poor environmental conditions inadequate Supervision bystanders | Infrastructure damage Reputational loss Commercial loss | 4 | Failure to comply with procedure Failure to conduct pre starts and machine maintenance Failure to provide adequate supervision | BHP References 09-004 Training & Competency 09-005 Hazard and Risk Management 09-011 Light Vehicles, Buses & Mobile Plant SPR-IHS-SAF-024 Isolation and Permit to Work- Isolation, Lockout and Tagging Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-ST057 Vehicles and Mobile Plant | Usage of correct parts and equipment maintenance schedule adhered to Training or VOC process in place Asset maintenance schedule developed Only qualified / trained personnel to be operate / Maintain plant & equipment Statutory inspections completed as required |  | 10 | 1 | 10
equipment | Earthworks/ Mobile Equipment/excavations | Non compliant equipment | • Non compliant earth works mobile equipment • Unroad worthy/operatable earth works mobile equipment • Wrong piece of equipment for task | • Unaware of BHP compliance requirements • Unaware of Western Australian compliance requirements • Poor project planning | Multiple Fatalities Breach of Regulations Infrastructure Damage | 5 | Operators can put not only themselves in an unsafe position but also any other personnel working in the immediate area | BHP References 09-003 Induction and Orientation 09-004 Training & Competency 09-011 Light Vehicles, Buses & Mobile Plant 09-39 Bulk Earthworks and Civil Works Downer References DA-ZH-PR003 Training and Competency Management DA-HR-PR001 Recruitment and Induction DA-ZH-ST057 Vehicles and Mobile Plant | • Project Schedule in place and resources to complete available • Mobile Plant Compliance checklists and resources available to complete checklists | Breach of Regulations Infrastructure Damage | 10 | 0.3 | 3
equipment | Earthworks/ Mobile Equipment/excavations | Mobile Plant/Vehicle/Pedestrian interface | • Unauthorised access to work area • Motor Vehicle/Mobile Plant/Pedestrian related injury • Untrained operators • Uncontrolled Mobile Plant/Vehicle/Pedestrian interface - No separation | • Drivers/Operators/Pedestrians not complying with Company Traffic Management and Site Traffic Control Plans • Insufficient/no road signage • Call up signage when entering restricted areas not adhered to | Multiple Fatalities Infrastructure Damage Project Delay Reputation Damage | 4 | Drivers/Operators can put not only themselves in an unsafe position but also any other personnel working in the immediate vicinity | BHP References 09-003 Induction and Orientation 09-004 Training & Competency 09-005 Hazard and Risk Management 09-011 Light Vehicles, Buses & Mobile Plant 09-012 Traffic Management 09-048 Communication and Consultation Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR022 Visitor and Contractor Management DA-HR-PR001 Recruitment and Induction DA-ZH-PR013 Communication and Consultation DA-ZH-ST057 Vehicles and Mobile Plant DA-ZH-PR135 Traffic Management DA-ZH-PR107 Plant and Pedestrian Interface Downer Traffic Management Plan | • Project Site Induction in place and resources available to communicate • Site Traffic Management Plan and Traffic Control Plan in place and resources available to communicate to all personnel | Infrastructure/Property Damage Project Delay Reputation Damage | 10 | 3 | 30
equipment | Formwork installation | hand tools work design awkward body position to complete work | • Personnel injury - First Aid Case, Medical Treated Injury • Personnel Injury - Lost Time Injury if no first aid/medical treatment | • awkward body position •extensive manual handling • PPE not available/appropriate for task • Personnel not trained in PPE correct use | Personnel Injury Project Delay | 3 |  |  | PPE - Hexarmour gloves job rotation manual handing training safe spine program correct tool for job | Personal Injury Project Delay | 10 | 3 | 30
equipment | agitator spills on completion | hazardous material shute malfunction incompetent operator suspended loads | concrete spills/ splashes Burns from incorrect handling | incompetent operator Faulty equipment No Exclusion Zones No Spotter | Personnel Injury Equipment damage Environmental event Project Delay | 3 |  |  | delivery driver to operate machine - no unauthorised access to equipment Bunded area for cleaning shute - heavy duty plastic barrier shute operated by competent operator exclusion zone from bund spoil removed by mechanical means | personal Injury Project Delay environmental event | 10 | 3 | 30
people | Selection of Personnel / Recruitment | Personnel not inducted (Client, company or legislative inductions not provided); Inadequate supervision; Non-compliance with site safety procedures, including PPE; | Potential delay to start / completion of works; | Inadequate training Failure to follow procedures Failure to follow BHP procedures | Potential delay to start / completion of works. | 2 | Employee / personnel are unfamiliar of working conditions and working remote areas | BHP References 09-004 Training & Competency 09-005 Hazard and Risk Management 09-100 Health and Safety Management Plan Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management Downer Health and Safety Management Plan | Project inductions Downer / General Construction induction); Induction process to include visual verification of driver's license, Construction Induction and other relevant qualifications; PPE issued to all personnel as required. Minimum site requirements include: - Safety footwear; - Safety glasses; - Hi-Visibility vest/shirt; - Long sleeved shirt; - Long pants; - Hard hat; - Gloves | minor delays to work commencement | 3 | 0.3 | 0.9
people | Mobilisation of personnel to site | • Personnel not inducted (Client, company or legislative inductions not provided); • Inadequate supervision; • Non-compliance with site safety procedures, including PPE; Fatigue | personal injury damaged reputation | Inadequate training Failure to follow procedures Failure to follow BHP procedures | Personal injury Potential delay to start / completion of works. | 2 | Employee / personnel are unfamiliar of working conditions and working remote areas | BHP References 09-004 Training and Competency 09-008 Site Access & Security 09-011 Light Vehicles, Buses & Mobile Plant 09-030 Fitness for Work SPR-HR-GEN-005 BHP Approved Training Providers SPR-IHS-SAF-098 WA Iron Ore Requirements for Light Vehicles and Surface Mobile Equipment Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR057 Vehicles and Mobile Plant | New employee passport program completed for all new employees, including inductions and safety training programs, competency and authorisations Downer, project and client inductions; Review and sign off of associated Safe Work Method Statements (SWMS) Suitable training for personnel engaged on site. | minor delays to work commencement | 3 | 1 | 3
people | Crane Operations | Incompetent operators | Single Fatality Project delay Infrastructure damage Legislative Reportable incident Financial loss Plant / truck rollover Load failure / dropped objects | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No VOC process developed HR Recruitment process inadequate Insufficient risk assessment | Single Fatality Project delay Infrastructure damage Legislative Reportable incident Financial loss Crane collapse insufficient risk assessment | 5 | No pre-start checks completed Incorrect equipment used Untrained personnel No risk assessment completed No audits / checks undertaken No rigging or operating procedures implemented No training and VOC process in place | BHP References 09-003 Induction and Orientation 09-004 Training & Competency SPR-IHS-SAF-029 Cranage, Lifting & Slinging Downer References DA-ZH-PR003 Training and Competency Management DA-HR-PR001 Recruitment and Induction DA-ZH-ST057 Vehicles and Mobile Plant DEDI-ZH-047-CG Cranes and Lifting Equipment | Trained and competent personnel identified through recruitment and VOC process Scheduled audits and inspections of safety management system | Minor equipment and property damage FAC injury | 10 | 0.3 | 3
people | Forklift Operations | Incompetent Operators | Single Fatality Project delay Infrastructure damage Legislative Reportable incident Financial loss Plant / truck rollover | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No VOC process developed HR Recruitment process inadequate Insufficient risk assessment | Single Fatality Project delay Infrastructure damage Legislative Reportable incident Financial loss Plant / truck rollover collision Insufficient risk assessment | 4 | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No loading / unloading operating procedures implemented Poor training and VOC process in place | BHP References 09-003 Induction and Orientation 09-004 Training & Competency 09-011 Light Vehicles, Buses & Mobile Plant Downer References DA-ZH-PR003 Training and Competency Management DA-HR-PR001 Recruitment and Induction DA-ZH-ST057 Vehicles and Mobile Plant | Trained and competent personnel identified through recruitment and VOC process Scheduled audits and inspections of safety management system | Minor equipment and property damage FAC injury | 10 | 1 | 10
people | Worker fatigue | Workers fatigued - long travel and working days | Loss of native fauna Loss of human life Vehicle and infrastructure damage falling asleep whilst in control | Falling asleep whilst in control Being under the influence of drugs and alcohol No fatigue management, Journey plan in place | Fatality Native fauna and cattle loss infrastructure damage | 3 | Fatigue management process not implemented or adhered to | BHP References 09-030 Fitness for Work SPR-IHS-SAFOH-004 Iron Ore Fatigue Management Plan 09-100 Health and Safety Management Plan Downer References Downer Health and Safety Management Plan | Fatigue management process implemented Fatigue assessment process implemented D and A testing implemented All personnel to be trained in fatigue identification | Personal injury Environmental loss Infrastructure damage | 3 | 1 | 3
people | Alcohol and other drugs | Impaired judgement and fitness for work | Loss of life Addiction Relationship breakdown Depression Violence Property damage Imprisonment Loss of livelihood | Loss of employment and income Relationship breakdown FIFO worker Isolation Loss of family members and friends | Single fatality Property damage | 4 | Loss of employment and income Relationship breakdown FIFO worker away from home Isolation Loss of family members and friends Peer pressure Wet mess failure to identify harmful limit of alcohol to personnel Peer pressure No BAC testing | BHP References 09-001 Contractor Selection & Engagement 09-003 Induction and Orientation 09-008 Site Access & Security 09-030 Fitness for Work 09-031 Medical, Injury and Illness Management SPR-IHS-SAF-073 WAIO Drug and Alcohol Management SPR-IHS-SAFOH-004 Iron Ore Fatigue Management Plan 09-100 Health and Safety Management Plan Downer References DI-ZH-PO002 Health and Safety Policy DI-ZH-PO004 Smoking in the Workplace DI-ZH-PO005 Alcohol and Other Drugs Policy DA-ZH-PR022 Visitor and Contractor Management DA-HR-PR001 Recruitment and Induction Downer Health and Safety Management Plan | Employee Assistance Program (EAP) to be implemented and communicated to all employees at site induction and periodic toolbox meetings Counselled by Company , help sessions Zero tolerance policy | Personal Injury Infrastructure damage | 10 | 1 | 10
people | Camp / Accommodation | Anti social behaviour | Violence Property damage | Loss of employment and income Relationship breakdown FIFO worker Isolation Loss of family members and friends Aggressive personality Alcohol intolerance | Property damage Assault on other camp residents | 1 | Loss of employment and income Relationship breakdown FIFO worker roster Isolation Aggressive personality Alcohol intolerance | BHP References 09-030 Fitness for Work Downer References Downer Health and Safety Management Plan | Employee Assistance Program (EAP) to be implemented and communicated to all employees at site induction and periodic toolbox meetings | property damage | 3 | 0.3 | 0.9
people | Commuting to and from Camp | Incompetent / inexperienced drivers | Single Fatality Project delay Infrastructure damage Legislative Reportable incident Financial loss Plant / truck rollover | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No VOC process developed HR Recruitment process inadequate Insufficient risk assessment | Single Fatality Project delay Infrastructure damage Legislative Reportable incident Financial loss Plant / truck rollover collision Insufficient risk assessment | 4 | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No loading / unloading operating procedures implemented Poor training and VOC process in place | BHP References 09-004 Training and Competency 09-008 Site Access & Security 09-011 Light Vehicles, Buses & Mobile Plant 09-030 Fitness for Work SPR-HR-GEN-005 BHP Approved Training Providers SPR-IHS-SAF-098 WA Iron Ore Requirements for Light Vehicles and Surface Mobile Equipment Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR057 Vehicles and Mobile Plant | Trained and competent personnel identified through recruitment and VOC process Scheduled audits and inspections of safety management system | Minor equipment and property damage FAC injury | 10 | 0.3 | 3
people | Commuting to and from Camp | Night Driving Speeding Fatigue Other drivers | Infrastructure property, plant and equipment damage Loss of life, human / fauna Breaching WA Traffic road rules BHP site requirements and legislation | Journey ManagementPlan not completed Not diving to road conditions, Not complying to state law road rule , BHP TCP' TMP. Driver affected by drugs & alcohol and fatigue | Multiple fatalities Infrastructure damage Breaches of state law regulations and BHP site requirements Native fauna and cattle loss | 4 | Untrained personnel No risk assessment completed Poor training and VOC process in place Poor planning Inadequate supervision | BHP References 09-030 Fitness for Work SPR-IHS-SAFOH-004 Iron Ore Fatigue Management Plan 09-100 Health and Safety Management Plan Downer References Downer Health and Safety Management Plan Downer Journey Management Plan | Journey Management Plan (inc Night Driving Risk Assessment) Fatigue assessments Alcohol and drug testing DETEC training Current Australian drivers licence applicable to vehicle being driven BHP requirements dictates all personnel under 21 years of age not to drive light vehicles and trucks | personal injury infrastructure damage | 10 | 1 | 10
people | Sleeper Laying | Incompetent Operators | Infrastructure property, plant and equipment damage injury, loss of life | Incompetent operator Faulty equipment No Exclusion Zones No Spotter | Single Fatality Injury plant and equipment damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | BHP References 09-003 Induction and Orientation 09-004 Training & Competency 09-011 Light Vehicles, Buses & Mobile Plant 09-036 Rail Safety Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-ST057 Vehicles and Mobile Plant DI-ZH-PO003 Rail Safety Policy | Trained and competent personnel identified through recruitment and VOC process Scheduled audits and inspections of safety management system | property damage personal injury | 10 | 1 | 10
track construction | Laying of Rail | Incompetent Operators | Infrastructure property, plant and equipment damage injury | Failure to follow procedure regarding VOC and ATO process Failure to provide adequate supervision | Personal injury material damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | BHP References 09-003 Induction and Orientation 09-004 Training & Competency 09-011 Light Vehicles, Buses & Mobile Plant 09-036 Rail Safety Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-ST057 Vehicles and Mobile Plant DI-ZH-PO003 Rail Safety Policy | Trained and competent personnel identified through recruitment and VOC process Scheduled audits and inspections of safety management system and procedures | FAC injury | 10 | 1 | 10
track construction | Laying of Rail | Interaction with other contractors | Infrastructure property, plant and equipment damage Fatality | Failure to provide pre start information on interactions with other contractors Failure to implement Track Access Procedures Failure to follow TPO directions Uncontrolled energy | Single Fatality Injury plant and equipment damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | BHP References 09-003 Induction and Orientation 09-004 Training and Competency 09-012 Traffic management 09-036 Railroad Safety 09-049 Guarding, Barricading, Signage and Housekeeping Downer References DA-HR-PR001 Recruitment and Induction DA-ZH-PR003 Training and Competency Management DA-ZH-PR013 Communication and Consultation DA-ZH-PR107 Plant and Pedestrian Interface DI-ZH-PO003 Rail Safety Policy DA-ZH-PR135 Traffic Management Downer Health and Safety Management Plan | Exclusion zones implemented General Alert information provided at pre start communications Correct equipment / guards Trained personnel Positive communications, and allocated radio channels used Risk assessment completed Audits / checks undertaken Implement and communicate TMP and scope to all contractors through EPCM alert system, as required Hot works training and control | Injury Minor Infrastructure damage | 10 | 1 | 10
track construction | Welding of Rail | Incompetent Welders | Infrastructure not built to specifications Unable to utilise tracks Rework to meet specifications Infrastructure damage | Incompetent welder Inadequate Supervision Lack of reporting failures Excessive risk tolerance poor environmental conditions Faulty equipment | Infrastructure damage Reputational loss Commercial loss | 3 | Failure to comply with procedure Failure to conduct adequate VOC and ATO process Failure to provide adequate supervision | BHP References 09-003 Induction and Orientation 09-004 Training & Competency 09-011 Light Vehicles, Buses & Mobile Plant 09-036 Rail Safety Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-ST057 Vehicles and Mobile Plant DI-ZH-PO003 Rail Safety Policy | Trained and competent personnel identified through recruitment and VOC process Scheduled audits and inspections of safety management system and procedures | financial loss | 3 | 1 | 3
track construction | Grinding of Rail | Incompetent Operator | Single Fatality Project delay Infrastructure damage Legislative Reportable incident Financial loss Plant / truck rollover Load failure / dropped objects | Failure to follow Track Access Requirements No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No VOC process developed HR Recruitment process inadequate Insufficient risk assessment | Single Fatality Project delay Infrastructure damage Legislative Reportable incident Financial loss Crane collapse Insufficient risk assessment | 4 | No pre-start checks completed Incorrect equipment used Untrained personnel No risk assessment completed No audits / checks undertaken No rigging or operating procedures implemented No training and VOC process in place | BHP References 09-003 Induction and Orientation 09-004 Training & Competency SPR - IHS-SAF-034-Hot Work Permit SPR - IHS-SAF-071-Hot Work Overview 09-036 Rail Safety Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-ST041 Hot Work DI-ZH-PO003 Rail Safety Policy | Follow TPO directions and process Trained and competent personnel identified through recruitment and VOC process Scheduled audits and inspections of safety management system |  | 10 | 1 | 10
track construction | Clipping Up of Rail | Interaction with other contractors | Infrastructure property, plant and equipment damage Fatality | Failure to provide pre start information on interactions with other contractors Failure to implement Track Access Procedures Failure to follow TPO directions | Single Fatality Injury plant and equipment damage | 4 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | BHP References 09-004 Training and Competency 09-036 Railroad Safety 09-049 Guarding, Barricading, Signage and Housekeeping Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR013 Communication and Consultation DI-ZH-PO003 Rail Safety Policy | Pre start to communicate General alerts, contractor movements Correct equipment / guards Trained personnel Positive communications, and allocated radio channels used Risk assessment completed Audits / checks undertaken Implement and communicate TMP and scope to all contractors through EPCM alert system, as required | personal injury financial loss | 10 | 1 | 10
track construction | Ballasting | Incompetent Ballast Train Operator | Single Fatality Project delay Infrastructure damage Legislative Reportable incident Financial loss Plant / truck rollover Load failure / dropped objects | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No VOC process developed HR Recruitment process inadequate Insufficient risk assessment | Single Fatality Project delay Infrastructure damage Legislative Reportable incident Financial loss Crane collapse Insufficient risk assessment | 4 | No pre-start checks completed Incorrect equipment used Untrained personnel No risk assessment completed No audits / checks undertaken No rigging or operating procedures implemented No training and VOC process in place | BHP References 09-003 Induction and Orientation 09-004 Training & Competency 09-011 Light Vehicles, Buses & Mobile Plant 09-036 Rail Safety Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-ST057 Vehicles and Mobile Plant DI-ZH-PO003 Rail Safety Policy | Trained and competent personnel identified through recruitment and VOC process Scheduled audits and inspections of safety management system | property damage personal injury | 10 | 1 | 10
track construction | Tamping and Regulating | Incompetent Tamper/Regulator Operator | Personal injury Project delay Infrastructure damage Legislative Reportable incident Financial loss Plant / truck rollover Load failure / dropped objects | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No VOC process developed HR Recruitment process inadequate insufficient risk assessment | Single Fatality Project delay Infrastructure damage Legislative Reportable incident Financial loss Crane collapse Insufficient risk assessment | 4 | No pre-start checks completed Incorrect equipment used Untrained personnel No risk assessment completed No audits / checks undertaken No rigging or operating procedures implemented No training and VOC process in place | BHP References 09-003 Induction and Orientation 09-004 Training & Competency 09-011 Light Vehicles, Buses & Mobile Plant 09-036 Rail Safety Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-ST057 Vehicles and Mobile Plant DI-ZH-PO003 Rail Safety Policy | Exclusion zones implemented TPO direction adhered to Trained and competent personnel identified through recruitment and VOC process Scheduled audits and inspections of safety management system | property damage personal injury | 10 | 1 | 10
construction | Earthworks/ Mobile Equipment/excavations | Incompetent operators | • Untrained personnel for task • Inexperienced personnel for task • Injury to personnel | • Operator not licensed • No Verification of Competency completed • Poor task planning • Competent operators not available | Multiple Fatalities Breach of Regulations Infrastructure Damage | 5 | Untrained/inexperienced personnel can put not only themselves in an unsafe position but also any other personnel working in vicinity of them. | BHP References 09-003 Induction and Orientation 09-004 Training & Competency 09-011 Light Vehicles, Buses & Mobile Plant 09-39 Bulk Earthworks and Civil Works Downer References DA-ZH-PR003 Training and Competency Management DA-HR-PR001 Recruitment and Induction DA-ZH-ST057 Vehicles and Mobile Plant | • Site Project Induction detailing VOC process in place and resources available to communicate to all project personnel • Training Needs Analysis in place and resources available to comply with • Project Schedule in place and resources to complete available | Breach of Regulations Infrastructure Damage | 10 | 0.3 | 3
construction | working at Heights | Working from back of truck bed - fall from heights | Loss of human life permanent disability Breach of BHP policies and procedures | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No loading / unloading procedures implemented | Workers compensation claim Family impacted Financial loss | 4 | Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No loading / unloading procedures implemented | BHP References 09-005 Hazard and Risk Management SPR-IHS-SAF-018 Working at Heights-Fall Injury Prevention Systems SPR-IHS-SAF-082 Working at Heights Downer References DA-ZH-PR028 Zero Harm Risk Management DA-ZH-PR042 Working at Heights | Correct equipment / guards Trained personnel Risk assessment completed Audits / checks undertaken Loading / unloading procedures implemented | Personal injury Financial loss permanent disability | 10 | 0.3 | 3
Mobilisation | Development of SWP's, JHA's and CRAW | Not capturing all of the hazards and correct controls for the work on site within the JHA's and SWP's. | Potential delay to start / completion of works; Damaged reputation | Inadequate training Failure to follow procedures Failure to follow BHP procedures | Potential delay to start / completion of works. | 2 | No due diligence process undertaken regarding the hierarchy of controls of the hazards in the project environment | BHP References 09-004 Training & Competency 09-005 Hazard and Risk Management 09-100 Health and Safety Management Plan Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management Downer Health and Safety Management Plan | Training matrix Induction process to include experienced personnel to conduct company training for SWMS, JHA and Take 5 for all personnel involved in the project Company training matrix implemented | minor delays to work commencement | 3 | 0.3 | 0.9
construction | Unloading / Loading | Unescorted trucks | Loss of human life Environmental loss, damage and breach Infrastructure damage Community impact Breaches of the department of transport act & legislation Financial penalties Project delays | No pre-start checks completed Untrained personnel No risk assessment completed No audits / checks undertaken No pre-planning conducted | Multiple fatality Property damage / Loss Environmental damage / loss Financial loss Project delay Breaches of state laws, acts and Regulations | 4 | No pre-start checks completed Untrained personnel No risk assessment completed No audits / checks undertaken No pre-planning conducted | BHP References SPR-OHN-SAFES-001 Vehicle Escort - On and Off Site Downer References DA-ZH-PR022 Visitor and Contractor Management | Trained and competent personnel identified through recruitment process Correct planning and scheduling Contractors to be inducted to site Plant and equipment to comply with BHP Environmental and site compliance inspection TOA/TWA | Breaches of state law traffic and Mines Act legislation Project delays Financial loss | 30 | 3 | 90
construction | Unloading / Loading | Delivery drivers not compliant with site requirements | Infrastructure property, plant and equipment damage Loss of life, human / fauna Breaching WA Traffic road rules BHP site requirements and legislation | Area not secured and managed insufficient contractor screening at contracts stage Failure to complete contractor induction | Personal injury Property damage / Loss Environmental damage / loss Breaches of state laws, acts and Regulations | 3 | Contractors not receiving induction Drivers not holding a current applicable Valid drivers licence | BHP References 09-004 Training and Competency 09-008 Site Access & Security 09-011 Light Vehicles, Buses & Mobile Plant Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR022 Visitor and Contractor Management | Driver inductions implemented and adhered to Trained and competent contractors identified through tender process Correct planning and scheduling Contractors to be inducted to site | Breaches of state law traffic and Mines Act legislation Project delays Financial loss | 3 | 1 | 3
construction | Unloading / Loading | Inadequate lay down/storage area | Vehicle & plant collision Dropped objects Chemical spills Fire & explosion Environmental incident | Incorrect storage facilities No high risk training or VOC assessments No PEAHR review completed Inadequate or no risk assessment Poor planning | Property damage / Loss Environmental damage / loss Breaches of state laws, acts and Regulations | 2 | Untrained and not VOC'd personnel No risk assessment completed No audits / checks undertaken No loading / unloading procedures implemented | BHP References 09-005 Hazard and Risk Management 09-014 Loading & Unloading SPR-IHS-SAF-006 Personal Protective Equipment Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DA-ZH-PR052 Personal Protective Equipment | Prior planning and risk assessments completed Correct storage practices implemented and maintained TMP and signage approved hazard chemical storage containers Spill response equipment in place and maintained Personnel trained in spill response and chemical handling | Infrastructure damage Breaches of state law traffic and Mines Act legislation Financial penalties Pollution of the environment , land and marine Breaches of BHP site requirements | 3 | 0.3 | 0.9
construction | Crane Operations | Incorrect positioning of truck or crane | Loss of human life permanent disability Equipment failure Crane collapse Truck damage | Poor planning Poor supervision Inadequate risk assessment | Single fatalities Property damage / Loss Environmental damage / loss Financial loss Project delay | 4 | No risk assessment completed No audits, inspection / checks undertaken | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management SPR-IHS-SAF-029 Cranage, Lifting & Slinging Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DEDI-ZH-047-CG Cranes and Lifting Equipment | Correct surveying of area Correct planning Risk assessments completed Trained and VOC competent personnel Civil works completed to required standard | Minor Infrastructure damage Project delays Financial loss | 10 | 1 | 10
construction | Moving Culverts with Forklift | Load exceeding SWL | Loss of human life permanent disability Equipment failure Crane collapse Crane damage | Poor planning Poor supervision Inadequate risk assessment Breach of BHP and state law requirements | Single fatalities Property damage / Loss Environmental damage / loss Financial loss Project delay | 4 | No pre-start checks completed Untrained personnel No risk assessment completed No audits / checks undertaken No rigging or operating procedures implemented No training and VOC process in place | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management SPR-IHS-SAF-029 Cranage, Lifting & Slinging Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DEDI-ZH-047-CG Cranes and Lifting Equipment | Lifting and rigging register developed compliant to site requirements Daily gear check undertaken Training and VOC process developed, implemented and communicated to all personnel HR recruitment process developed & reviewed periodically Lessons learnt process developed, implemented and timely actioned Health & safety management system to be reviewed periodically | Infrastructure damage Breaches of state law traffic and Mines Act legislation financial penalties | 10 | 1 | 10
construction | Moving Culverts with Forklift | Travelling with load | Loss of human life permanent disability Equipment failure Crane collapse Crane damage Property damage Connecting with power line Electric shock Reportable incident | No tag lines to secure load No TMP in place Poor communications / spotter Uneven ground / surface No power line vicinity permits in place No risk assessments in place | Loss of human life permanent disability Equipment failure Crane collapse Crane damage Property damage Connecting with power line Electrocution | 4 | Tag lines and dogman to secure load whist travelling load TMP in place Positive communications Uneven ground / surface to be surveyed prior to No power line vicinity permits in place No risk assessments in place | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management SPR-IHS-SAF-029 Cranage, Lifting & Slinging Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DEDI-ZH-047-CG Cranes and Lifting Equipment | Tag lines and dogman to secure load whist travelling load TMP in place Positive communications Uneven ground / surface to be surveyed prior to No power line vicinity permits in place No risk assessments in place | FAC Minor property damage | 3 | 0.3 | 0.9
construction | Placing culverts | uneven placement | damage to material | untrained personnel incorrect survey mark out material caught on bottom of culvert legs | incorrect placement material damage |  |  | BHP References 09-005 Hazard and Risk Management 09-014 Loading and Unloading Downer References DA-ZH-PR028 Zero Harm Risk Management | Check survey mark out spotter and guide to be in alignment where placement should occur clean legs with broom, keeping hands clear of the line of fire. | minimal damage | 3 | 0.03 | 0.09
construction | Forklift Operations | Uneven loads | Loss of human life Dropped objects Chemical spill Property damage | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No loading / unloading procedures implemented | Single fatality Property damage / Loss Environmental damage / loss Financial loss | 4 | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No loading / unloading procedures implemented | BHP References 09-005 Hazard and Risk Management 09-014 Loading and Unloading Downer References DA-ZH-PR028 Zero Harm Risk Management | Pre-start checks completed Correct equipment Trained VOC'd personnel High risk licenced operator Risk assessment completed Audits / checks undertaken Loading / unloading procedures implemented | Minor Infrastructure damage Plant breakdown | 3 | 1 | 3
construction | Excavations | Underground services | Single Fatality Project delay Infrastructure damage Legislative Reportable incident Financial loss Community services disruption | Poor planning Sufficient survey report Scope of works not adhered to Poor supervision Dial before you dig not conducted No spotter in place | Single fatality Property damage / Loss Environmental damage / loss Financial loss Project delay | 4 | No Site survey prior to commencing task No dial before you dig permission obtained prior to commencing work No service locator used and red lined before excavation No pre-planning undertaken No risk assessment | BHP References 09-005 Hazard and Risk Management SPR-IHS-SAF-001 WAIO Health & Safety Excavation & Penetration SPR- IHS-SAF-059 Authority to Work Downer References DA-ZH-PR028 Zero Harm Risk Management DA-ZH-ST043 Excavation Trenching and Services | Site survey prior to commencing task Dial before you dig permission obtained prior to commencing work Service locator used and red lined on plan before excavation Pre-planning undertaken Risk assessment conducted, and reviewed Spotter in place Positive communication | Minor Infrastructure damage | 3 | 0.3 | 0.9
construction | Manual Handling | Muscle strain / injury | MTI permanent disability | No risk assessment completed No personal risk assessment completed Failure to provide Lifting aid Failure to implement safety spine training | Lifting Injury Workers Compensation claim | 3 | Risk assessment not completed prior to starting task Failure to provide PPE to personnel Incorrect PPE Failure to implement safe spine technique Poor planning Inadequate supervision | BHP References 09-005 Hazard and Risk Management 09-028 Manual Handling SPR-IHS-SAF-006 Personal Protective Equipment Downer References DA-ZH-PR085 Manual Handling and Ergonomics DA-ZH-PR052 Personal Protective Equipment | Risk assessment to be completed prior to starting task Provide PPE to personnel Correct PPE Implementation of safe spine technique Correct planning Supervision to monitor personnel | Minor lifting injury | 10 | 1 | 10
construction | Traffic movements within work site | Mobile Plant/Vehicle/Pedestrian interface | Pedestrians hit by plant & equipment Loss of human life | Working without correct permits Inadequate TMP Poor communications No Training or VOC process in place Poor or no planning undertaken Unsure of work scope and limitations of boundaries | Pedestrians hit by plant & equipment Loss of human life Project delays Compensation claim Legislative enquiry | 4 | Incorrect equipment and permits not in place Untrained and not VOC'd personnel No risk assessment completed No audits / checks undertaken Prior planning not undertaken No risk assessment undertaken Poor or no supervision | BHP References 09-004 Training & Competency 09-005 Hazard and Risk Management 09-011 Light Vehicles, Buses & Mobile Plant 09-012 Traffic Management 09-048 Communication and Consultation Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR013 Communication and Consultation DA-ZH-ST057 Vehicles and Mobile Plant DA-ZH-PR135 Traffic Management DA-ZH-PR107 Plant and Pedestrian Interface Downer Traffic Management Plan | Exclusion Zones implemented TMP communicated, implemented and constantly reviewed Contractor meeting schedule developed and implemented Positive communications procedure developed and training conducted Pre- planning prior to commencing contract | FAC injury Minor plant damage | 10 | 1 | 10
track construction | Sleeper Laying | Incorrect manual handling techniques and practices | injury to workers equipment damage | Over exertion Poor posture during lifting, handling Muscle Fatigue Isometric Muscle Movement Prolonged static postures Handling of sharp or awkward materials | Injury causing permanent damage | 3 | Failure to provide adequate training in correct manual handling techniques Failure to provide alternative manual handling equipment or mechanical aids | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management 09-028 Manual Handling SPR - IHS-SAF006-Personal Protective Equipment (PPE) Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DA-ZH-PR052 Personal Protective Equipment DA-ZH-PR085 Manual Handling and Ergonomics | Risk assessment to be completed prior to starting task Provide PPE to personnel Correct PPE Implementation of safe lifting technique sessions Correct planning prior task Supervision to monitor review Risk assessments | FAC injury | 10 | 1 | 10
track construction | Sleeper Laying | Unstable Sleeper Stacks | Infrastructure property, plant and equipment damage injury | failure to follow stacking procedure unloading. Loading of sleepers Uneven Ground Heavy Objects | Personal injury material damage | 3 | Failure to correctly assess environmental conditions and adhere to procedure Failure to provide adequate training Incorrect PPE Poor planning Inadequate supervision | BHP References 09-005 Hazard and Risk Management 09-014 Loading and Unloading Downer References DA-ZH-PR028 Zero Harm Risk Management | Pre-start checks completed Correct equipment Trained VOC'd personnel Risk assessment completed Audits / checks undertaken Loading / unloading procedures implemented | FAC injury | 10 | 1 | 10
track construction | Laying of Rail | Travelling with load | Infrastructure property, plant and equipment damage injury | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No loading / unloading procedures implemented | Single Fatality Injury plant and equipment damage | 4 | Incorrect equipment and permits not in place Untrained and not VOC'd personnel No risk assessment completed No audits / checks undertaken Prior planning not undertaken No risk assessment undertaken Poor or no supervision | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management SPR-IHS-SAF-029 Cranage, Lifting & Slinging Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DEDI-ZH-047-CG Cranes and Lifting Equipment | Exclusion zones implemented TMP communicated, implemented and constantly reviewed Contractor meeting schedule developed and implemented Positive communications procedure developed and training conducted Pre- planning prior to commencing contract | property damage | 10 | 1 | 10
track construction | Welding of Rail | Incorrect manual handling techniques and practices | Infrastructure property, plant and equipment damage injury | • Over-exertion (excessive manual lifting force); • Poor posture during lifting/handling; • Muscle fatigue; • Repetitious movement; • Prolonged static postures; • Handling of sharp / hazardous loads; | • Personal Injury - Slip, Trip, Fall; • Personal Injury - Musculoskeletal injury (Strain/disc injury); • Personal Injury - Hand injury (Crush / Laceration). | 3 | Incorrect body posture Isometric muscle movement Inadequate training in manual handling, correct body posture techniques | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management 09-028 Manual Handling SPR - IHS-SAF006-Personal Protective Equipment (PPE) Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DA-ZH-PR052 Personal Protective Equipment DA-ZH-PR085 Manual Handling and Ergonomics | Risk assessment to be completed prior to starting task Provide PPE to personnel Correct PPE job rotation process Implementation of safe lifting technique sessions Correct planning prior task Supervision to monitor review Risk assessments | FAC injury | 3 | 1 | 3
track construction | Grinding of Rail | Incorrect manual handling techniques and practices | Personal injury leading to permanent damage | Over-exertion (excessive manual lifting force); Poor posture during lifting/handling; Muscle fatigue; Repetitious movement; Prolonged static postures; Handling of sharp / hazardous loads; | Personal Injury - Slip, Trip, Fall; Personal Injury - Musculoskeletal injury (Strain/disc injury); Personal Injury - Hand injury (Crush / Laceration). | 4 | Incorrect body posture Isometric muscle movement Inadequate training in manual handling, correct body posture techniques | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management 09-028 Manual Handling SPR - IHS-SAF006-Personal Protective Equipment (PPE) Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DA-ZH-PR052 Personal Protective Equipment DA-ZH-PR085 Manual Handling and Ergonomics | Use of mechanical aids where possible this may include: - Cranes; - Trolleys; - Hoists. Optimal storage/transport of equipment and materials Correct Manual Handling Techniques Job rotation | personal injury | 10 | 1 | 10
track construction | Clipping Up of Rail | Incorrect manual handling techniques and practices | Personal injury leading to permanent damage | • Over-exertion (excessive manual lifting force); • Poor posture during lifting/handling; • Muscle fatigue; • Repetitious movement; • Prolonged static postures; • Handling of sharp / hazardous loads; | • Personal Injury - Slip, Trip, Fall; • Personal Injury - Musculoskeletal injury (Strain/disc injury); • Personal Injury - Hand injury (Crush / Laceration). | 3 | Incorrect body posture Isometric muscle movement Inadequate training in manual handling, correct body posture techniques | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management 09-028 Manual Handling SPR - IHS-SAF006-Personal Protective Equipment (PPE) Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DA-ZH-PR052 Personal Protective Equipment DA-ZH-PR085 Manual Handling and Ergonomics | Job rotation system to be implemented Risk assessment to be completed prior to starting task Provide PPE to personnel Correct PPE Implementation of safe lifting technique sessions Correct planning prior task Supervision to monitor review Risk assessments | FAC injury | 10 | 1 | 10
track construction | Ballasting | Incorrect manual handling techniques and practices | Infrastructure property, plant and equipment damage injury | • Over-exertion (excessive manual lifting force); • Poor posture during lifting/handling; • Muscle fatigue; • Repetitious movement; • Prolonged static postures; • Handling of sharp / hazardous loads; | • Personal Injury - Slip, Trip, Fall; • Personal Injury - Musculoskeletal injury (Strain/disc injury); • Personal Injury - Hand injury (Crush / Laceration). | 3 | Incorrect body posture Isometric muscle movement Inadequate training in manual handling, correct body posture techniques | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management 09-028 Manual Handling SPR - IHS-SAF006-Personal Protective Equipment (PPE) Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DA-ZH-PR052 Personal Protective Equipment DA-ZH-PR085 Manual Handling and Ergonomics | Risk assessment to be completed prior to starting task Provide PPE to personnel Correct PPE Implementation of safe lifting technique sessions Correct planning prior task Supervision to monitor review Risk assessments Barricading | personal injury | 10 | 1 | 10
track construction | Tamping and Regulating | Incorrect manual handling techniques and practices | Personal injury leading to permanent damage | Over-exertion (excessive manual lifting force); Poor posture during lifting/handling; Muscle fatigue; Repetitious movement; Prolonged static postures; Handling of sharp / hazardous loads; | Personal Injury - Slip, Trip, Fall; Personal Injury - Musculoskeletal injury (Strain/disc injury); Personal Injury - Hand injury (Crush / Laceration). | 3 | Incorrect body posture Isometric muscle movement Inadequate training in manual handling, correct body posture techniques | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management 09-028 Manual Handling SPR - IHS-SAF006-Personal Protective Equipment (PPE) Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DA-ZH-PR052 Personal Protective Equipment DA-ZH-PR085 Manual Handling and Ergonomics | Job rotation to be in place Risk assessment to be completed prior to starting task Provide PPE to personnel Correct PPE Implementation of safe lifting technique sessions Correct planning prior task Supervision to monitor review Risk assessments | FAC injury | 10 | 1 | 10
construction | Earthworks/ Mobile Equipment/excavations | Load exceeding SWL | • Dropped load • Earthworks Mobile Plant over • Personnel injury • Damage to infrastructure | • Untrained personnel for task • Inexperienced personnel for task • Poor task planning • SWL not identifiable on plant • Plant manual not available | Multiple Fatalities Infrastructure Damage Project Delay Reputation Damage | 5 | Operators can put not only themselves in an unsafe position when lifting but also any other personnel working with crane operator | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management 09-011 Light Vehicles, Buses & Mobile Plant Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management DA-ZH-ST057 Vehicles and Mobile Plant | • Pre-lifting complete checklists available and resources available to complete • Training Needs Analysis in place and resources available to comply with | Infrastructure/Property Damage Project Delay Reputation Damage | 10 | 0.3 | 3
construction | Earthworks/ Mobile Equipment/excavations | Travelling with load | • Dropped object • Injury to personnel • Uncontrolled movement of load • Damage to other Vehicle Mobile Plant & Infrastructure | • Operator/Dogman/Rigger not experienced • Operator/Dogman/Rigger not aware of lifting procedures • Lifting procedures not made available to Operator/Dogman/Rigger • Load not controlled using tag lines • Competent operators not available • Poor task planning | Multiple Fatalities Infrastructure Damage Project Delay Reputation Damage | 5 | Operators/Dogman/Riggers can put not only themselves in an unsafe position but also any other personnel working in the immediate vicinity | BHP References 09-004 Training and Competency 09-005 Hazard and Risk Management Downer References DA-ZH-PR003 Training and Competency Management DA-ZH-PR028 Zero Harm Risk Management | • Project Site Induction detailing lifting operation process in place and resources available to communicate • Pre-lifting complete checklists available and resources available to complete • Lifting training package in place and resource available to implement | Infrastructure Damage Project Delay Reputation Damage | 10 | 3 | 30
construction | concrete delivery | Reversing vehicles Spills equipment blockages stored energy | personal injury equipment damage | • no spotter for reversing agitator - blind spots incorrect handling of shute untrained operators incorrect equipment usage | Personnel Injury Equipment damage Project Delay | 3 |  |  | Delivery driver to operate machine - no unauthorised access to equipment | personal Injury Project Delay environmental event | 10 | 3 | 30
construction | concrete placement | hazardous material shute malfunction incompetent operator formwork malfunction suspended loads | concrete spills/ splashes formwork does not hold material Burns from incorrect handling | incompetent operator Faulty equipment No Exclusion Zones No Spotter | Personnel Injury Equipment damage Environmental event Project Delay | 3 |  |  | delivery driver to operate machine - no unauthorised access to equipment Formwork certified by supervisor shute operated by competent operator exclusion zone from suspended load | personal Injury Project Delay environmental event | 10 | 3 | 30
construction | curing | chemical spills | personal injury environmental event | Incompetent operator Faulty equipment No Exclusion Zones No Spotter | personal injury environmental event | 3 |  |  | Chemical drums located on stable ground refilling to be completed over a bunded area - HD plastic in place Eye wash station in close proximity | personal Injury Project Delay environmental event | 10 | 3 | 30
construction | formwork removal | removal of formwork construction by hand manual handling work design | personal injury | incorrect manual handling techniques line of fire work design | personal injury | 3 |  |  | correct ppe - hexarmour gloves work redesign mechanical aids transport to close proximity manual handling techniques two man lift where required | personal Injury Project Delay environmental event | 10 | 3 | 30
construction | working at Heights | untrained/Inexperienced Personnel incorrect Equipment | single fatality Project Delay | No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken | Single fatality |  |  |  | Pre-start checks completed Correct equipment Fall prevention devices in place Fall arrest devices checked and tagged Trained VOC'd personnel High risk licenced operator Risk assessment completed Audits / checks undertaken | personal Injury Project Delay | 10 | 3 | 30
track construction | Turnout Building | Tight access areas Uneven ground Plant V plant V Rollingstock | infrastructure property plant and equipment damage loss of life, LTI | Failure to follow TPO Direction incompetent operator Faulty equipment no exclusion zones incorrect lifting | Death or permanent disability Infrastructure damage plant & equipment damage | 4 | Failure to follow procedure Failure to implement exclusion zones | hard barricading | TPO in place & Direction WP4 form Vortex Fencing ( hard barricade ) | personal injury equipment damange | 10 | 3 | 30
track construction | Ballast removal | Tight access areas Uneven ground Plant V plant V Rollingstock | infrastructure property plant and equipment damage , LTI | Failure to follow TPO Direction incompetent operator Faulty equipment no exclusion zones incorrect lifting | personal injury infrastructure damage plant & equipment damage | 3 | Failure to follow exclusion zones Hard barricading not in place | Vortex fencing between live rail and construction track | TPO in place & Direction WP4 form Vortex Fencing ( hard barricade ) if going going below sub ballast capping dig permit require | personal injury equipment damange | 10 | 3 | 30
track construction | Laying bearers of steel work | Tight access areas Uneven ground Plant V plant V Rollingstock | infrastructure property plant and equipment damage loss of life, LTI | Failure to follow TPO Direction incompetent operator Faulty equipment no exclusion zones incorrect lifting | Death or permanent disability Infracsture damage plant & equipment damage | 3 |  | exclusion zones | Pretsart checks completed TPO in place & Direction Exclusion zones implemented correct equipemnt risk assessments completed Aduits / check undertaken | personal injury equipment damange | 10 | 3 | 30
track construction | clipping up | Manual handling | Personal injury leading to permanent damage | over -exertion ( excessive manual lifting force ) poor posture during lifting & handling Musluce Fatigue Repetitious movement prolonged static postures handling of sharp /hazardous loads | Personal injury - slip trip fall Personal injury Musculoskeletal injury strain/disc injury hand injury crush /laceration | 3 | failure to follow correct lifting techniques | mechanical aids | Experienced Trained & competent personnel identify through recruitment process Correct lifting techniques & use of mechanical aids proper manual handling training correct inspection of hand tools | personal injury equipment damange | 10 | 3 | 30
track construction | welding of rail | Sparks & Fires | Personal injury leading to permanent damage | Failure to follow Track Access Requirements No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No VOC process developed HR Recruitment process inadequate Insufficient risk assessment | Personal injury - slip trip fall Personal injury Musculoskeletal injury strain/disc injury hand injury crush /laceration | 3 | Failure to follow procedure Failure to implement exclusion zones | guards and barriers | Experienced Trained & competent personnel identify through recruitment process Hots works & Fire Fighter trained | personal injury equipment damange | 10 | 3 | 30
track construction | moving rail | Stored energy | Personal injury leading to permanent damage | Failure to follow Track Access Requirements No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No VOC process developed HR Recruitment process inadequate Insufficient risk assessment | Personal injury - slip trip fall Personal injury Musculoskeletal injury strain/disc injury hand injury crush /laceration | 3 | Failure to follow procedure Failure to implement exclusion zones | mechanical aids where possible | Experienced Trained & competent personnel identify through recruitment process procedure for clipping unclipping rail cutting rail work redesign considered supervision of work site to be maintained correct plant & equipment to carry out steel work place ment prior planning & communication of plan to all work groups | personal injury equipment damange | 10 | 3 | 30
track construction | Dissmantling Turnouts and Railway track removal | Stored energy | Infrastructure property plant and equipment damage loss of life, LTI Wildlife beening injured or dead | Failure to follow Track Access Requirements No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No VOC process developed HR Recruitment process inadequate Insufficient risk assessment | Death or permanent disability infrastructure damage plant & equipment damage |  | Failure to follow Track Access Requirements No pre-start checks completed Incorrect equipment Untrained personnel No risk assessment completed No audits / checks undertaken No VOC process developed HR Recruitment process inadequate Insufficient risk assessment | mechanical aids where possible | Hot works , TPO in place risk easements done before task are start ID possible wildlife in area or under tracks | personal injury equipment damange | 10 | 3 | 30
DO NOT REMOVE
[17 empty] | Severity | Likelihood | MFL Level | Entered in to 1SAP
[17 empty] | 1000 | 10 | 1 |  | Yes
[17 empty] | 300 | 3 | 2 |  | No
[17 empty] | 100 | 1 | 3
[17 empty] | 30 | 0.3 | 4
[17 empty] | 10 | 0.1 | 5
[17 empty] | 3 | 0.03 | 6
[17 empty] | 1 |  | 7
Note on I3: sallyannerinehart: references to be amended over coming week