## Cover Page
BHPB IRON ORE RISK REGISTER COVER PAGE
Date: | 2013-09-16
Physical Site: | BiLo
Department: | Rail Engineering
Area: | Nelson Point Rail Yard
Risk Assessment Title / Description: | BiLo Crossing Upgrade
Risk Assessment Scope: (Boundry of assessment/Subject) | Design, supply and installation of active crossing protection- flashing signal and boom barrier assembly.
Risk Assessment type: (Work place risk assessment, Construction risk assessment, Coporate risk assessment) | Construction Risk Assesment
Other References: Documents/Photographs:
Risk Assessment Team Details:
Name |  | Position | Signature | Industry Experience in similar industry (Years) | Job Experience in similar role (Years)
Approved By: |  | Name: |  | Signature: | Date:

## References
Reference documents included in the Risk Assessment workshop
Ref. | Number | Title | Location | Description
1 |  |  |  | Hot Works
2 |  | SPR-IHS-SAF-034 |  | Hot Work Permit Procedure
3 |  | FRM-IHS-SAF-028 |  | Hot Work - Hazardous Area Hotwork Permit Certificate
4 |  | FRM-IHS-SAF-011 |  | Hot Work Permit Cut Off Disc
5 |  | SPR-IHS-SAF-026 |  | Preventing Electric Shocks when using Electric Arc Welding Machines
6
7 |  |  |  | Working at Heights
8 |  | SPR-IHS-SAF-082 |  | Working at Heights (FRCS 2.9) – Working at Heights
9 |  | FRM-IHS-SAF-007 |  | Working at Heights Permit
10 |  | SPR-IHS-SAF-013 |  | Mobile Elevated Work Platforms
11 |  | SPR-IHS-SAF-014 |  | Working at Heights (FRCS 2.9) - Working on Roofs Safely
12 |  | SPR-IHS-SAF-015 |  | Scaffolding
13 |  | SPR-IHS-SAF-016 |  | Portable Ladders
14 |  | SPR-IHS-SAF-017 |  | Fixed Platforms
15 |  | SPR-IHS-SAF-018 |  | Working at Heights
16 |  | SPR-IHS-SAF-019 |  | Working at Height Permit Procedure
17 |  | SPR-IHS-SAF-020 |  | Removal of flooring and hand railing safety procedure
18 |  | SPR-IHS-SAF-092 |  | Working at Heights (FRCS 2.9) Control of Dropped Object Hazards
19 |  | FRM-IHS-SAF-128 |  | Working at Heights (FRCS 2.9) - Dropped and Falling Objects Checklist
20
21 |  |  |  | Authority to Work & Isolations
22 |  | SPR-IHS-SAF-059 |  | WAIO Authority to Work
23 |  | SPR-IOH-SAF-009 |  | Iron Ore Authority to Work
24 |  | FRM-IHS-SAF-006 |  | Authority to Work Form
25 |  | SPR-IHS-SAF-024 |  | Isolation & Permit To Work (FRCS 2.8)
26
27 |  |  |  | Confined Space
28 |  | SPR-IHS-SAF-070 |  | Confined Spaces (FRCS 2.11) - WAIO Confined Space Management
29 |  | FRM-IHS-SAF-029 |  | Confined Space Permit
30 |  | FRM-IHS-000-031 |  | Confined Space Inherent Hazard Risk Assessment template
31
32 |  |  |  | Excavations & Penetration
33 |  | SPR-IHS-SAF-001 |  | WAIO Health & Safety Excavation & Penetration Procedure
34 |  | FRM-IHS-SAF-041 |  | Excavation & Penetration Permit
35
36 |  |  |  | Portable Hand Tools & Electrical
37 |  | SPR-IHS-SAF-040 |  | Portable Hand Tools
38 |  | SPR-IHS-SAF-060 |  | Safe Electrical Work On Low Voltage Electrical Installations
39 |  | SPR-IHS-SAF-095 |  | Electrical Tool Check
40 |  | SPR-IHS-SAF-075 |  | Electrical Log Book Procedure
41 |  | REG-IHS-SAF-026 |  | WAIO Prohibited and Restricted Use Register
42
43 |  |  |  | Site Access Procedure
44 |  | SPR-IHS-SAF-007 |  | Site Access Procedure
45 |  | FRM-IHS-000-010 |  | Request for Site Access
46 |  | FRM-IHS-000-011 |  | Visitor Site Access Exception
47 |  | PDN-IHS-000-002 |  | WAIO Site Responsible Person (SRP) Role and Responsibilities
48 |  | SPR-OHN-SAF-069 |  | Daily Workplace Inspections
49 |  | FRM-OHN-SAF-050 |  | Daily Workplace Inspection Checklist
50 |  | FRM-IHS-SAF-001 |  | JHA Template

## RISK ASSESSMENT
| Install/Repair "Hungry" boards | Working at Heights | Fall from height to ground | No barrier or physical restrain e.g. handrails or barricading | Fatality | Major | Possible | E | Extreme (18) | Build scaffolding to access tray area, using a competent scaffolder. |  |  |  | x |  |  | Low | Unlikely | L | Low (2) | N/A |  |  |  | x
| Install/Repair "Hungry" boards | Working at Heights | Fall from height to ground | No procedure in place to explain safe working process; Unsafe behaviour (3-point contact) | Fatality | Major | Possible | E | Extreme (18) | FRCP 9 procedure SPR-SAF-XXX-002 and use fall restrain harness to prevent walking over the edge of the tray |  |  |  |  | x |  | Major | Unlikely | H | High (14) | Install temporary steps with handrails and handrails at the back of the tray. |  |  |  | x
BiLo Crossing Upgrade
Issue # | Activity/Task (Description) | Hazard/ Aspect | Unplanned/unwanted Event (Issue) | Contributing Factors/Causes Root Causes - Latent Causes - Direct Causes | Maximum Foreseeable Loss (Most plausible worst case scenario - controls not in place) | Raw Risk |  |  |  | Current Controls/ODG Controls | Hierarchy of Controls | [5 empty] | Residual Risk |  |  |  | New Actions / Further Requirements BHPBIO Controls | Hierarchy of Controls | [5 empty] | Risk After Action |  |  |  | Actioned by Who? (Name and Surname) | Actioned By When | Entered into FPe
[6 empty] | Consequence | Likelihood |  | Ranking |  | Eliminate | Substitute | Redesign | Separate | Administrate | PPE | Consequence | Likelihood |  | Ranking |  | Eliminate | Substitute | Redesign | Separate | Administrate | PPE | Consequence | Likelihood |  | Ranking
1 | Employee Selection | Safety | Incorrect Skill Set Injury/damage | No pre employment process to verify personnel | Fatality/Perm disability | Major | Possible | Possible,Major | Extreme (18) | Pre Employment Interview & Selection Process ODG Induction & Conduct on site. Contractor competencies are presented to ODG and assessed prior to mobilisation. If they are found to be lacking in any specific area required for the work to be completed, they will either be up skilled prior to mobilisation or at site. |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | [9 empty] | ,
|  | Safety | Unsafe Acts, Behaviours and Misconduct | Lack of accountability | Fatality/Perm disability | Major | Possible | Possible,Major | Extreme (18) | Workers encouraged to participate in BBS process, Adequate Supervision, Selection process followed, |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | SPR-IHS-SAF-103 Behavioural Based Safety Peer on Peer, Managers to supervisor level to participate in SAO process SPR-IHS-SAF-081 Safe Act Observation Procedure. HR and onsite Management to utilise the Just Culture Framework WIN-IHS-GEN-004 Just Culture Decision Tree
2 | Training | Safety | Training Competencies not valid | VOC/Qualifications not confirmed prior to mobilisation WAIO training requirements not followed Inductions not completed prior to mobilisation | Fatality/Perm disability | Major | Possible | Possible,Major | Extreme (18) | VOC on all operators/Drivers, Training Matrix, ODG TNA, Spv Workshop ,ODG IMS 4.2 HSEC Training Requirements, ODG IMS 4.3 Safety Inductions, BHPBIO WAIO Training requirements. ODG will ensure that all of their supervisors undertake Front Line Management Training . |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | we will comply with the requirements of BHPBIOB WAIO Leadership Training.BHPBIO review qualifications prior to mobilisation. ODG to provide updated training matix, BHP Supervisor mobilisation, spot audits conducted by BHPB | [8 empty] | ,
3 | Fitness for Work | Safety | Personnel not fit for work | No D&A process conducted during pre employment Personnel under the influence of drugs and alcohol | Fatality/Perm disability | Major | Possible | Possible,Major | Extreme (18) | Pre employment medical & D&A Testing ODG IMS 4.1 Employee selection and pre-placement health evaluation, daily alcohol testing, random BHP D&A screening. |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | [9 empty] | ,
|  | Safety | Fatigue related incidents. | Rosters driving. No rest breaks during travel. Late work hours. Fatigue Management not followed. | Fatality/Perm disability | Major | Possible | Possible,Major | Extreme (18) | Shared Drivings, passenger/s to monitor driver. Approved TMP, All staff to complete Fatigue Awareness. All personnel assessed at daily prestart - Fit for work by supervisor. Reduced working hours, a mandatory 10 hrs break between starting time. Comply with BHP fatigue management. BHPBIO WAIO SPR-IHS-SAFOH-004 FATIGUE MANAGEMENT |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14)
4 | Site Location | Safety | Inadequate Supervision | Supervisor not competent in role Supervision unable to cover all work areas due to limited numbers | Fatality/Perm disability | Major | Rare | Rare,Major | High (14) | Provide relevant training. Develop Safe Work Procedure and Job Hazard Analysis, Correct Supervisor to Worker Ratio. 1:10 Ratio Supervisors to workers. |  |  |  |  | x |  | Major | Rare | Rare,Major | High (10) | BHPBIO FRM-IHS-SAF-159 Rail Interactions, BHPBIO GLD.010 FATAL RISK CONTROLS. BHPBIO WAIO SPR-IHS-SAFOH-004 FATIGUE MANAGEMENT, BHPBIO FRCP 1. & 2 | [8 empty] | ,
|  | Safety | Incident, Injury, Equipment damage, Uncontrolled release, Unplanned events | Personnel not competent/trained for the task, non-conformance and failed reporting | Fatality/Perm disability/Equip Damage | Major | Possible | Possible,Major | Extreme (18) | Promote ODG Zero Harm and Safety Allways Philosophy. |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | SPR-IHS-SAF-002 Event Management Procedure
5 | Clearing lay down area | Safety / Environment | Wrong location Permits not acquired | Environmental clearance requirements not considered | Significant Environmental/Heritage Damage | Major | Possible | Possible,Major | Extreme (18) | Authorization & Permits in place Weed & Seed Clearance with all Surface Equipment , ODG ensure Weed and Seed requirements met. |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | Area in line with PEAHR Requirements | [8 empty] | ,
6 | Motor Vehicle / Plant Vehicle Selection | Safety | Not fit for task | FRCS compliance not achieved prior to mobilisation | Fatality/Perm disability | Major | Possible | Possible,Major | Extreme (18) | Pre-Starts completed each day prior to departing, All vehicles tracked by ODG fleet to ensure they are covered by FRCS (not expired), |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | BHPBIO FRCP 1. & 2. LV and road going vehicles to comply with BHPBIOBIO SPR-IHS-000-001 Light and Roadgoing Vehicle Use, SPR-IHS-SAF-098 Minimum requirements for Light Vehicles and Surface Mobile Equipment and STD-IOH-SAF-004 WAIO Traffic Management | [8 empty] | ,
|  | Safety / Environment | Spillage of Hydrocarbons' | No spill kits Faulty plant | Fatality/Perm disability | Major | Possible | Possible,Major | Extreme (18) | Spill Kit/Bunding/Permits WIN-IEN-HC-001 Major and Minor Spill Response. Prestart completed before coming to site. If equipment is faulty tag out and report to supervisor. CCCR | x |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | [9 empty] | ,
7 | Motor Vehicle / Plant Operations | Safety | Single Vehicle Incident , Rail mounted equpiment vs vehicle (SME or LV) | WAIO traffic management plan not followed, incompetent driver, Track procedures not followed, fatigue, Fitness for Work | Fatality/Perm disability | Major | Possible | Possible,Major | Extreme (18) | Relevant licenses/tickets, VOC, Trained and competent in plant, Road going vehicles procedure, Take 5 and JHA., drive to conditions, avoid driving at night |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | Rail traffic management plan, STD-IOH-SAF-004 WAIO Traffic Management, LV and road going vehicles to comply with BHPBIOBIO SPR-IHS-000-001 Light and Roadgoing Vehicle Use, SPR-IHS-SAF-098 Minimum requirements for Light Vehicles and Surface Mobile Equipment Confirm the driver awareness training, BHB Fatigue Management Procedure | [8 empty] | ,
|  | Safety / Environment | Unfamiliar with travel requirements' | Travel management requirements not communicated | Fatality/Perm disability | Major | Possible | Possible,Major | Extreme (18) | WA road rules, drive to conditions, more experienced driver to travel the first few trips with new driver |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | Journey Management/Speed limits BHPBIO WAIO access road operating procedures | [8 empty] | ,
|  | Safety / Environment | Vehicle damage | No vehicle inspections Poor maintenance | Fatality/Perm disability | Major | Possible | Possible,Major | Extreme (18) | Vehicles Inspected on daily basis (Pre-start) FRCS compliance, SPR-IHS-SAF-098 Minimum requirements for Light Vehicles and Surface Mobile Equipment |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | [9 empty] | ,
|  | Safety | Injured by operating plant | Equipment guarding removed or missing/Inadequate demarcation and seperation of machine and people. | Fatality/Perm disability | Major | Possible | Possible,Major | Extreme (18) | No plant or machinery to be operated with guards missing or removed. Machinery to be maintined to manufacturers specifications. Hard barricading installed where necessary at work area. 'Spotter' required at all times whilst machine is in operation. Spotter to keep position of safety. |  |  |  | x | x |  | Major | Unlikely | Unlikely,Major | High (14) | Hard Barricade around Excavations Signage SPR-HIS-SAF-001
|  | Health | Excessive noise generation- Damage to hearing from operation of plant. | Not wearing suitable hearing protection. | LTI/RWC | Moderate | Possible | Possible,Moderate | High (13) | Noise Management ODG-SP-019. Provide training in hearing loss prevention. Supervision to exclude persons not involved in direct activity to reduce exposure. Select suitable hearing protection and wear hearing protection when using noisy machinery. i.a.w. WA Code of Practice ‐ Managing Noise at Workplaces. |  |  |  | x |  | x | Major | Unlikely | Unlikely,Major | High (14) | Personal Protection Equipment (PPE) SPR-IHS-SAF-006.
|  | Safety | Mobile Plant vs. People, Mobile Plant vs. Vehicles, Mobile Plant vs. Rolling Stock | Poor worksite layout/traffic management | Fatality/Perm disability | Major | Likely | Likely,Major | Extreme (21) | ODG worksite traffic management, use of barricading and signage, appropriate segregation of SME, LV's and pedestrians. |  |  |  | x | x |  | Major | Unlikely | Unlikely,Major | High (14)
9 | Establish Lay down Area | Safety / Environment | Wrong location - Lay Down established in an unsafe position with unstable grounds and hydrology issues | Poor communication Incorrect drawings | Fatality/Perm disability | Major | Likely | Likely,Major | Extreme (21) | Obtain correct drawing & locations. |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | [9 empty] | ,
| Transport of Materials/loading of trucks. | Safety | Manual Handling Injury | Poor technique no mechanical aids | LTI/RWC | Moderate | Likely | Likely,Moderate | High (17) | Safe Spine/ Mechanical Aids |  | x |  |  | x |  | Moderate | Unlikely | Unlikely,Moderate | Moderate (9) | SPR-HIS-SAF-064 WAIO Manual handling | [8 empty] | ,
10 |  | Safety | Poorly secured loads can shift in transit and can be dangerous to unload resulting in further damage and injury to people unloading equipment | Inadequate securement of plant and equipment and/or hazardous road conditions during transportion to site | LTI/RWC | Moderate | Possible | Possible,Moderate | High (13) | Loading restraint to comply with NTC Australia Load Restraint Guide. |  |  |  |  | x |  | Moderate | Unlikely | Unlikely,Moderate | Moderate (9)
| Unload & loading of Plant | Safety / Environment | Transport Company unfamiliar with Area | No escort | Fatality/Perm disability | Major | Likely | Likely,Major | Extreme (21) | BHPBIOBIO Approved transport company (no escort required) Inducted personnel to escort vehicles ODG Delivery Driver Inductiion |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | [9 empty] | ,
|  | Safety | Incorrect loading of equipment | No supervision | Fatality/Perm disability | Major | Likely | Likely,Major | Extreme (21) | Loading to be supervised by ODG JHA / Take 5/Pre lift assessment completed to address risk of loading. Traffic Management. |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | [9 empty] | ,
|  | Safety | load not suitable for transport | No load plan | LTI/RWC | Moderate | Likely | Likely,Moderate | High (17) | Load plan to be sent with all loads |  |  |  |  | x |  | Moderate | Unlikely | Unlikely,Moderate | Moderate (9) | [9 empty] | ,
13 |  | Safety / Environment | Shifting of loads | Road condition Inadequate strapping resulting in unsecured load | Fatality/Perm disability | Major | Likely | Likely,Major | Extreme (21) | Load to be inspected in Transit Load secured |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | [9 empty] | ,
| Fuel storage-Hydrocarbon | Safety / Environment | Incorrect storage | Storage requirements not understood | Fatality/Perm disability | Major | Possible | Possible,Major | Extreme (18) | Bulk Fuel Trailer double skinned & Spill kit available. |  |  | x |  | x |  | Major | Unlikely | Unlikely,Major | High (14)
14 |  | Safety / Environment | Ignition | Hydrocarbon chemical nature No fire equipment on site | Fatality/Perm disability | Major | Possible | Possible,Major | Extreme (18) | Portable fire equipment on site & near fuel storage |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14)
15 | Chemical stores | Safety / Environment | Unknown Chemicals Chemicals not stored correctly | Hazard management process not complied with | Chemical exposure | Moderate | Possible | Possible,Moderate | High (13) | Lay down Area to be sign posted & barricaded Bunded storage areas |  |  |  |  | x |  | Moderate | Unlikely | Unlikely,Moderate | Moderate (9) | Hazard Materials Management to comply with BHPBIO SPR-PHS-SAFHY-001, MSDS for all Chemical's JHA/Pre-Start BHPBIO BIO Approved Separation/fire equipment/ no flame signage Fire Cabinet's SPR-IEN-HC-001 WAIO Hydrocardon and Hazardous Chemicals
| Excavation/ Trenching/ Under boring | Safety / Environment | Open Trench/excavation causing fall hazard | Area not delineated barricading not in place | Fatality/Permanent disability | Moderate | Possible | Possible,Moderate | High (13) | Hard barricading, Appropriate signage, Backfill (same day), Overnight Management Plan SPR-HIS-SAF-001. WMS, JHA and 5 Step to address risks of injury from falls into open trenches as well as ensuring vehicles and plant are not driven into or onto open trenches. Pedestrian access limited or restricted, vehicle access restricted, defined access points, benching batters and windrows managed, use barricading appropriate to the risk at the site |  |  |  | x |  |  | Major | Rare | Rare,Major | High (10)
|  | Safety / Environment | Equipment failure | Pre starts not completed equipment failure, personnel within the slew zone. | Fatality/Perm disability | Major | Likely | Likely,Major | Extreme (21) | VOC operator to carry out prestarts, prestart checks, personnel/spotters to stay outside slew zones, operator to stop machine and inspect, e-stops, regular inspections of machinery |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | Pre- Star Checks JHA/Take 5
|  | Health | Extreme weather causing heat illness | No enough water provided No rest breaks | LTI/RWC | Moderate | Possible | Possible,Moderate | High (13) | Training and instruction/ Monitor/Water shade where possible Regular breaks, |  |  |  |  | x |  | Moderate | Unlikely | Unlikely,Moderate | Moderate (9)
|  | Safety / Environment | Dust causes reduced visability + Respitory issues | Dust suppression not utilised | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Water truck available if dust becomes a hazard / Suitable PPE . |  |  | x |  |  | x | Major | Unlikely | Unlikely,Major | High (14)
|  | Safety | Hitting Existing Underground Services | Excavation permit not obtained Failure to identify existing services CSM diagrams not up to date Unidentified services | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Current drawings and/or vacuum pot-holing and have excavation permit approved, keep at hand on site. Vicinity/Excavation Permit, gummy bucket, positively identify services, no mechanical excavtions within 1m of known services. Isolate where possible, spotter, |  |  |  |  | x |  | Major | Rare | Rare,Major | High (10) | Excavation Penetration Permits - updated monthly
|  | Safety / Environment | Site Traffic | Not following Rail TMP Breakdown in communication | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Approved TMP, Suitable signage i.e. warning, speed, radio channel etc / Contractor co-ordination |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | General alert issued notifying site of TMP.
|  | Safety / Environment | Caught in moving parts Struck by equipment | Missing Guards Person in line of fire No Prestart Inadequatre supervision | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Prestarts, equipment compliance, keep out of line if fire i.e outside slew radius and keep hands clear of moving parts, exclusion zones/barricading, communications, adequate supervision, workplace inspections, | [6 empty] | Major | Unlikely | Unlikely,Major | High (14) | BHPB compliant equipment, VOC requirements, WAIO and site specific inductions.
17 | Pit & Pipe installation. | Safety | Muscular/skeletal damage from manual work; burns from hot conduits | Inadequate planning and execution of lifting, carrying and placing conduits/direct sunlight | LTI/RWC | Moderate | Possible | Possible,Moderate | High (13) | WMS, JHA and Take 5 to address risks of injury from manual work and on the job training/supervision in manual handling of conduits. Ensure correct P.P.E |  |  |  |  | x | x | Moderate | Unlikely | Unlikely,Moderate | Moderate (9)
|  | Safety | Chemical Exposure | Inapropriate use, inadequate storage, lack of PPE | LTI/RWC | Moderate | Possible | Possible,Moderate | High (13) | MSDS, use in accordance with manufacturers guidelines, first aid kits in vehicles, safety event management, stored in accordance with site requirements. | [6 empty] | Moderate | Unlikely | Unlikely,Moderate | Moderate (9) | BHPB ESO on site.
18 | Lifting | Safety | Unauthorised personal in work Area | lack of barricading/supervision | Fatality/Perm disability | Major | Possible | Possible,Major | Extreme (18) | Rigger/dogman to identify safe position of all pesonnel in vicinity prior to lift. Barricade working radius. Inc signage FRCP10, Traffic Management, do not walk under suspended loads, |  |  |  | x | x |  | Major | Unlikely | Unlikely,Major | High (14)
|  | Safety | Fall from height to ground | Personnel not trained Incorrect access to equipment | Fatality/Permanent disability | Major | Likely | Likely,Major | Extreme (21) | Only Trained & VOC personal to work with Crane FRCP10, 3 points of contact, no acessing plant unless adequate barricading fitted, |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14)
|  | Safety | Extreme Weather resulting in loss of load | Not following lifting procedure | Fatality/Permanent disability | Major | Likely | Likely,Major | Extreme (21) | Weather Report/ no lifting in Lifting bad weather, rigger/dogman, crane driver to determine if safe to lift, follow crane OEM standards |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | SPR-HIS-SAF-029
|  | Safety | Over loading of Crane & lifting Gear | Lifting chart/prelift assessment (lift study)not completed | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | VOC Rigger manufactures lifting chart to be used JHA & Engineered Lift study over 30 Tonne |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | SPR-HIS-SAF-029 FRCP10,
|  | Safety | Lifting equipment not maintained in good order | Pre-starts not completed | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | All lifting equipment must be inspected prior to use and must have current quartely test/tag |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14)
19 | Electrical Installation/Removal | Safety | Electric shock/Electrocution | No isolation in place Isolation procedure not followed | Fatality/Permanent disability | Major | Likely | Likely,Major | Extreme (21) | Tag out lock out by Trained SPV ODG Training analysis Trained and competent |  |  |  | x | x |  | Major | Unlikely | Unlikely,Major | High (14) | SPR-HIS-SAF-024 FRCP8 BHPBIO Event management Isolation Procedures
|  | Safety | Installation and Cutting of cables causing laceration | unqualified personnel PPE (gloves) Correct tool for the job | LTI/RWC | Moderate | Possible | Possible,Moderate | High (13) | Gloves Take 5 Pre Start correct tool for job. Retractable Stanley knives 'only'. Stripping tools, cable cutters |  |  |  |  | x | x | Moderate | Unlikely | Unlikely,Moderate | Moderate (9) | BHPBIO Banned tools register Portable Hand Tools & Electrical. REG-IHS-SAT-026.Waio Prohibited & Restricted use Register
|  | Safety | Removal of Incorrect Cable | Isolation breach Person not competent to preform task Incorrect labelling/drawings | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Competent person to identifys, drawings to be checked for currency prior to works commencing, |  |  | x |  |  |  | Major | Rare | Rare,Major | High (10) | Authority to Work & Isolations. SPR-IHS-SAF-024 Isolation & Permit to Work (FRCS 2.8)
|  | Loss/Damage | Damage to existing services and new cables | Unqualified personnel Pit conditions Manual handling Installing equipment | $15 - $150k | Moderate | Possible | Possible,Moderate | High (13) | Competent person to identify , isolate and tag redundant cables at both ends, prior to removal works, drawings to be checked for currency prior to works commencing, | [6 empty] | Moderate | Unlikely | Unlikely,Moderate | Moderate (9) | Authority to Work & Isolations. SPR-IHS-SAF-024 Isolation & Permit to Work (FRCS 2.8) Excavation and penetration permit Supervision/Permit officer present and approve method.
|  | Safety | Sprains/strains | Manual Handling | LTI/RWC | Moderate | Possible | Possible,Moderate | High (13) | Correct lifting technique Mechanical aids | [6 empty] | Moderate | Unlikely | Unlikely,Moderate | Moderate (9)
20 | Ladder Work | Safety | Fall from height Use of Ladder's causing fall from height when entering/exiting plant General use of ladders including platform ladders | No 3 points of contact Uneven Ground Incorrect ladder set up | LTI/RWC | Moderate | Possible | Possible,Moderate | High (13) | 3 Point contact at all times Take 5 Avoid use of ladder where possible Operator to verify safe even ground |  |  |  |  | x |  | Moderate | Unlikely | Unlikely,Moderate | Moderate (9) | FRCP9 SRP-IHS-SAF-016. Use of Portable Ladders.
21 | Use of EWP | Safety | Fall from height | Unstable ground faulty machine not wearing fall protection Not qualified to operate equipment | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Trained and competent operators, Prestart, Fall protection worn, High Risk Licence, environmental conditions, level and stable ground, fall protection tagged and in good condition - inspections, spotter, VOC | [6 empty] | Major | Rare | Rare,Major | High (10) | WAH Procedure
|  |  | Mechanical failure | Prestarts not completed Incompetent operators Incorrect machine | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Pre starts, EWP approved to be on site, Quarterly Inspection sticker, correct machine for task, trained and competent operators. | [6 empty] | Major | Unlikely | Unlikely,Major | High (14) | FRCS Compliance
|  |  | Rail/Vehicle Interactions with EWP | Work site in close proximity to road and rail Working between traffic Incorrect level of protection i.e TOA, TWA, etc | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | TPO to be present when working within rail corridor and to obtain relevant level of protection, spotter, allow clear path to be able clear track, Traffic management when required, clear communication between operator, TPO and Traffic management. | [6 empty] | Major | Unlikely | Unlikely,Major | High (14) | BHP Rail Procedures Approved TMP
|  |  | Falling Objects | No lanyards/matting/kickboards Unsecured tools and equipment No nominated drop zone | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Lanyards, matting and kickboards in place, Drop zone in place, correct EWP selection, spotter, | [6 empty] | Major | Unlikely | Unlikely,Major | High (14) | Dropped Object Checklist, WAH Procedure
23 | Hand Tools | Safety | Personal Injury Damage to equipment | Inspection and testing of hand tools not completed, guarding removed/missing Tools in poor condition | LTI/RWC | Moderate | Possible | Possible,Moderate | High (13) | Inspection of Hand tools & correct storage to be used, PPE to be used, guarding inspection and maintenance, Deadman devices on rotating plant and hand tools, | [5 empty] | x | Moderate | Unlikely | Unlikely,Moderate | Moderate (9) | BHPBIO Banned tools register Portable Hand Tools & Electrical. REG-IHS-SAT-026.Waio Prohibited & Restricted use Register
24 | Generator use | Safety | Electrocution Generator Damage Exhaust fumes Petrol Hydrocarbon Spill | Generator not inspected or in poor condition | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Inspection of Gen set for Earth & RCD Leads off ground compliance sticker SPR-HIS-SAF-027 FRCP8. Inspected by competenet person/s. Testing and tagging, generator to be set up to avoid fumes entering work site and enclosed spaces, Ensure permit to use petrol is obtained, correct storage, spill kit, self bunded tank conforming to BHP requirements. |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14)
25 | Working on or near Rail. | Safety | Safeworking Breach | Track protection not in place Working on live line Break down in communication Use of mobile phone | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | BHPBIOBIO Train Infrastructure basic training for all ODG site workforce Advanced rail coordinator on track when required TOA & TWA. Correct level of protection is being used. Ensure POS is clearly identified. Follow procedures, utilise look outs. Take 5 & JHA. AS4292. Work under Rail Protection Radio contact with Train control No fouling the line with out rail safety controls or with out permission. Check work teams know which radio channel is applicable to their work area. Also ensure verbal acknowledgement is taking place. No phones to be used within the rail corridor. |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | PRC-RRO-PLN-023 BHPBIO railroad safety management plan SPR-RHS-SAF-025 Railroad operations communications Use of two way radio/UHF Channel 19 PRC-RAL-GEN-004 Rail Escalation Procedure Hard barricading at 3m from outer rail Rail Safety Standards. Qualified TPO to verify controls. Track Access Training for all construction personnel
|  |  | Damage to per way due to excavation | Excavator bucket causes misalignment of track or other track damage Track obstruction |  | Moderate | Possible | Possible,Moderate | High (13) | TPO to minitor site, notify track maintenance in the event of damage, spotter in place, notify BHP personnel, | [6 empty] | Moderate | Unlikely | Unlikely,Moderate | Moderate (9)
|  |  | Injury due to uneven terrain | Nature of work site ballast, rail, track side equipment, leads, poor housekeeping |  | Moderate | Possible | Possible,Moderate | High (13) | Housekeeping, vigilant, eyes on path, sure footing, trained and competent, laced up ankle, personnel behaviours, awareness. Risk assessment - take 5, JHA, safestart, nominated walkways, safe access/egress. | [6 empty] | Moderate | Unlikely | Unlikely,Moderate | Moderate (9)
26 | Cyclone warning/Extreme Weather | Safety / Environment | Injury to personnel and property damage due to extreme weather | Cyclone procedure not followed Inadequate preparation Personnel unaware of procedure | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Rapid/ODG Cyclone Procedures to be used/ Cyclone watch to monitor event BHPBIO induction & evacuation area to be seen. Raise at safety talks - prestarts and toolbox. |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | Tropical Cyclone Preparedness and Response- SPR-OHN-SAF-026. Port and Rail General Cyclone Procedure. SPR-PHS-SAFES-001. Port and rail Cyclone Travel Management Plan. SPR-RHS-SAF-018.
|  | Safety | Heat illness and dehydration. | Adequate water not provided Personnel not acclimatised Drug and alcohol use FFW Strenuous labour Inadequate shade | LTI/RWC | Moderate | Possible | Possible,Moderate | High (13) | Continually promote water intake / Toolbox / Pre-start / Take 5 / Water bottle - ODG supplied / Clean ice & water on hand/PPE Hydration testing Continually promote use of heat protection i.e. wide brim hats, water intake / Toolbox / Pre-start / Self monitoring / Shade where possible |  |  |  |  | x | x | Moderate | Unlikely | Unlikely,Moderate | Moderate (9) | FFW Policy,
|  | Safety | Lightning strike to personnel | Lightning procedure not followed Working when lightning is present | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Use of 30/30 rule for lightning / Pre-start awareness training Lightning Detectors |  |  |  | x | x |  | Major | Unlikely | Unlikely,Major | High (14)
27 | Hazardous Substance/waste Disposal | Safety / Environment | Damage to flora & fauna Personal injury or illness Exposure to hazardous substances. | No correct disposal available No bunding | LTI/RWC | Moderate | Possible | Possible,Moderate | High (13) | The use of an approved BHPBIOBIO Contractor for the correct disposal of all waste Recycling to be promoted at all times |  |  |  | x |  |  | Moderate | Unlikely | Unlikely,Moderate | Moderate (9)
28 | Transport/Delivery of Precast slabs. | Safety / Environment | Crush injuries handling and positioning heavy precast slabs | Body parts in line of fire of moving heavy object. Inadequate job planning and resourcing | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | WMS, JHA, Take 5 to address risk of being hit by moving concrete slabs. Gloves to be worn. Tag lines to be used for directing loads.Apply National Code of Practice for Precast Tilt‐Up and Concrete Elements in Building Construction. |  |  |  |  | x | x | Major | Unlikely | Unlikely,Major | High (14) | Lifting Operations- Fatal Risk Control Standard, Cranage Lifting, Slinging. SPR-IHS-SAF-029
|  | Safety | Incorrect Plant Use | Risk assessment not completed Lifting charts not used | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Information on anchor footing to be supplied / Lifting charts to be used / JHA / Take 5 As per WMS SPR-HIS-SAF-029 FRCP10, |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14) | Lifting Operations- Fatal Risk Control Standard, Cranage Lifting, Slinging. SPR-IHS-SAF-030
|  | Safety | Incompetent Operator | Incompetent/unauthorised Operator VOC/Qualifications not confirmed prior to mobilisation WAIO training requirements not followed | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | VOC Operator (plant specific) / Plant check sheet / JHA / Take 5 |  |  |  |  | x |  | Major | Rare | Rare,Major | High (14) | Lifting Operations- Fatal Risk Control Standard, Cranage Lifting, Slinging. SPR-IHS-SAF-031 Unload and load checklist
|  | Safety | Manual Handling Injuries | Incorrect technique Mechanical aids not used | LTI/RWC | Moderate | Possible | Possible,Moderate | High (13) | Mechanical Aids/Safe Spine Training |  | x |  |  | x |  | Moderate | Unlikely | Unlikely,Moderate | Moderate (9)
|  | Safety | Entrapment | Barricading not in place poor communication | LTI/RWC | Moderate | Possible | Possible,Moderate | Extreme (18) | No personnel are to be within the excavation whilst the mast/signal base is being lifted into position. Personnel can only enter the excavation once the lifting chains have been removed. | x | [5 empty] | Moderate | Unlikely | Unlikely,Moderate | High (14)
|  | Safety | Underated Lifting Equipment | Lifting equipment not inspected prior to use | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Lifting equipment checked & tagged for correct SWL / WLL Tag lines to be used ,SPR-HIS-SAF-029 FRCP10 |  |  |  |  | x |  | Major | Rare | Rare,Major | High (10)
|  | Safety | Unstable Ground Conditions | Ground conditions not inspected JHA/take 5 not completed | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Ground to be checked for underground services, pits & trenches / JHA / Take 5 SPR-HIS-SAF-001, |  |  |  |  | x |  | Major | Rare | Rare,Major | High (10)
29 | Transport- (Heavy rigid & Heavy combination) entering/exiting at Crossing | Safety | Collision with Locomotive | Inadequate rail protection. Inadequated sighting of rail corridor | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Transport Driver to call-up T.P.O on approach to Crossing. Location specific Traffic Management Plan prepared by certified Traffic Management provider, approved by MRD and fully and effectively implemented. Signage inc radio call up channel. |  |  |  | x |  |  | Major | Rare | Rare,Major | High (10) | Follow signage and existing procedure to cross BILO. General Alerts to be issues and Operating Notices/ Instructions as required.
30 | Installing/removing footings | Safety | Lifting Plinth into Position (dropped loads ) | Lift study not completed Pre-starts and inspections of crane and crane gear not completed | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Lift Study (if required) / JHA / Take 5 / Lift check list / Test Lift (if required)SPR-HIS-SAF-029 FRCP10, |  |  |  |  | x |  | Major | Rare | Rare,Major | High (10)
|  | Safety | Incorrect Lifting | Operator not competent | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | VOC Rigger (plant specific) / Tag lines to be used / Test lift (if required),FRCP10, Ensure load travel path is free from obstacles or contact with infrastructure. |  |  |  | x |  |  | Major | Unlikely | Unlikely,Major | High (14)
31 | New Batteries Installation - Gel Cells | Safety | Manual Handling | Poor technique no mechanical aids | LTI/RWC | Moderate | Possible | Possible,Moderate | High (13) | Safe Spine Training / Mechanical Aids / Suitable PPE |  |  |  | x |  |  | Moderate | Rare | Rare,Moderate | Moderate (6)
|  | Safety / Environment | Acid Leaks onto personnel | PPE not used Double eye protection not in place | LTI/RWC | Moderate | Possible | Possible,Moderate | High (13) | Rubber gloves / Double eye protection / Apron / Spill kit | [5 empty] | x | Moderate | Unlikely | Unlikely,Moderate | Moderate (9)
|  | Safety / Environment | Fumes from batteries Volatile Vapours | Correct PPE not in place | LTI/RWC | Moderate | Possible | Possible,Moderate | High (13) | Vent all SER before entering / Face mask / MSDS apron PVC gloves No naked flame allowed in SER / Vent SER / Fire Fighting Equipment / Suitable PPE | x | [5 empty] | Moderate | Rare | Rare,Moderate | Moderate (6)
|  | Safety / Environment | Incorrect Wiring | Operator not competent in task | LTI/RWC | Moderate | Possible | Possible,Moderate | High (13) | Only Trained Electrical Signalling personal to connect |  |  |  |  | x |  | Moderate | Rare | Rare,Moderate | Moderate (6)
|  | Safety / Environment | Mains Power isolation breach | Correct isolation training not achieved or inspected prior to task | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Isolate - Module 2 & 3 ONLY / Disconnect / Check / Test / Tag / JHA / Take 5 FRCP8 SPR-HIS-SAF-024, Ensure competent person has performed the isolation |  |  |  | x |  |  | Major | Rare | Rare,Major | High (10) | Isolation and Permit to work on low voltage electrical installations. SPR-IHS-SAF-024.
|  | Safety | Electric shock/Burns from batteries | Incorrect handling and use | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Isolate and Cover terminals, use correct and insulated tools for the task. Ensure competent person/s undertake task |  |  |  |  | x | x | Major | Unlikely | Unlikely,Major | High (14) | General Electrical Procedures SPR-IHS-SAF-085. Isolation and Permit to work on low voltage electrical installations. SPR-IHS-SAF-024.
32 | Under rail/road boring | Safety / Environment | Under ground services | Permits not obtained Risk assessment not conducted | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Permits approved, VOC of operator's JHA, TAKE 5 up to date CSM plans SPR-HIS-SAF-001. Cable locator. |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14)
|  | Safety | Person/s getting caught in moving parts. | Guards missing | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Complete plant specific pre‐start checks to ensure guarding in place. Isolate and Lock Out/Tag Out. |  |  |  |  | x |  | Major | Rare | Rare,Major | High (14)
|  | Safety | Unstable footing, loose ballast and slippery rail | Approved PPE not used Eyes not on path | LTI/WRC | Moderate | Possible | Possible,Moderate | High (13) | Approved lace up footwear, Take 5,do not step on rail, re-iterate at pre-starts. |  |  |  |  | x | x | Moderate | Unlikely | Unlikely,Moderate | Moderate (9)
33 | Termination of Cables | Safety | Cuts | Approved equipment not used to cut cables | LTI/WRC | Moderate | Possible | Possible,Moderate | High (13) | Approved cable stripping tool to be used, suitable gloves No Stanley Knives |  |  | x |  |  | x | Moderate | Rare | Rare,Moderate | Moderate (6)
34 | Switchboards | Safety | Untrained workforce | Personnel not qualified or competent in task | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Trained & Licensed WA Electricians / Verify Licence / Register |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14)
35 | Packing Containers | Safety | Unsecured Items | Items not secured or stored correctly | MTI/FAI | Minor | Possible | Possible,Minor | Moderate (8) | Secure items on floor / Lay tall items down / Package accordingly | x | [5 empty] | Minor | Rare | Rare,Minor | Low (3)
|  | Safety / Environment | Chemicals mixed | No MSDS Chemical storage procedure not followed | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Separation of chemicals / MSDS / Chemical storage cabinets / clear labelling |  |  |  | x |  |  | Major | Rare | Rare,Major | High (10)
36 | Refurbishing Site Areas | Safety / Environment | Items Left at Site | Area not inspected prior to demobilisation | MTI/FAI | Minor | Possible | Possible,Minor | Moderate (8) | Client to sign area off | x | [5 empty] | Minor | Rare | Rare,Minor | Low (3)
37 | Atmospheric Contaminants, including silica, asbestos | Health | Excessive dust reduces visibilty on roads, site and increases dust inhalation risk to personnel. Exposure to airborne particles. | Lack of effective dust suppression. No monitoring (hygienist) | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Wear suitable respiration. Adhere to Code of Practice for the Safe Removal of Asbestos 2nd Edition [NOHSC:2002(2005)],Code of Practice for the Management and Control of Asbestos in Workplaces. Barricades/Signage. Continued monitoring of suspect worksites, water suppression where possible and thorough risk assessment before work commences. |  |  |  |  | x | x | Major | Unlikely | Unlikely,Major | High (14)
|  | Health | Untrained personnel entering worksite | Area not inspected Asbestos areas not barricaded Personnel not qualified/competent | Fatality/Permanent disability | Major | Likely | Likely,Major | Extreme (21) | WMS, JHA, Take 5, Barricades, Signage, appropriate PPE and conform to Asbestos CoP's. |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14)
|  | Health | Plant and Equipment not decontaminated | Area not inspected Asbestos areas not barricaded Personnel not qualified/competent | Fatality/Permanent disability | Major | Possible | Possible,Major | Extreme (18) | Adhere to Code of Practice for the Safe Removal of Asbestos 2nd Edition [NOHSC:2002(2005)],Code of Practice for the Management and Control of Asbestos in Workplaces, Supervision - |  |  |  |  | x |  | Major | Rare | Rare,Major | High (10)
|  | Health | Wearing Fibrous Material PPE in excessive heat. | Heat stress | Fatality/Permanent disability | Major | Likely | Likely,Major | Extreme (21) | Wearing of breathable coveralls, limit work periods to 20 minutes. Pre works hydration monitoring and documentation. Constant hydration during task using 'Camelback hydration back-pack' |  |  |  |  | x |  | Major | Unlikely | Unlikely,Major | High (14)
|  | Health | Water cart breakdown | Not inspected or maintained | LTI/WRC | Major | Rare | Rare,Major | High (10) | Portable spray containers to be readily available. Second water cart to be arranged/and available if needed. Water cart to be inspected and operation tested prior to arrival on site. |  |  |  |  | x |  | Major | Rare | Rare,Major | High (10)
Do not change or delete
|  |  | Consequence | Likelihood | Risk Assessment Matrix
|  |  | Low | Almost Certain | Likelyhood,Consequence | Risk
|  |  | Minor | Likely | Almost Certain,Low | High (11)
|  |  | Moderate | Possible | Almost Certain,Minor | High (16)
|  |  | Major | Unlikely | Almost Certain,Moderate | Extreme (20)
|  |  | Critical | Rare | Almost Certain,Major | Extreme (23)
[5 empty] | Almost Certain,Critical | Extreme (25)
[5 empty] | Likely,Low | Moderate (7)
[5 empty] | Likely,Minor | High (12)
[5 empty] | Likely,Moderate | High (17)
[5 empty] | Likely,Major | Extreme (21)
[5 empty] | Likely,Critical | Extreme (24)
[5 empty] | Possible,Low | Low (4)
[5 empty] | Possible,Minor | Moderate (8)
[5 empty] | Possible,Moderate | High (13)
[5 empty] | Possible,Major | Extreme (18)
[5 empty] | Possible,Critical | Extreme (22)
[5 empty] | Unlikely,Low | Low (2)
[5 empty] | Unlikely,Minor | Low (5)
[5 empty] | Unlikely,Major | High (14)
[5 empty] | Unlikely,Moderate | Moderate (9)
[5 empty] | Unlikely,High | High (14)
[5 empty] | Unlikely,Critical | Extreme (19)
[5 empty] | Rare,Low | Low (1)
[5 empty] | Rare,Minor | Low (3)
[5 empty] | Rare,Moderate | Moderate (6)
[5 empty] | Rare,Major | High (10)
[5 empty] | Rare,Critical | High (15)
|  | Yes |  |  |  | Elimination
|  | No |  |  |  | Substitution
Engineering/ Redesign
Separation/ Isolation
Administration
PPE
Safety
Health
Environment
Heritage
Community
Loss/Damage
Note on L4: Mark the relevant control with an "x"
Note on L5: Eliminate the Hazard
Note on M5: Substitute the hazard or risk
Note on N5: Redesign the equipment or work process
Note on O5: Separate the hazard by guarding or enclosing it
Note on P5: Introduce administrative controls
Note on Q5: Provide personal protective equipment
Note on W5: Eliminate the Hazard
Note on X5: Substitute the hazard or risk
Note on Y5: Redesign the equipment or work process
Note on Z5: Separate the hazard by guarding or enclosing it
Note on AA5: Introduce administrative controls
Note on AB5: Provide personal protective equipment

## ACTIONS
Risk Assessment Action Plan |  |  | BiLo Crossing Upgrade
Item | Risk Assessment Reference # | Action | Responsiblility | Due Date
1
2
3
4
5
6
7
8
9
10
11
12
13
14

## Consequence and Likelyhood Tbl
WAIO Risk Assessment Matrix (FRM-IHS-000-007)
CONSEQUENCE TABLE
Consequence | Health & Safety | Environment | Community / Media / Government |  | Loss / Damage
LOW | First aid treatment | Limited damage to area or low significance | Public concern restricted to local complaints |  | $0-$15K
MINOR | Medical Treatment | Minor short-term damage to environment / heritage | Minor, adverse local public or media attention and complaints |  | $15K-$150K
MODERATE | Classified Injury (LTI or restricted workcase) | Moderate effects on environment / heritage | Attention from media and / or heightened concern from community |  | $150K-$1.5M
MAJOR | Fataility or severe permanent disability | Significant environmental / heritage damage | Significant advers national media/public attention |  | $1.5M-$15M
CRITICAL | Multiple fatalities / healt effects to > 50 persons | Severe damage to environment / heritage with long-term effects | Serious public or media outcry |  | $15M-$150M
LIKELIHOOD TABLE |  |  |  | Likelihood | Consequence
Likelihood | Description | Frequency at Location |  |  | Low | Minor | Moderate | Major | Critical
ALMOST CERTAIN | Expected to happen | Occurs once a week |  | Almost certain | High (11) | High (16) | Extreme (20) | Extreme (23) | Extreme (25)
LIKELY | May easily happen | Occurs once a month |  | Likely | Moderate (7) | High (12) | High (17) | Extreme (21) | Extreme (24)
POSSIBLE | May happen | Occurs once every year |  | Possible | Low (4) | Moderate (8) | High (13) | Extreme (18) | Extreme (22)
UNLIKELY | May happen sometime | Occurec once every 10 years |  | Unlikely | Low (2) | Low (5) | Moderate (9) | High (14) | Extreme (19)
RARE | May happen in extreme circumstances | Occurs once every 100 years |  | Rare | Low (1) | Low (3) | Moderate (6) | High (10) | High (15)

## BowTie
|  |  | 4. Existing Controls (Preventative) |  |  |  | 5. Existing Controls (Reactive)
| IRON ORE ~BOW TIE ~ |  | No. | Existing Preventative Controls | Control Owner |  | No. | Existing Reactive Controls |  | Control Owner
|  |  | 4a | WAIO, Rail, local area inductions - Take 5 JHA | HSE Manager |  | 5a | Emergency Procedures |  | Rail Ops Manager |  |  | No HSEC Impacts
|  |  | 4b | Barricading - fencing, boom gates, gates | T&S Manager |  | 5b | ESO & ERT |  | HSE Manager |  |  | HSEC Impacts only
|  |  | 4c | Fatal Risk Control Protocols | HSE Manager |  | 5c | Stop relevant operational activities |  | Rail Ops Manager |  |  | HSEC & other Impacts
|  |  | 4d | 15 Standards - site PPE requirements | HSE Manager |  | 5d | Evacuations |  | Rail Ops Manager
|  |  | 4e | Radio, Rulebook Training, fatigue management | Rail Ops Manager |  | 5e | Incident Investigations (ICAM), SIR |  | Rail Ops Manager |  |  | 20-30% Getting started
|  |  | 4f | Operating procedures | Rail Ops Manager |  | 5f | Internal/External inquiry |  | GM Rail |  |  | 30-50% Under way
| Risk Context |  | 4g | Community awareness campaigns | Public Affairs Manager |  | 5g | Public Affairs |  | Public Affairs Manager |  |  | 50-60% Past half way
| Interaction with rail mounted vehicle |  | 4h | Signage, CCTV | T & S Manager |  | 5h | Internal/External Communication |  | Public Affairs Manager |  |  | 60-70% Good progress
|  |  | 4i | Supervision | Relevant manager |  | 5i | Just Culture |  | HR Manager |  |  | 70-80% Almost there
|  |  | 4j | Train control signalling system / communication | Rail Ops Manager |  | 5j | [5 empty] | >90% Review and monitor
2. Causes | [12 empty] | Change in ESVA
No. | Cause | Type | [10 empty] | Change in project return (-NPV)
2a | Lack of awareness of rules & consequences | L | [8 empty] | 3. Impacts |  | Health and safety
2b | Trespassing / unauthorised access | L | [8 empty] | No. | Impact | Natural environment
2c | Insufficient level of protection | R | [8 empty] | 3a | Fatality or injury | Social/Cultural Heritage
2d | Increase in number of rail vehicles | L | [8 empty] | 3b | Public image / outcry | Community/Govt/ Reputation/Media
2e | Incorrect work location | R |  |  |  | Ineffective surface water management |  |  |  |  | 3c | Loss of production | Legal
2f | Lack/misinterpretation of communication | L |  |  |  | adequately remediated |  |  |  |  | 3d | Property damage
2g | unauthorised movement | D | [8 empty] | 3e | Temporary closure of site
2h | uncontrolled movement | D | [8 empty] | 3f | Business interuption
2i | Overlapping work areas (Port & Rail) | L | [8 empty] | 3g | Loss of licence to operate
2j | Poor or lack of isolation | R | [8 empty] | 3h | Psycological trauma
2k | Segregation - lack of | L | [8 empty] | 3i
2l | Inexperience / lack of knowledge | L | [8 empty] | 3j
2m | Work culture / complacency | L | [8 empty] | 3k
2n | Line of vision /obstruction | L
2o | Sabotage | D
2p | Mischievious actions | L
Types of Causes
Root (R) = First event in cause-effect chain |  |  | 6. Risk Control Action Plan
Latent (L) = Due to environment |  |  | No. | Risk Control Action |  |  |  |  | Due Date | Task Owner
Direct (D) = Results in the event |  |  | 6a | Continue with community awareness program | [5 empty] | Richard O'Connell
|  |  | 6b | Review risk control mechanisms annually utalising available risk management tools & resources | [5 empty] | All Rail Managers
|  |  | 6c | Review current site internal communication stakeholder lists (quarterly review and update) | [5 empty] | All Rail Managers
|  |  | 6d | Run emergency situation simulations - annually | [5 empty] | HSE Manager
|  |  | 6e | Review of FRCP & HSEC self assessment/audit outcomes (PIP) | [5 empty] | All Rail Managers
|  |  | 6f | Procedure for runaway rail vehicles | [5 empty] | Rail Ops Manager
|  |  | 6g | Review current integration of planning scheduling with Port and Rail day to day operations | [5 empty] | Rail Ops Manager
|  |  | 6h | Ensure Saferworking Rules, Standards & Procedures are adequate and reviewed | [5 empty] | Rail Ops Manager
|  |  | 6i | Implementing ZIP, PRAISE & SAO's | [5 empty] | All Rail Managers
6j
| Other Information |  | Ratings Basis
| Accountable Manager | [8 empty] | Impact Type: | HSEC
| Peter Hanrahan |  | Single fatality and or severe permanent disability. Impact Type: HSEC Severity: 30 Likelihood: 1 | [6 empty] | Severity: | 30
[10 empty] | Likelihood: | 1
Control Self Assessment Score (%)
| 30 | [8 empty] | Residual Risk Rating: | 30
Maximum Foreseeable Loss (US$M) Assessment:
| Type of Impact (HSEC and/or other) |  | Loss could equate between US$1M < US$10M | [6 empty] | MFL (US$M): | US$10M
HSEC
Maximum Foreseeable Loss (Fatality) Assessment:
|  |  | Fatality - single | [6 empty] | MFL (Fatalities): | 1
Risk Comments
1. Risk Issue
Interaction with rail mounted vehicle
Identify potential risks that could cause a fatality/ severe or permanent disability.
Event(s)
Struck by rail mounted vehicle.
EXISTING PREVENTATIVE & DETECTIVE CONTROLS
EXISTING PREVENTATIVE & DETECTIVE CONTROLS

## BowTie_Examples
|  |  | 4. Existing Controls (Preventative) |  |  |  | 5. Existing Controls (Reactive)
| IRON ORE ~BOW TIE ~ |  | No. | Existing Preventative Controls | Control Owner |  | No. | Existing Reactive Controls |  | Control Owner
|  |  | 4a | Culture Program Charter Actions | K. Bright |  | 5a | [5 empty] | No HSEC Impacts
|  |  | 4b | Graduate recruitment program | C. Wilbur |  | 5b | [5 empty] | HSEC Impacts only
|  |  | 4c | International Recruitment Program | K. Bright |  | 5c | [5 empty] | HSEC & other Impacts
|  |  | 4d | Labour Policy review | C. Wilbur |  | 5d
|  |  | 4e | Workforce Planning Charter Actions | K. Bright |  | 5e | [5 empty] | 20-30% Getting started
|  |  | 4f | Implementation of Housing Strategy (Phase 1&2) | C. Wilbur |  | 5f | [5 empty] | 30-50% Under way
| Risk Context |  | 4g |  |  |  | 5g | [5 empty] | 50-60% Past half way
| People |  | 4h |  |  |  | 5h | [5 empty] | 60-70% Good progress
|  |  | 4i |  |  |  | 5i | [5 empty] | 70-80% Almost there
|  |  | 4j |  |  |  | 5j | [5 empty] | >90% Review and monitor
Change in ESVA
Change in project return (-NPV)
2. Causes | [10 empty] | 3. Impacts |  | Health and safety
No. | Cause | Type | [8 empty] | No. | Impact | Natural environment
2a | Growth programs | R | [8 empty] | 3a | Delay in project completion | Social/Cultural Heritage
2b | Market competition | L | [8 empty] | 3b | Limited growth capacity | Community/Govt/ Reputation/Media
2c | Mining in remote locations | R |  |  |  | Ineffective surface water management |  |  |  |  | 3c | Faliure to meet production targets | Legal
2d | Shortage of Housing | R |  |  |  | adequately remediated |  |  |  |  | 3d | Increased labour cost/recruitment costs
2e | Failing to attract skilled personnel | L | [8 empty] | 3e | Increased capital costs for housing
2f | Failing to retain skilled personnel | L | [8 empty] | 3f | Loss of business knowledge
2g | Lack of diversity in hiring | L | [8 empty] | 3g | Third Party intervention in Labour Relations
2h | Management of Gen-Y | L | [8 empty] | 3h
2i | Increased turnover rate | D | [8 empty] | 3i
2j | Poaching by competitors | L | [8 empty] | 3j
2k | Changes in Federal IR Legislation | L | [8 empty] | 3k
2l
2m
Types of Causes
Root (R) = First event in cause-effect chain |  |  | 6. Risk Control Action Plan
Latent (L) = Due to environment |  |  | No. | Risk Control Action |  |  |  |  | Due Date | Task Owner
Direct (D) = Results in the event |  |  | 6a | Recruitment Blitz |  |  |  |  | 2008-01-10 | K. Bright
|  |  | 6b | AWA Support Program actions |  |  |  |  | 2008-10-10 | C. Wilbur
|  |  | 6c | etc
|  |  | 6d | etc
6e
6f
6g
6h
6i
6j
| Other Information |  | Ratings Basis
| Accountable Manager |  | Residual Risk Rating Assessment: | [6 empty] | Impact Type: | Financial
| M. Smith |  | FY08 Planned Production = 120MT. Estimated 2008 Labour Cost= (WAIO=345M)+(Brazil=21M)= TOTAL = US$366M. 2012: Production = 155MT. Most likely Case Price per tonne (Mid) = US$22.6 over 5 years. Worst Case Price per tonne (High) = US$28.2 over 5 years. Discount Rate = 6.2%. Most Likely Scenario: Under-resourced to deliver planned budget resulting in 10% increased labour cost margin over 5 years = 366M * 10% * 5= US$183M = NPV=USM154M = NPV = 100. Likelihood=1. Impact Type: Financial Severity: 100 Likelihood: 1 | [6 empty] | Severity: | 100
[10 empty] | Likelihood: | 1
Control Self Assessment Score (%)
| 82 | [8 empty] | Residual Risk Rating: | 100
Maximum Foreseeable Loss (US$M) Assessment:
| Type of Impact (HSEC and/or other) |  | Worst Case Scenario: Under-resourced to deliver RGP4 planned budget (155MT by 2012) resulting in 20% labour cost margin over 5 years before labour market stablises= 500M (mean increase to 2012) * 20% * 5 years = Gross US$500M = US$420M NPV. | [6 empty] | MFL (US$M): | 420
HSEC and Other
Maximum Foreseeable Loss (Fatality) Assessment:
|  |  | N/A. | [6 empty] | MFL (Fatalities): | 0
Risk Comments
1. Risk Issue
Skilled Resources
Context of risk: Shortage of skilled resources to meet current and growth forecasts until 2012 (RGP4 - 155MT). Market competition, growth strategies, remoteness of WAIO operations and lack of housing are some of the contributing factors to this risk resulting in loss of opportunity thereby leading to reduced EBIT.
Event(s)
Shortage of skilled resources.
Example

## ACTION ITEMS
ACTION ITEMS FROM RISK ASSESSMENT
BiLo Crossing Upgrade
Issue # | Action # | Area | Unplanned/unwanted Event (Issue) | Cause | Impact | New Actions / Futher Requirements | Actioned by Who | Actioned By When | Status 1 - Incomplete 2 - Progressing 3 - Complete | Comments | Required for Trial / Full Operation
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43