## Sheet2
1 | The base document that is broken up into six sections; 1. Overview, 2. Quality, 3. WHS, 4. Enviro, 5. Traffic, 6. Records and 7. Responsibilities. Is it possible in the Table of Contents to make a minor change to the titles? eg. Section 1. Overview, Section 2.Quality Mgt, Section 3. WHS Mgt, Section 4. Environment etc. This may just highlight the different sections and make it clear for users of the document. | Alan Richo: SC_CSMP - Council System Management Plan - Final.doc changed and TOC updated
2 | References to staff roles that are not existent. There are a lot of places where roles and responsibilities need to be sorted | Alan Richo: To be completed by Client?
3 | Some references are not understood eg, SHEQ Management system, QIR, SIM, Site Inspection Lists, Decision Report, | Alan Richo: SC_CSMP - Council System Management Plan - Final.doc edited SHEQ Management System changed to WHS Management System QIR change to ? SIM change to ? Site Inspection Lists change to ? Decision Report change to ?
4 | Management Corporate Objectives need to be reviewed and agreed by senior management. (emailed appropriate sections to Jason, Mark, Damian, Conor for feedback / endorsement. 02/07/2020. Not expecting any change) | Alan Richo: To be completed by Client?
5 | Some documents and procedures are referenced in this Management Plan but haven't been provided as part of the submission. These are; Training Needs Analysis; Internal Audit Procedure; Tool and Equipment Register; Plan for Minor Works; Site Safety Rule Handout; Site Safety Rules; Inspection Report Form; Safety Incident Plan; Environmental Emergency Plan; Environmental Work Method Statements, Project Records Register. Request to Peter - Can we have a copy of these documents or templates | Alan Richo: To be completed by Client?
6 | Sections regarding Design - largely unused as to date all works have been maintenance related. Some of the design requirements need to be discussed. Some comments recieved from Sam Masoomi in relation to design | Alan Richo: To be completed by Client? Client comments: "Discussed design requirements with Sam Masoomi. Infrastructure Services are working to re-establish in-house design team and they will probably have involvement in delivering RMCC design works (if applicable)."
7 | Selection of Contractors refers to Councils Prequalified Contractor List. No Prequalified Contractor List. At the moment there are Plant Hire Rates, Trade & Miscellaneous Services and Regional Procurement Tenders. Discuss creation of a Prequalified Contractor list specific to RMCC. | Alan Richo: To be completed by Client?
8 | There are no ITP's provided with the submission. | Alan Richo: To be completed by Client? Note Council System Management Plan (CSMP) Att .6 Project Quality Representative > Project Coordinator RMCC to be Council’s Project Quality Representative (PQR) with delegated authority from, and responsibility to, the General Manager for the maintenance of the QMP. > Responsibilities: Preparing inspection/test plans
9 | Some documents/processes are referred to and capital letters aren't used eg. 'work method statement'. | Alan Richo: Alan Richo: SC_CSMP - Council System Management Plan - Final.doc edited
10 | Some of the responsibilities are not clear. eg. Director Planning and Infrastructure is mentioned throughout the document but is not included in Annexure A- Responsibilities. The Manager Infrastructure Delivery is not mentioned in Annexure A-Responsibilities. Direct Planning and Infrastructure is listed in Section 2. Management requirements, yet not in Annexure A-Responsibilities. | Alan Richo: To be completed by Client? Difficult to complete without heirarchy of reporting and list of responsibilities?
11 | Training refers to people having appropriate licenses or certificates. Discussion is needed to clarify certificates, competencies, familiarisation etc. email sent to Conor/Pam 01/07/2020 and response recieved. | Alan Richo: To be completed by Client?
12 | There are conflicting references within the document to the staff who are nominated as 24 hour emergency contacts. | Alan Richo: Arne R comments "24 hour contacts are Civil Operations Coordinator and Project Coordinator". SC_CSMP - Council System Management Plan - Final.doc and Attachment 1 Project organisation structure, responsibilities and contact details changed to reflect comments.doc. Request for Client to confirm primary / secondary 24hr contacts?
13 | A Work Health Safety Consultation Policy is provided. The WHS Consultation Policy will need to be reviewed by members of Integrated Risk, for endorsement by General Manager. | Alan Richo: To be completed by Client?
14 | Work Health Safety Policy is provided. This needs to be reviewed by members of Integrated Risk team, for endorsement by General Manager. Specific responsibilities section. | Alan Richo: To be completed by Client?
15 | A Risk Assessment Matrix is provided. This is different to the council standard matrix. | Alan Richo: To be completed by Client?
16 | A hierarchy of control is provided. This is different to the council standard hierarchy of control. | Alan Richo: To be completed by Client?
17 | There is no reference to the new TfNSW requirement of the 5 minutes reporting for Significant Incidents. | Alan Richo: Does it apply https://www.rms.nsw.gov.au/assets/ssiep/poster-significant-safety-incident-protocol.pdf? If so Where does the Client want this reference to be inserted?
18 | Incidents and Accident reporting forms are referred to. No reference to DoneSafe. | Alan Richo: SC_CSMP - Council System Management Plan - Final.doc changed Incidents and Accident Reporting Forms based on Client comments "suggest referring to Councils Incident Reporting Management System". Unsure on how Client wants to differentiate on incendent reporting between employees and contractors with reference to "At site induction training all personnel will be informed of their responsibility for reporting unsafe work practices and unsafe work conditions..."
19 | Register of Injuries is mentioned. Check how Risk Management monitor workplace injuries. | Alan Richo: Client to clarify further pls
20 | Rehabilitation Policy is referenced. I dont think this policy exists. Refer to ""Injury Mgt and Recover at Work Procedure"". | Alan Richo: SC_CSMP - Council System Management Plan - Final.doc changed
21 | Need to source a list of employee training records, especially for traffic control. | Alan Richo: To be completed by Client?
22 | UV Clothing Policy is referenced. Councils policy is called Workwear Policy. | Alan Richo: SC_CSMP - Council System Management Plan - Final.doc changed
23 | Records Management-Technical Specifications - there are a lot of Specifications that haven't been used and are unlikely to be used. Suggest including more regularly used specifications. R107, R101, R116, R141, R142. | Alan Richo: Request Client to identify technical specification sub-clauses to be referenced in SC_CSMP - Council System Management Plan - Final.doc. Note https://www.rms.nsw.gov.au/business-industry/partners-suppliers/document-types/specifications/qa/roadworks.html#Pavement(Bituminous),R101-R126. Alternatively, could paste complete table from 4.1 Hold Point Schedule (Rev 1.0).xls?
24 | Disaster Management. A number of strategies are mentioned. Do these match what council has in place?. Seek advice for what council has in place for Disaster Management. | Alan Richo: To be completed by Client?
25 | The document refers to retrieval time objectives for records - seek feedback from Information Management on whether these match. | Alan Richo: To be completed by Client?
26 | In Appendix A-Responsibilities. No reference to 'Team Leader'. | Alan Richo: Can't locate "Appendix A-Responsibilities" in SC_CSMP - Council System Management Plan - Final.doc
27 | Appendix A. Formatting needs to be tidied up. Indent tabs etc. | Alan Richo: Can't locate "Appendix A-Responsibilities" in SC_CSMP - Council System Management Plan - Final.doc
28 | Hazard Identification & Control Table. - Some hazards don't apply to roadworks and can be removed. | Alan Richo: Request Client to idenditfy hazards for removal?
29 | Plant Requirement- seems to be missing some information. | Alan Richo: Request Client to idenditfy what information to be included?

## Sheet1
SINGLETON COUNCIL ROADS MAINTENANCE COUNCIL CONTRACT (RMCC)
SECTION | FOLDER | DOCUMENT | NOTES | Alan Richardson's comments
Council System Management Plan Ed1 V1 |  |  | SEE WORKSHEET "SHEET2" 1. The base document that is broken up into six sections; 1. Overview, 2. Quality, 3. WHS, 4. Enviro, 5. Traffic, 6. Records and 7. Responsibilities. Is it possible in the Table of Contents to make a minor change to the titles? eg. Section 1. Overview, Section 2.Quality Mgt, Section 3. WHS Mgt, Section 4. Environment etc. This may just highlight the different sections and make it clear for users of the document. 2. References to staff roles that are not existent. There are a lot of places where roles and responsibilities need to be sorted 3 Some references are not understood eg, SHEQ Management system, QIR, SIM, Site Insection Lists, Decision Report, 4. Management Corporate Objectives need to be reviewed and agreed by senior management. (emailed appropriate sections to Jason, Mark, Damian, Conor for feedback / endorsement. 02/07/2020. Not expecting any change) 5. Some documents and procedures are referenced in this Management Plan but haven't been provided as part of the submission. These are; Training Needs Analysis; Internal Audit Procedure; Tool and Equipment Register; Plan for Minor Works; Site Safety Rule Handout; Site Safety Rules; Inspection Report Form; Safety Incident Plan; Environmental Emergency Plan; Environmental Work Method Statements, Project Records Register. Request to Peter - Can we have a copy of these documents or templates 6. Sections regarding Design - largely unused as to date all works have been maintenance related. Some of the design requirements need to be discussed. Some comments recieved from Sam Masoomi in relation to design 7. Selection of Contractors refers to Councils Prequalified Contractor List. No Prequalified Contractor List. At the moment there are Plant Hire Rates, Trade & Miscellaneous Services and Regional Procurement Tenders. Discuss creation of a Prequalified Contractor list specific to RMCC. 8. There are no ITP's provided with the submission. 9. Some documents/processes are referred to and capital letters aren't used eg. 'work method statement'. 10. Some of the responsibilities are not clear. eg. Director Planning and Infrastructure is mentioned throughout the document but is not included in Annexure A- Responsibilities. The Manager Infrastructure Delivery is not mentioned in Annexure A-Responsibilities. Direct Planning and Infrastructure is listed in Section 2. Management requirements, yet not in Annexure A-Responsibilities. 11. Training refers to people having appropriate licenses or certificates. Discussion is needed to clarify certificates, competencies, familiarisation etc. email sent to Conor/Pam 01/07/2020 and response recieved. 12. There are conflicting references within the document to the staff who are nominated as 24 hour emergency contacts. 13. A Work Health Safety Consultation Policy is provided. The WHS Consultation Policy will need to be reviewed by members of Integrated Risk, for endorsement by General Manager. 14. Work Health Safety Policy is provided. This needs to be reviewed by members of Integrated Risk team, for endorsement by General Manager. Specific responsibilities section. 15. A Risk Assessment Matrix is provided. This is different to the council standard matrix. 16. A hierarchy of control is provided. This is different to the council standard hierarchy of control. 17. There is no reference to the new TfNSW requirement of the 5 minutes reporting for Significant Incidents. 18. Incidents and Accident reporting forms are referred to. No reference to DoneSafe. 19. 'Register of Injuries' is mentioned. Check how Risk Management monitor workplace injuries. 20. Rehabilitation Policy is referenced. I dont think this policy exists. Refer to "Injury Mgt and Recover at Work Procedure". 21. Need to source a list of employee training records, especially for traffic control. 22. UV Clothing Policy is referenced. Councils policy is called Workwear Policy. 23. Records Management-Technical Specifications - there are a lot of Specifications that haven't been used and are unlikely to be used. Suggest including more regularly used specifications. R107, R101, R116, R141, R142. 24. Disaster Management. A number of strategies are mentioned. Do these match what council has in place?. Seek advice for what council has in place for Disaster Management. 25. The document refers to retrieval time objectives for records - seek feedback from Information Management on whether these match. 26. In Appendix A-Responsibilities. No reference to 'Team Leader'. 27. Appendix A. Formatting needs to be tidied up. Indent tabs etc. 28. Hazard Identification & Control Table. - Some hazards don't apply to roadworks and can be removed. 29. Plant Requirement- seems to be missing some information. | SEE WORKSHEET "SHEET2"
Construction | Project Specific Plan - Construction (Rev 1.0) |  | 1. Within the PSP there isn't any reference to managing quality. No Quality Mgt Plan has been provided. There is no Safety Mgt Plan referenced in the PSP. 2. A number of documents are referred to that haven't been provided as part of the submission; eg. Project Communication Plan; Reference is made to a council General Induction Package. Does council currently have an induction package? 3. Reference is made to council gravel pits, of which there are none. | Alan Richo: 1. SC_CSMP - Council System Management Plan - Final.doc contains Quality and WHS Management Plans. Maybe insert reference plans in SC PSP-Construction (Rev 1.0).docx 2. Communication Plan referenced in Att 1.1 Communication plan requests reader to refer to Attachment 13.3 Workers on Foot Management Plan Section 5 for worksite communication. Is this adequate? 3. Please confirm if all references to council gravel pits, quarries etc. in document be removed?
| Att-2 Works Program | empty | No template provided
| Att-3 Purchasing Plan | 3.1 Purchasing Plan Rev 1.0 | Good. Minor change
| Att-4 Schedule of Hold Points | 4.1 Hold Point Schedule | 1. The document refers to RMS specifications but doesn't provide Edition numbers or Revision numbers for these specifications. 2. In G22 the clause numbers for Hold Points don’t match up with the specification. I checked with six specifications (R11, R53, R71, R101, R107 and R116) and in most cases the clause numbers did not match up to the specification. 3. The bottom section of the timing column is missing information. | Alan Richo: 1. Perhaps reference could be inserted into document 4.1 Hold Point Schedule (Rev 1.0).xls to visit RMS QA roadworks specifications https://www.rms.nsw.gov.au/business-industry/partners-suppliers/document-types/specifications/qa/roadworks.html for current version. 2.Updated document 4.1 Hold Point Schedule (Rev 1.0).xls to reflect TRANSPORT FOR NSW(TfNSW) QA SPECIFICATION R11 STORMWATER DRAINAGE downloaded from https://www.rms.nsw.gov.au/business-industry/partners-suppliers/document-types/specifications/qa/roadworks.html. Downloaded version declares “unsuitable material” replaced by “inadequate foundation material” though document document 4.1 Hold Point Schedule (Rev 1.0).xls still references "unsuitable material". I updated clause and hold points (description and timing) for R11 only in document 4.1 Hold Point Schedule (Rev 1.0).xls to reflect downloaded version. Do you want me to update R53, R71, R101, R107 and R116 to reflect versions located at https://www.rms.nsw.gov.au/business-industry/partners-suppliers/document-types/specifications/qa/roadworks.html for current version. 3. 226x line items for "Timing" to be completed in document 4.1 Hold Point Schedule (Rev 1.0).xls. Do you want me to complete?
| Att-5 Inspection and Test Schedule | 4.2 Inspection and Test Schedule (Rev 1.0) | Some roles and responsibilities need clarification. Note. | Alan Richo: To be completed by the Client?
| Att-6 Audit and Review Schedule | 6.1 Internal Audit Schedule Rev 1.0 | Typo | Alan Richo: Spellcheck completed.
| Att-7 Environmental | 7.1 Environmental Legislation (Rev 1.0) | Very detailed list of legislative requirements to be met on construction projects. | Alan Richo: Yes, to be expected.
| Att-8 Environmental Management Plans | 8.1 Construction Environmental Management Plan | Very comprehensive plan suitable for a construction project. 1. Some of the document references are not valid - or - the forms have not been made available. 2. Some roles and responsibilities need clarifying. 3. Plan references council 'Local Environmental Officer', no role currently within council. 4. Is there a requirement to provide a Qual Management Plan and a Safety Management Plan, in the same format as this CEMP? | Alan Richo: 1. Some of the document references are not valid - or - the forms have not been made available. Is the Client responsible to prepare these forms not sighted to date or are these avilable elswhere? 2. Some roles and responsibilities need clarifying. Client to specify 3. Plan references council 'Local Environmental Officer', no role currently within council. Client to specify who performs role in council. 4. Is there a requirement to provide a Quality Management Plan and a Safety Management Plan, in the same format as this CEMP? Presume management plans captured by SC PSP-Construction (Rev 1.0)?
|  | 8.2 Waste Minimisation and Management Plan | Some roles and responsibilities need clarification. Useful guidance for waste treatments | Alan Richo: To be completed by the Client?
|  | 8.3 Wet Weather Management Plan | Good. A couple of typos | Alan Richo: Spellcheck completed.
|  | 8.4 Unexpected Threatened Species Finds Procedure | Good | NA
|  | 8.5 Unexpected Heritage Finds Procedure | Good | NA
| Att-9 Project Risk Assessment | 9.1 Project Risk Assessment | Letterhead from Walgett Shire Council. Questions about use of this template in place of the Council Integrated Risk forms and procedures. This template Allows for Safety, Environmental and Journey Management risks so it is unique to state road works. Risk Matrix is slightly different | Alan Richo: Singleton Council logo inserted to header of document. Does the Client want to replace with organisational document?
| Att-10 Induction Package | empty | empty | NA
| Att-11 Emergency Procedures | 5.1 Emergency Incident Plan | There is no reference to Singleton Local Emergency Plan and the specific roles set up eg. LEMO. This plan also doesn't make any reference to the new RMS requirement SIGNIFICANT SAFETY INCIDENT ESCALATION PROCEDURE (5 minutes). Also no reference in the document to Business Continuity. | Alan Richo: Request Client to identify specific location in document/procedure new RMS requirement SIGNIFICANT SAFETY INCIDENT ESCALATION PROCEDURE (5 minutes)
| Att-12 Supplementary Management Plans | 14.1 COR Management Plan | Question about using this Management Plan in place of the Integrated Risk COR Mgt Plan. Consider substituting this will councils COR Mgt Plan. | Alan Richo: To be completed by the Client? I can't sight copy of the Integrated Risk COR Mgt Plan
| Att-13 Traffic Management Plans | 9.2 Workers on Foot Plan | Good. Some roles and responsibilities need clarification | Alan Richo: To be completed by the Client?
| Att-15 Project Forms | 15.1 Hold Point Release Form | Form doesn't have a Singleton Council logo. Suggest minor editing | Alan Richo: Singleton Council logo inserted to header of document.
|  | 15.2 Non Conformance Report (NCR) | Good. Maybe a line to identify source of Non Conformance Report (eg, Quality, Safety, Env) | Alan Richo: Client to clarify request.
|  | 15.3 NCR Register | Form doesn't have Singleton Council logo. Some editing needed | Alan Richo: Singleton Council logo inserted to header of document.
|  | 15.4 Corrective Action Request (CAR) | Can the NCR Report and the CAR have the same format for simplicity? Two very similar forms with different formats. | Alan Richo: Aligned formatting of documents.
|  | 15.5 CAR Register | The CAR Register and NCR Register are similar forms with very different formats. Can these use the same format type? | Alan Richo: Aligned format of two documents.
|  | 15.6 Site Environmental Checklist | OK
|  | 15.7 Site WHS Checklist | OK
|  | 15.8 Risk Assessment Form | Question about using this Risk Assessment Form in place of the Integrated Risk document. Both are blank templates which include Hierarchy of Controls, Risk Matrix. Differences: Council form allows for breakdown into Tasks/Activities. Also includes Training Requirements, List of Codes of Practice. Peters form just allows for Risk, Risk Score and Controls. Has a section for typical risks. Is there a benefit in moving away from the council template? | Alan Richo: To be completed by the Client?
|  | 15.9 Toolbox Meeting Record | Form doesn’t have Singleton Council logo. The form is similar to the Council form. Is there a benefit in moving away from the council template? | Alan Richo: Singleton Council logo inserted to header of document.
|  | 15.10 Receiving Inspection Form | References to a Form 115. Unsure of this form. | Alan Richo: To be completed by the Client?
|  | 15.11 Council Incident Form (to be inserted) | Incidents to be reported through DoneSafe computer system. Council Form made available | Alan Richo: To be completed by the Client?
|  | 15.12 Council Daily Plant Inspection (to be inserted) | Daily Plant Checklists uploaded on computer tablets. Council Form made available | Alan Richo: To be completed by the Client?
|  | 15.13 Daily TC Checklist -Traffic Control At Worksites | TCP Checklist which may need modifying to suit Council. References Walgett Shire Council in Header | Alan Richo: Reference to Walgett Shire Council removed. Singleton Council logo inserted to header of document.
|  | 15.14 Traffic control at Worksites Location checklist | RMS standard Checklist from TCAWS. | Alan Richo: Singleton Council logo inserted to header of document.
|  | 15.15 TCAWS Appendix E | RMS standard Checklist from TCAWS. | Alan Richo: Singleton Council logo inserted to header of document.
|  | 15.16 Work Verification Checklist | This must be the verification document to say we are doing our verification checks. Some minor changes | Alan Richo: Client to clarify request.
|  | 15.17 Management Review Agenda | We might do a Management Review meeting one day | Alan Richo: To be completed by the Client?
|  | 15.18 Management Review Meeting Minutes | And we have minutes | Alan Richo: To be completed by the Client?
|  | 15.19 Rainfall Chart | Missing Council Logo - Header | Alan Richo: Singleton Council logo inserted to header of document.
|  | 15.20 Register of Waste and Recyclable Materials | Minor change | Alan Richo: Completed minor change.
|  | 15.21 EHSMS Environmental, Health and Safety Management System Audit Tool | Very comprehensive audit tool. | NA
|  | 15.22 Hired Plant and Operator Checklist | Checklist seens to be missing some basic checks such as operation of Brakes, Flashing beacon fitted, Two Way Radio fitted, Safe Working Loads displayed. Form missing Singleton Council logo | Alan Richo: Logo inserted to document. Client to update checklist to reflect organisational needs.
|  | RMS Form COR Self Assessment | Standard RMS form | Alan Richo: Client to clarify request.
|  | RMS Form 259c - RMCC SPR Field Data Collection | Standard RMS form | Alan Richo: Client to clarify request.
|  | RMS Form 901 - Contractor Pre-engagement Questionnaire | Standard RMS form | Alan Richo: Client to clarify request.
|  | RMS Form 904 - Contractor WHS Checklist | Standard RMS form | Alan Richo: Client to clarify request.
|  | RMS Form 905 - Contractor Environmental Checklist | Standard RMS form | Alan Richo: Client to clarify request.
|  | RMS Form 906 - Contractor Quality Checklist | Standard RMS form | Alan Richo: Client to clarify request.
|  | RMS Form 907 - Contractor ITP Checklist | Standard RMS form | Alan Richo: Client to clarify request.
|  | RMS Form 908 - Contractor Traffic Checklist | Standard RMS form | Alan Richo: Client to clarify request.
|  | RMS Form 909 - Contractor Work Method Statement Review Checklist | Standard RMS form | Alan Richo: Client to clarify request.
|  | RMS Form 911 - Contractor Verification Surveillance Checklist | Standard RMS form | Alan Richo: Client to clarify request.
| Att-16 ITP's | empty
| Att-17 SWMS | empty
| Other Procedures | Handling and Storage Procedure | Minor changes | Alan Richo: Client to clarify request for roles and responsibilites insert
|  | Identification and Traceability Procedure | Document missing Singleton Council logo | Alan Richo: Logo inserted to document.
|  | Inspection and Testing Procedure | Some changes required. | Alan Richo: Client to accept on changes in the document.
Maintenance | Project Specific Plan - Maintenance (Rev 1.0) |  | 1. A number of references made to processes or documents. Some have capital letters but there is inconsistency eg. 'Ordered Works', 'ordered works'. 2. Question about whether we refer to Spec G10 or G10M for purposes of the contract (or both). This may need to be clarified by RMS. 3. Some recent changes to Reactive and Routine maintenance (now Corrective, Amenity and Scheduled maintenance) may need to re-worded. 4. A Plan for Minor Works document is mentioned but none provided with the submission. 5. Table of road segments. Road information inputted. Can there be an additional column for Road Category. Can there be another table added to include Amenity areas. 6. A lot of sections will need clarification of roles and responsibilities. 7. Adjustments have been suggested to the Project Organisational Structure. 8. Project Management Team - Clarify who are the 24 hour contacts. Four people are listed currently.
| Att 2 - Maintenance System Procedures | MSP-01 Asset Inspection System | 1. Some changes may be required that reflect the new M3 Specification. Reactive Maintenance has been removed and now the categories are; Corrective, Amenity, Scheduled. 2. Asset Inspection Calendar - Check that these are still being produced. Possibly now done as 'Planned Work' ? 3. Priority Table Guide - Maybe just a reference that these response times are a guide only and that M3 should be referred to for detailed response times.
MSP-02 Managing Requests
|  | MSP-03 Defect Management | 1. Some changes may be required that reflect the new M3 Specification, especially removal of Reactive Maintenance. Intervention Frequency is no longer referenced, only Intervention Standard. 2. A lot of roles and responsibilities need to be clarified.
|  | MSP-04 Scheduling | Roles and responsibilities need to be clarified. Roads Project Officer is not referenced.
|  | MSP-06 Ordered Works | A reference to DMT is not understood. Can this be changed. Some clarification of roles and responsibilities.
|  | MSP-07 Incident Response | 1 A reference to TSS is not understood. 2.Also reference to a Recovery Procedure for Motor Vehicle Accidents and a Vehicle Removal (Unattended / Abandoned Vehicles) Report form. Are these standard RMS documents? 3. As evidence required, consider adding Police Event Number which is a Hunter region requirement.
|  | MSP-08 Managing Third Party Claims | • A process flow chart is provided. It is unclear at some stages whether the responsibilities are for Council or TfNSW.
|  | MSP-09 Recording Accomplishments | • Significant changes to M3 spec means that Work group names have changed, along with some Activity titles. Unfortunately this section will need to be re-worked to reflect changes in M3.
| Att 3 - Maintenance Activity Procedures | MAP-110 Asset Inspection | • Due to changes in M3 spec, there are only two types of inspection; Safety Inspection and Scheduled Inspection. Changes are needed to explain the two inspection types. | Some activities don't have a MAP. These include Remove Non Critical Graffiti (332), Seal Pavement Crack (211), Sweep Road Pavement (272), Repair drainage Structure (521), Maintain Stormwater improvement Device (526), Maintain Wire rope safety barrier (621)
|  | MAP 201 Pothole Repair | • Minor change. Pothole now fall under Corrective category
|  | MAP 202 Edge Repair | • Edge Repair is now in the Corrective category
|  | MAP 203 Repair Wearing Surface | • Repair Wearing surface category is now called Corrective
|  | MAP 204 Minor Pavement Patch | • Minor Pavement Patch category is now called Corrective
|  | MAP 221 - 222 - 223 - 224 Unsealed Pavement | This Procedure can be removed. No unsealed pavement within network.
|  | MAP 241 - 242 - 243 Unsealed Shoulder | • Activity 243 (Incorporate New Shoulder Material) is no longer included in M3 Specification
|  | MAP 301 - 339 Remove Litter Sweep Roadway | • Activity 301 changed to Remove Dead Animal (Corrective). • Activity 339 changed to Collect Roadside Litter (Amenity Maintenance-Roadside). • Some sections regarding safety ramps and snow banks can be removed. • Activity description may need changing to reflect new M3 specification
|  | MAP 302 Remove Graffiti | • Activity 302 changed to Remove Critical Graffiti • Activity description may need changing to reflect new M3 specification
|  | MAP 303 Reactive Roadside Maintenance | • Activity 303 no longer exists in M3 Specification
|  | MAP 311 Control Ground Veg (Mowing and Slashing) | • Change in M3 Specification. Slashing is now covered under Activity 321. • Table of Minimum sight distances and stopping distances, no longer referenced by new M3 Spec.
|  | MAP 311B Control Ground Veg (Chemical) | • Change in M3 Specification. Weed Spraying is now covered under Activity 322. • Table of Minimum sight distances and stopping distances, no longer referenced by new M3 Spec.
|  | MAP 312 - 316 - 317 Control Veg - Tree and Bush | • Change in M3 Specification. Trim Tree branch Activity 312. Remove tree 316 • Reporting Accomplishment table needs to be changed to reflect new M3 Spec. • Table of Minimum sight distances and stopping distances, no longer referenced by new M3 Spec.
|  | MAP 319 Maintain Landscaping | • Change to reference activity Weed Spraying.
|  | MAP 333 - 613 Repair Fencing | • Change to activity titles in M3 Specification. Repair Fauna and Boundary Fence - Activity 333. Reinstate Safety Barrier and Pedestrian Fence - Activity 612
|  | MAP 351 Maintain Roadside Slope | • No change
|  | MAP 354 Renew Rockfall Protection Fencing Netting | • Change to activity title - Repair Rock Fall Protection Fencing and Netting.
|  | MAP 355 Renew Retaining Wall | • Change to activity title - Repair Retaining Wall.
|  | MAP 420 - 480 Service Toilet Rest Area | • Change to Activity numbers. • No servicing of toilets in current RMCC. • Reference to other Veg control procedures which have incorrect Activity numbers
|  | MAP 511 Renew Surface Drain | • Change in M3 specification. Repair surface drain - Activity 522. Clean Surface drain - Activity 525 • New M3 Specification now uses m for unit of measures. • This MAP only covers repair works and doesn't include surface drain cleaning. Consider including or create new MAP for cleaning
|  | MAP 513 Clean Culvert | • Change to activity title - Clean Drainage Structure Activity 524. • Change to M3 Specification. Activity 524 covers all drainage structures, not just culverts.
|  | MAP 515 Clean Drainage Pit | • New M3 Specification. Activity 515 no longer exists. Refer to MAP 524 -Clean Drainage Structures
|  | MAP 611 Maintain Non Pavement Delineation | • New M3 Specification. Activity 611 name changed to 'Reinstate Non-Pavement Delineation'. • Note. 'Programmed works must be done under a Plan for Minor Works using Technical Procedures' probably not relevant to this task.
|  | MAP 612 Renew Safety Barrier | • New M3 Specification. Activity 612 name changed to 'Reinstate Safety Barrier'. • Could this MAP also include Activity 622 Maintain Steel Safety Barrier.
|  | MAP 614 - 616 Signs Maintain Replace | • New M3 Specification. Activity 601 no longer exists. • Activity 614 Name changed to Reinstate sign. • Activity 615. Name changed to Scheduled Sign Replacement. Activity 616. Name changed to Clean or Adjust Sign. • Modify activity description to match new M3 Specifications.
| Att 4 - Schedules - Inspection Test Audit and Hold Point | 4.1 Hold Point Schedule - Maintenance | • Specification column doesn’t include Edition and Revision Numbers. • Some of the reference clauses don’t match up to the Specification. • Some activities such as Clearing and Grubbing, Pavement Construction are not likely to be used or not a current maintenance activity. These could be removed.
|  | 4.2 Inspection and Test Schedule (Rev 1.0) | • Some roles and responsibilities need clarification • No ITP's have been provided which means they would need to be generated in house
|  | 4.3 Internal Audit Schedule | • Notification to Director Planning and Infrastructure of the Management Review resonsibility
| Att 5 - Emergency Procedures | 5.1 Emergency Incident Plan | • Same document as Emergency Incident Plan for Construction.
| Att 6 - Maintenance Induction Package | Empty
| Att 7 - Safe Work Method Statements (SWMS) | Empty | • Will need to include SWMS relevant to Road maintenance activities
| Att 8 - Environmental Management Plans | 8.1 Environmental Legislative Requirements Register | Very detailed list of legislative requirements to be met on construction projects.
|  | 8.2 Waste Management Plan | Some roles and responsibilities need clarification. Useful guidance for waste treatments
|  | 8.3 Erosion and Sediment Control Plan | Good. A couple of typos
|  | Environmental Assessment Procedure for Routine and Minor Works | Standard RMS form
|  | Environmental Assessment Procedure for Routine and MW - Standard Safeguards List | Standard RMS form
|  | Environmental Assessment Procedure for Routine and MW - Activity Checklist | Standard RMS form
|  | Environmental Fact Sheet - Noxious Weed Management | Standard RMS form
| Att 9 - Traffic Management Plans | 9.2 Workers on Foot Plan | Good. Some roles and responsibilities need clarification
| Att 11 - Reports | Form 259C - Field Data Collection Sheet for Systems Performance Report (SPR) | Standard RMS form
| Att 12 - Forms | 15.1 Hold Point Release Form | Form doesn't have a Singleton Council logo. Suggest minor editing. Suggest sending Peter a copy of councils current HPR, NCR and CAR forms. Would be nice to have a similar format style for each form.
|  | 15.2 Non Conformance Report (NCR) | Good. Maybe a line to identify source of Non Conformance Report (eg, Quality, Safety, Env). Suggest sending Peter a copy of councils current HPR, NCR and CAR forms. Would be nice to have a similar format style for each form.
|  | 15.3 NCR Register | Form doesn't have Singleton Council logo. Some editing needed. Would be nice to have the same format style for both NCR, HPR and CAR register
|  | 15.4 Corrective Action Request (CAR) | Can the NCR Report and the CAR have the same format for simplicity? Two very similar forms with different formats. Suggest sending Peter a copy of councils current HPR, NCR and CAR forms. Would be nice to have a similar format style for each form.
|  | 15.5 CAR Register | The CAR Register and NCR Register are similar forms with very different formats. Some editing needed. Would be nice to have the same format style for both NCR, HPR and CAR register
|  | 15.6 Site Environmental Checklist | OK
|  | 15.7 Site WHS Checklist | OK
|  | 15.8 Risk Assessment Form | Question about using this Risk Assessment Form in place of the Integrated Risk document. Both are blank templates which include Hierarchy of Controls, Risk Matrix. Differences: Council form allows for breakdown into Tasks/Activities. Also includes Training Requirements, List of Codes of Practice. Peters form just allows for Risk, Risk Score and Controls. Has a section for typical risks. Is there a benefit in moving away from the council template?
|  | 15.9 Toolbox Meeting Record | Form doesn’t have Singleton Council logo. The form is similar to the Council form. Is there a benefit in moving away from the council template?
|  | 15.10 Receiving Inspection Form | References to a Form 115. Unsure of this form.
|  | 15.11 Council Incident Form (to be inserted) | Incidents to be reported through DoneSafe computer system. Council Form made available
|  | 15.12 Council Daily Plant Inspection (to be inserted) | Daily Plant Checklists uploaded on computer tablets. Council Form made available
|  | 15.13 Daily TC Checklist -Traffic Control At Worksites | TCP Checklist which may need modifying to suit Council. References Walgett Shire Council in Header
|  | 15.14 Traffic control at Worksites Location checklist | RMS standard Checklist from TCAWS.
|  | 15.15 TCAWS Appendix E | RMS standard Checklist from TCAWS.
|  | 15.16 Work Verification Checklist | This must be the verification document to say we are doing our verification checks. Some minor changes
|  | 15.17 Management Review Agenda | We might do a Management Review meeting one day
|  | 15.18 Management Review Meeting Minutes | And we have minutes
|  | 15.19 Rainfall Chart | Missing Council Logo - Header
|  | 15.20 Register of Waste and Recyclable Materials | Minor change
|  | 15.21 EHSMS Environmental, Health and Safety Management System Audit Tool | Very comprehensive audit tool.
|  | 15.22 Hired Plant and Operator Checklist | Checklist seens to be missing some basic checks such as operation of Brakes, Flashing beacon fitted, Two Way Radio fitted, Safe Working Loads displayed. Form missing Singleton Council logo
|  | RMS Form COR Self Assessment | Standard RMS form
|  | RMS Form 259c - RMCC SPR Field Data Collection | Standard RMS form
|  | RMS Form 901 - Contractor Pre-engagement Questionnaire | Standard RMS form
|  | RMS Form 904 - Contractor WHS Checklist | Standard RMS form
|  | RMS Form 905 - Contractor Environmental Checklist | Standard RMS form
|  | RMS Form 906 - Contractor Quality Checklist | Standard RMS form
|  | RMS Form 907 - Contractor ITP Checklist | Standard RMS form
|  | RMS Form 908 - Contractor Traffic Checklist | Standard RMS form
|  | RMS Form 909 - Contractor Work Method Statement Review Checklist | Standard RMS form
|  | RMS Form 911 - Contractor Verification Surveillance Checklist | Standard RMS form
| Att 13 - Project Risk Assessment (HVCoR) | 13.1 Example Project Risk Assessment HVCoR
| Att 14 - Chain of Responsibility Management Plan | 14.1 COR Management Plan | Question about using this Management Plan in place of the Integrated Risk COR Mgt Plan. Consider substituting this will councils COR Mgt Plan.
| Other Documents | Project Organisational Structure | An amended Project Organisational Structure has been suggested in the PSP - Maintenance. This fits closer to councils current operations.
No ITP's have been provided which means they would need to be generated in house
Meeting with Jen Rudder 06/07/2020
| • A WHS Consultation Policy is provided. This will need to be reviewed by members of Integrated Risk - or – replaced with councils policy - for endorsement by General Manager. | Refer to councils IRM Consultation and Communication Procedure. Copy on intranet
| • A Work Health Safety Policy is provided. This needs to be reviewed by members of Integrated Risk – or – replaced with council policy for endorsement by General Manager. Specific responsibilities section. | Refer to WHS Statement of commitment. Can be included in the document.
| • A Risk Assessment Matrix and Hierarchy of Control is provided. These are different to the council standard matrix but is more specific to road related activities as it does include Journey Management. | Refer to councils standard Risk Assessment at this point.
| I would prefer to use the council endorsed Risk Assessment but note that this document is more specific to work on a main road. | Change to councils Hierarchy of Control to keep consistency.
| • Incidents and Accident reporting forms are referred to. No reference to DoneSafe. May require some wording to detail this process. | Refer to councils Incident Management Procedure. Have the Donesafe screenshot as an attachment.
| • 'Register of Injuries' is mentioned. Will require some detail on how Council manages workplace injuries. | Electronic register. Jenny to provide some detail on this.
| • A Rehabilitation Policy is referenced. I don’t think this policy exists. Refer to "Injury Mgt and Recover at Work Procedure" ?. | As above
| • A UV Clothing Policy is referenced. Refer to council’s “Workwear Policy” | Councils Workwear Procedure
| • Disaster Management. A number of strategies are mentioned. Do these match what council has in place?. Seek advice for what council has in place for Disaster Management/ Business Continuity | Council has Emergenvcy Mgt Procedure, Local Emergency Management Operations( Damian), Emergency Response Procedure,
| • The document refers to retrieval time objectives for records - seek feedback from Business Continuity Plan | Seek advice from Records and/or John Harding. Compare objectives. Reference the BCP. Not necessarily share this Plan. Critical sub-function plans
Question for Peter - What is the source or reference document for meeting WHS and Environmental requirements (eg. Emergency Incident Plan)
Note> Any reporting to SafeWork NSW to be done by Intergrated Risk
Send a copy of COR Mgt Plan to Jen for review.
Need to check if there is any reference to say how often this document is to be reviewed.
Note on C8: Redemski, Arne: Highlighted documents are duplicated elsewhere