w

WET WEATHER MANAGEMENT PLAN

Project Name:	RMCC

Contract No.:

Road No.:		Sate Controlled Roads

Contents

- Introduction									3

- Description of works and program					3

- Site locations and conditions						3

- Weather patterns in the works area					4

- Monitoring weather conditions 						4

- Resources and contractors on site 					5

6.1	Basic list of planned resources

6.2	Resource breakdown for the various stages of work

- Steps to minimise losses due to wet weather impacts		6

7.1	Planning of works

7.2	Effective on site management

7.3	Redeployment of resources

8.  Records and potential subsequent claims 				7

1.	 Introduction

This Wet Weather Contingency Plan provides information on how Council intends to plan and manage works in the event of adverse weather conditions and also how to minimize the risk to works, and in turn mitigate against losses, in the event of adverse weather conditions.

Adverse weather conditions include rain, wind, hail, lightning and any other weather condition that is likely to affect the overall outcome of the works, bring a halt to the works or affect the safety of workers.

The plan is to be used in works management and as a field guide for the Works Supervisor, Team Leaders and Contractors.

2.	 Description of Works and Program

The works for which this Wet Weather Contingency Plan relates is for the project known as the Example Project Name

The project consists of rehab works on culverts and roadworks including:

- Excavate and Cast in-situ base slabs

- Extend culverts with pre-cast units,

- Form up and cast in-situ headwalls and wing walls

- Anchor all precast units together also to base slab and existing pre-cast cells.

- Concrete aprons with toe wall

- Backfill with westlime DGB gravel and compact

- Excavate AUL, BAR and Shoulders to required depth.

- Fill with select layers and compact to achieve required density.

- Polvi full pavement width to a depth of 150mm to achieve 100mm below FSL.

- Import HD DGB westlime gravel to achieve a 100mm overlay.

- Mix and modify to a depth of 175mm below FSL with 1.5% 70/30 slag/lime

- Trim for 10mm primer seal / 5mm scatter coat

The works are expected to commence on ????? and be completed by end of ????.

3.	Site Locations and Conditions

3.1 	Location

3.2 	Conditions Affecting Contingency Planning

4.	Weather Patterns in the Works Area

The climate in the Singleton Council area is generally hot and dry in summer and cool and wet in winter.

The work is to be carried out in the Autumn to Winter months. The mean rainfall for this period is 40 mm per month with a mean of 4 days rain per month.

In winter, settling rain is likely which can produce lengthy, but heavy showers, wind and even hail.

5.	 Monitoring Weather Conditions

Forecasts will be obtained from the Bureau of Meteorology web site both leading up to and during the course of the works. www.bom.gov.au

As well as checking the forecast weather a constant check will be placed on actual weather conditions and an assessment made using local weather knowledge and forecast conditions to determine and risk to the works.

6.	 Resources and Contractors on site.

6.1 	Basic list of planned resources

| Site Office & Portable Toilets Traffic Lights Backhoe | Utility Work Truck / Concrete Variable Message Boards x 2 |
| --- | --- |

6.2	Resource breakdown for the various stages of work

Establishment, Traffic Control, sediment control

Utility x 2 Labour x 3 Traffic Controller x 3 Variable Message Boards x 2

Culvert Works

| Back hoe Labour x 3 Utility x 2 | Tipping Trucks x1 Traffic control (as above) |
| --- | --- |

Earthworks

| Grader Roller (padsfoot) Roller (smooth drum) Water Truck Utility | Tipping Trucks x4 Traffic control (as above) Stabilising Machine Spreader Truck |
| --- | --- |

7.	 Steps to Minimise Losses Due to Wet Weather Impacts on Works

7.1	Planning of Works

- The Road Project Officer will be responsible for checking the forecast weather prior to the works commencing and assessing whether the works should commence.

- Careful consideration will be given to the maximum amount of road to be exposed to wet weather at any one time. It is necessary to strike a balance between managing risk and achieving suitable economies of scale to carry out the works in a cost competitive manner.

- Effective sediment, erosion and drainage controls to be implemented early in the project so as to control the water movement past and through the site, and lessen the risk of damage to works due to unconstrained, high velocity flows.

- Placement of material and sequencing so as not to create low points that pool water and risk the material becoming over-wet.

7.2 	Effective management of Works

- If poor weather is forecast or threatening, exposed culvert works areas will be shaped to as to aid the quick draining of water.

- Drainage of working areas are to be maintained at all times

7.3 	Redeployment of Resources

- Short duration adverse weather may simply result in minor delays. However, prolonged adverse weather may result in ceasing the work for an extended period of time.

- Short duration of say less than 4 hours, work will be stopped temporarily but plant and workers will remain on site.

- For periods of say between 4 hours and 1 day, plant will remain on site unless local work can be organized. Workers will be relocated to other works and contractors will be sent away.

- For adverse weather lasting more than 1 day, plant will be relocated to other works, labour will be relocated to other works and contractors will be sent away.  Alternate works may include maintenance of the nearby sections of table drains, delineation, signs, and so forth.

8.	Records and Potential Subsequent Claims

The Daily Weather Record Sheet will be completed on daily basis and a proforma is included in the PSP Attachment 15 - Forms

In the event of adverse weather conditions, the Council will notify the Principal as soon as practicable as to the nature and expected delay time, so that the Principal has the opportunity to inspect the situation first hand.

The Road Project Officer will keep a record of any additional works due to adverse weather conditions and record the adverse weather start time, work that was in progress, resources on site, actions taken by Council to minimise the damage to the works and the length of the delay.

Council recognises that under the terms of the contract it is our responsibility to prepare all necessary supporting records to demonstrate the additional cost incurred, including, without limitation, details of weather conditions at the site, hours of work time lost, plant (idle or active) and labour onsite, details of damage caused by the wet weather and details of the costs of replacement materials

If Council determines it will need to claim for losses it will notify the TfNSW within 5 Business Days of the end of the relevant wet weather event.